2. Introduction
The desk appraisal of the Annual Work Plan and Budget (AWP&B) for the year 2009-10 was undertaken by an Appraisal Team consisting of the following members: Ms. Amita Singla, Ms. Deepti Bansal, Shri. O.P Nautiyal, Shri. Adil Rasheed, Shri. S.C. Girotra, Shri. Amit Saxena, Ms. Kiran Dogra, Dr. Anupriya Chadha, Shri. Jyoti Prakash Mohanty and Shri. Jitendre Kr. Panda; all from TSG. 

State Profile
	Area
	50362 Sq. Kilometer 

	Districts 
	20

	Tehsils
	72

	Sub Tehsils 
	81

	CD Blocks
	141

	Educational Block
	216

	Towns
	143

	Inhabited Villages
	12711

	Density
	484 people per sq.km.

	Literacy Total 
	69.70%

	Male Literacy 
	75.20%

	Female Literacy 
	63.40%

	Population                Total
	24358999

	Male
	12985045

	Female
	11373954

	Rural
	16096488

	Male
	8516596

	Female
	7579892

	Urban
	8262511

	Male
	4468449

	Female
	3794062

	SC Population 
	7028723 (29% of the total) 

	Male
	3714350

	Female
	3314373

	Rural
	5318254

	Male
	2807876

	Female
	2510378

	Urban
	1710469

	Male
	906474

	Female
	803995

	Sex Ratio-             Total
	876

	Rural
	890

	Urban
	849

	Total Literates
	14756970

	Rural Literates 
	9008431

	Urban Literates 
	5748539

	0-6 Population-    Total
	3171829  (13% of the total)

	Male
	1763801

	Female
	1408028

	Rural
	2176726

	Male
	1209856

	Female
	966870

	Urban
	995103

	Male
	553945

	Female
	441158


Basic Administrative Indicators

	SNo.
	Name of Districts
	No. of Educational Blocks (if any)
	No. of BRC/UBRCs*
	No. of CRCs
	No. of villages/ Wards*
	No. of Panchayats

	1
	Amritsar
	17
	8
	100
	918
	815

	2
	Barnala
	3
	3
	21
	221
	146

	3
	Bathinda
	6
	8
	41
	414
	314

	4
	Faridkot
	5
	2
	27
	248
	178

	5
	Fatehgarh Sahib
	6
	5
	47
	518
	432

	6
	Ferozepur
	19
	10
	115
	1404
	1356

	7
	Gurdaspur
	22
	16
	181
	1539
	1522

	8
	Hoshiarpur
	19
	10
	148
	1671
	1362

	9
	Jalandhar
	19
	10
	113
	996
	899

	10
	Kapurthala
	7
	5
	63
	793
	552

	11
	Ludhiana
	19
	12
	112
	1146
	924

	12
	Mansa
	5
	5
	34
	328
	244

	13
	Moga
	6
	5
	40
	387
	351

	14
	Mohali
	7
	4
	57
	432
	408

	15
	Muktsar
	6
	4
	38
	319
	319

	16
	Nawanshaher
	8
	5
	51
	529
	443

	17
	Patiala
	14
	8
	115
	1099
	981

	18
	Ropar
	8
	5
	60
	773
	653

	19
	Sangrur
	11
	9
	77
	765
	575

	20
	Tarntaran
	9
	8
	59
	532
	477

	 
	Punjab 
	216
	142
	1499
	15032
	12951


Planning Process:

Participatory Planning: The process of planning and implementation of elementary education is participatory in nature. 

· Planning and implementation teams at village, cluster, block, districts and state level. 

· Capacity building exercises like seminars, workshops and field visits etc. organized to orient and prepare the teams to formulate elementary education plans. 

· Districts plans formulated by DEDCs. 

· All the districts plans combined and compiled into State Annual Plan for SSA. 

· Sharing of ideas and information with all concerned functionaries at village, cluster, block, districts and state level 
Some of the meetings and workshops held at state level for the purpose of planning for 2009-10 are enumerated below:

	SNo.
	Date/s
	Activity
	Participants

	1.
	15th /16th 08. 08
	Planning on Gender Education  
	State level officers and District Gender Coordinators

	2.
	22.08.08
	Orientation of district teams for plan formulation
	District Education Officers (Elementary Education), District SSA Coordinators & Assistant Project Coordinators (General) & Assistant Project Coordinators (General).

	3.
	16.09.08
	Training on DISE software
	District MIS Coordinators

	4.
	23.09.08
	Training through EDUSAT on filling up of DISE Formats
	District MIS Coordinators

	5.
	14.10.08
	Review of DISE data 
	District MIS Coordinators

	6.
	5.12.08 to 12.12.08
	Field review for DISE
	Visit of all the districts by State level representatives for  checking DISE data

	7.
	7.01.09
	Submission of DISE data
	District MIS Coordinators

	8. 
	16.01.09
	Discussions on Civil works district plan for 2009-10 and revised norms thereof
	District Education Officers (Elementary Education),  District SSA Coordinators,

	9.
	17.01.09
	Workshop on Plan formulation for 2009-10 regarding revised financial norms and interventions under SSA
	District Education Officers (Elementary Education), District SSA Coordinators, District Resource Persons (Planning) & Assistant Project Coordinators (General).

	10.
	22.01.09
	Discussions on updation of HHS data 2008 for OOSC and deciding strategies to cover OOSC in 2009-10
	District AIE Coordinators

	11.
	30.1.09
	Reviewing district level Civil works requirements at SPO 
	District Resource Persons (Civil works) and Sub Divisional Engineers

	12.


	12.02.09
	Finalization of Component wise plans, data tables and financial norms
	District SSA Coordinators, District Resource Persons (Planning) & Assistant Project Coordinators (General).

	13.
	16.02.09
	Appraisal of civil works Plan for 2009-10
	District Resource Persons (Civil works) and Sub Divisional Engineers

	14.
	19.02.09    to 23.02.09
	Appraisal of district Plans  
	District Resource Persons (Planning), Assistant Project Coordinators (General) & Assistant Project Coordinators (Finance).

	15. 
	24.02.2009
	Submission of District plans
	District Education Officers (Elementary Education), District SSA Coordinators & Assistant Project Coordinators (General) & Assistant Project Coordinators (General).


3. Education Indicators: 
Enrolment:

· The state overall enrolment at primary level is increased by 50% and 36% at Upper Primary level. Table:1 

· District Nawashahar has almost no increase and also report a minor decrease in girls enrollment (213 girls) at upper primary level.Table:1

· Girls enrolment has increased with 44%(from 752537 to 1083834) at Primary level and with 31% (from 460116 to  601616 )at upper primary level against last year Table:1
· During year 08-09 under %girls parameter districts Fatehgarh Sahib (43.4%), Kapurthala (43.4%), Bathinda (43.38%), Patiala (43.35%), Mansa (43.26%) & Barnala (43.24%) reports comparatively very low %share of girls against state average of 44.19% at primary level and same districts reports low % share of girls at Up. Primary Level against state average (44.47%). Table:1
· The overall SC enrolment has increased by 20% at Primary & by 16% at Up. Primary level. District Nawashahar reports a minor decrease (from 18228 to 18166).Table:2
Single Teacher School:
As per DISE 2008 there are 1300 single teacher schools. After appointing 10678 primary and 4405 upper primary teachers the position has improved to a significant level. This is hereby clarified that the aforesaid new appointments were done in the months of November and December. There is no single teacher school at primary and no two teacher school at upper primary level as of now. Table: 4
Completion Rate: Table: 5

· Completion Rate of Boys is increased from 90.95 to 94.27 and for girls it increased from 92.07 to 95.78. 

· Following Districts reports a low completion rate against the state average for boys 94.27 and girls 95.78: Bathinda (B-88.33, G-92.98), Faridkot (B- 85.88 G- 90.49), Kapurthala (B-90.01 G- 93.31), Muktsar (B- 73.15, G- 76.93).

Dropout Rate: Table: 6

· The overall dropout rate has reduced in all the districts. 

· Districts with high dropout rate in comparison to state average (B-2.54 ,G- 1.60) at primary level  are Fatehgarh Sahib (B-6.84  G- 4.34), Gurdaspur (B-4.02 G-3.40), Hoshiarpur (B-6.09  G-4.30), Ludhiana (B-4.38  G-3.29), Mohali (B-6.69  G-6.60), Nawanshahr (B-7.04  G-5.54), Ropar (B-5.43  G-4.86).

· Districts with high dropout rate in comparison to state average (B- 4.46, G-3.99) at Upper primary level are Barnala (B-6.76, G-8.30), Hoshiarpur (B-7.66  G-9.33), Kapurthala (B-5.71  G-8.48), Mansa  (B-6.81   G-6.55).

GER: Table: 7

· State has an incremented GER at Primary level (from 81.43 to 93.22) and Up. Primary Level (from 70 to 78). 

· In Jalandhar a decrease of (-5.42) at primary and  a decrease of (-3.99) at Up. Primary level from the last year.

· In current year Districts Gurdaspur (82.55), Hoshiarpur (79.81), Ropar (83.16), Mohali (84.85), Ludhiana (84.47), Jalandhar (88.55) have a very low GER at Primary against state average (93.22).

· In current year Districts Muktsar (61.31), Ferozepur (64.76), Ludhiana (66.75), Tarntaran (68.23), Hoshiarpur (73.91), Mansa (75.89) have a very low GER at Up. Primary against state average (78).

NER: Table: 7

· State has an incremented NER at Primary level (from 72 to 74) and decremented NER at Up. Primary Level (from 60 to 54) against last year. 

· In current year Districts Gurdaspur 69.37, Hoshiarpur 65.05, Jalandhar 69.51, Ludhiana 66.69, Mohali 68.76, Ropar 66.86 have a very low NER at Primary against state average (74.09).

· In current year Districts Barnala 51.63, Bathinda 50.83, Ferozepur 45.60, Hoshiarpur 51.83, Jalandhar 51.28, Ludhiana 46.34, Muktsar 42.99, Tarntaran 50.41 have a very low NER at Up. Primary against state average (54.10).

Transition Rate: Table: 8

· Transition Rate of Boys is increased from 87.25 to 90.91 and for girls it increased from 86.17 to 90.49.

· Following Districts reports a low Transition rate against the state average for boys 90.91 and girls 90.49: Amritsar (B-85.86 G-83.57), Fatehgarh Sahib (B-82.43, G-88.25),      Gurdaspur (B-89.95, G-87.66), Kapurthala (B-84.20, G-86.57), Muktsar (B-85.01, G-86.70), Tarn Taran (B-88.07, G-77.56).

Pupil teacher Ratio: Table: 9

· The State throws a good picture of PTR below 40 almost in all the districts. Barnala has a highest fig. of 46.59 at Primary level.

Status of data entry in web-portal:

Quarterly data entry for web-portal forms are monitored by state MIS unit. Technical support on data entry and related problem solving is also provided by the state unit.

Data entry in web-portal has been completed upto 3rd quarter for the year 2008-09. All forms in the web-portal has been filled and approved as well at district level. The status of data entry of web Portal on 09/03/09 is:

	Year
	Quarter
	No. of Districts
	Status of Data Entry
(No. of Districts)

	
	
	
	Completed
	In Progress
	Yet to Start

	2007
	IV Qtr
	20
	20
	0 
	0 

	2008
	I Qtr
	20
	20
	0 
	0 

	2008
	II Qtr
	20
	20
	0 
	0 

	2008
	III Qtr
	20
	20
	0 
	0 


Educational development Index (EDI)-DISE 2007-08:

	
	Index
	06-07
	07-08

	At Primary
	Access
	16
	23

	
	Infrastructure
	2
	1

	
	Teacher
	21
	18

	
	Outcomes
	30
	11

	At Upper Primary
	Access
	13
	16

	
	Infrastructure
	3
	3

	
	Teacher
	16
	13

	
	Outcomes
	33
	29

	Composite
	Primary Level
	13
	9

	
	Up. Primary
	15
	15

	
	Pri. & U. Primary
	15
	12


State reports a major change in Ranking at primary level. In Access state came down from 16 to 23 and in Outcome it tremendously improved from 30 to 11.

Capacity building: Training sessions on filling up of DISE DCFs, data entry in DISE software, data entry in web portal and for generation requisite reports based upon the data collected every year are imparted to district/block and cluster level coordinators.
State level training for district MIS staff for checking of inconsistencies or discrepancies in the data collected from various sources is also given. The same process is followed at block/cluster and school level trainings thereafter.

A detailed training cum discussion session through EDUSAT under DISE Survey is organized for district, block and cluster level staff.

DISE: DISE survey is conducted by state MIS unit in all 20 districts of Punjab every year. Activities like data compilation, inconsistency checks and development of EDI is made at state level. Publication based upon the data is prepared and released every year. Data analysis for various departments like planning, civil works, teacher training, finance etc. are made by the state MIS unit.
Child Tracking System: Web based software for tracking out of school children has been developed by state MIS unit and data updations are made by the district MIS units.

Remedial Coaching Monitoring System: Web enabled software for keeping track of the remedial coaching has been developed and implemented by state MIS unit and data for the same is updated at district level.

Calendar of activities for DISE Survey:

MONTH





A C T I V I T I E S

July
Discussion with District MIS Coordinators on DCF, Finalizing of Master list of Schools, villages, Blocks, Clusters.

August 

Tender for printing of DISE DCF.


Training to District MIS Coordinators for filling of DISE DCF & hands-on on DISE Software. 

September
Distribution of DISE DCFs by state to districts, district to blocks, blocks to clusters and clusters to schools.


Selection of Independent Agency for 5% Sample Checking Survey.


Training to Block/Cluster Resource Persons for filling of DISE DCF by MIS Coordinator and teams for the monitoring of these trainings are sent to the respective training locations.


Detailed training session for District MIS Coordinators & Data Entry operators at state level on DISE Software.


Training to School Teachers for filling of DISE DCF by District MIS Coordinator / Block Resource Persons.

DISE DCFs will also be distributed among school teachers on the day of training.

October.
Collection and verification of filled DISE DCFs by Cluster Resource Persons.


Collection and verification of filled DISE DCFs by CRCs.


Collection and verification of filled DISE DCFs by District MIS Coordinators.



Submission of filled DISE DCFs by districts to State.

October-November
Data Entry of Filled DISE DCFs.

December

Data validation and report generation.

January 
Submission of DISE data to National Level.

DISE data dissemination strategies:

Detailed reports based upon DISE data are prepared and uploaded on the website of the department. Data for last 3-4 years are available on the website. The said data is widely used by education researchers and planners.

Publication based upon DISE data is circulated to all the wings of education department every year.

School report cards are sent to all the schools which reflect schools’ individual progress towards enrolment, infrastructure improvement, funds utilization etc.

Data sharing:

DISE data once compiled and finalized is used by concerned departments for carrying out various activities.

A publication “DISE Data Book” is released every year by MIS unit at state level.

Schools Report cards are sent back to all the schools for future reference and cross checking of data supplied by the schools.

School wise reports on selected indicators are prepared and shared with block/cluster/school representatives.

Calculation of EDI at State (District-wise) and District (Block-wise) Level:

Education Development Index based upon DISE data is calculated at state level for all 20 districts of Punjab. Some findings from the EDI calculated using DISE data 2007-08 are as follows:-

5 % Sample Checking:
5% post enumeration survey has been conducted last year i.e. 2007-08 and the said survey was carried out by Delhi based firm M/s Datamation Research Analyst. Report as submitted by the firm has also been submitted to GoI and findings from the said report has been shared with district/block level coordinators and measure based upon the report has been taken in to account positively while conducting DISE Survey for the current year 2008-09.

5% sample checking survey by independent agency for 5% schools from every block of all the districts of Punjab is going on for the current year. Report for the same will be submitted during this month (March, 2009) by the firm.

Distribution and discussion on School Report Cards:

School report cards are sent to all the schools covered under DISE every year and discussions are made on grey areas.

Hardware/Software/Internet connection requirements:
Appropriate hardware/software as per requirement is in placed at state/district/block level. Internet connection is also available at state and all district head quarters. Internet connection for all block offices is being provided during the year 2009-10.

Data validation plan at District/sub-district/cluster level:

Trainings by state MIS units to block/cluster level coordinators in respect of filling-up of DISE DCFs, inconsistency check etc. 

Household survey (Latest enumeration and updation):

Household survey was last conducted during January, 2008 and data for the same has been provided in 25 tables of AWP&B 2009-10. 

Table: 1- Enrolment
	Primary
	Up.Primary

	District Name


	2007-08
	2008-09
	2007-08
	2008-09

	
	B
	G
	B
	G
	B
	G
	B
	G

	Amritsar
	68709
	59316
	116735
	94435
	37724
	31106
	57142
	45984

	Barnala
	15325
	13428
	33569
	25569
	11446
	10697
	18597
	14691

	Bathinda
	51739
	42501
	71966
	55135
	30003
	24876
	36413
	28583

	Faridkot
	28741
	23387
	35482
	27744
	15745
	12750
	18317
	14395

	Fatehgarh Sahib
	24110
	19106
	27407
	21017
	15729
	13298
	16923
	13014

	Ferozpur
	90901
	80328
	105434
	86194
	39047
	32667
	51699
	39818

	Gurdaspur
	68403
	59728
	102771
	83989
	38013
	32618
	56174
	45909

	Hoshiarpur
	58809
	47757
	84794
	67274
	43425
	38906
	53404
	44217

	Jalandhar
	58193
	49333
	105809
	84397
	42903
	38199
	62000
	52315

	Kapurthala
	26878
	22226
	48751
	37377
	17173
	15272
	28643
	22207

	Ludhiana
	79769
	67995
	143730
	115457
	48681
	42702
	77348
	64553

	Mansa
	27869
	23260
	44412
	33864
	16586
	14087
	22739
	17271

	Moga
	38652
	33005
	52485
	42233
	21799
	19378
	27747
	22976

	Mohali
	18354
	15968
	33499
	26040
	12177
	11431
	19514
	15784

	Muktsar
	37802
	31599
	51395
	40191
	18665
	15266
	23238
	18410

	Nawanshahr
	30793
	24323
	31583
	24759
	19421
	17383
	20152
	17170

	Patiala
	58312
	48226
	103926
	79538
	37731
	31663
	60822
	46124

	Ropar
	20318
	18072
	33225
	26465
	14315
	13574
	21325
	17532

	Sangrur
	43372
	38619
	84952
	66242
	30721
	26951
	49513
	38850

	Tarantaran
	40073
	34360
	56946
	45914
	24089
	17292
	29626
	21813

	State
	887122
	752537
	1368871
	1083834
	535393
	460116
	751336
	601616


Table: 2- Social Category wise Enrolment SC
	District Name


	Primary
	Up. Primary

	
	2007-08
	2008-09
	2007-08
	2008-09

	
	B
	G
	B
	G
	B
	G
	B
	G

	Amritsar
	37397
	34481
	47275
	40294
	16195
	13644
	20232
	16693

	Barnala
	10132
	8898
	12771
	10954
	5347
	4942
	6034
	5292

	Bathinda
	26049
	22891
	29986
	25500
	11293
	10129
	11489
	10291

	Faridkot
	15438
	13792
	17020
	14760
	6381
	5446
	7048
	5943

	Fatehgarh Sahib
	10902
	9015
	11180
	9294
	6022
	5412
	6613
	5640

	Ferozpur
	32438
	30133
	51887
	46116
	10416
	8619
	20453
	16280

	Gurdaspur
	30999
	28757
	37014
	32966
	15459
	13534
	18907
	16751

	Hoshiarpur
	27288
	23544
	33443
	28093
	19193
	18329
	21261
	19312

	Jalandhar
	34221
	30015
	46050
	39097
	23944
	22772
	27678
	25227

	Kapurthala
	14238
	12179
	17981
	14656
	7926
	7915
	9429
	8670

	Ludhiana
	41429
	36626
	46683
	40525
	23910
	21657
	26021
	23495

	Mansa
	14851
	13111
	18066
	15443
	6262
	5274
	7065
	5837

	Moga
	22184
	19489
	25507
	22171
	8829
	8237
	10275
	9447

	Mohali
	8412
	7168
	9842
	8049
	4706
	4505
	5551
	5025

	Muktsar
	21832
	19932
	26382
	22945
	7823
	6574
	8745
	7648

	Nawanshahr
	15024
	12104
	14580
	11785
	9404
	8824
	9676
	8490

	Patiala
	24397
	20998
	29800
	24634
	13019
	11305
	15287
	12856

	Ropar
	8611
	7708
	9777
	8525
	5427
	5018
	6250
	5570

	Sangrur
	25272
	22508
	30004
	25578
	13906
	12111
	15383
	13132

	Tarantaran
	22064
	20456
	24801
	22021
	9348
	5955
	9831
	7176

	State
	443178
	393805
	540049
	463406
	224810
	200202
	263228
	228775


Table: 3- Social Category wise Enrolment ST
	District Name


	Primary
	Up. Primary

	
	2007-08
	2008-09
	2007-08
	2008-09

	
	B
	G
	B
	G
	B
	G
	B
	G

	Amritsar
	336
	230
	659
	547
	253
	113
	249
	181

	Barnala
	26
	11
	0
	0
	0
	0
	0
	0

	Bathinda
	88
	68
	232
	206
	23
	51
	95
	120

	Faridkot
	14
	14
	27
	30
	4
	5
	1
	2

	Fatehgarh Sahib
	6
	8
	0
	0
	28
	25
	0
	0

	Ferozpur
	257
	262
	221
	179
	7
	9
	144
	131

	Gurdaspur
	159
	212
	63
	49
	34
	206
	21
	53

	Hoshiarpur
	148
	136
	50
	25
	46
	33
	34
	18

	Jalandhar
	63
	44
	10
	4
	0
	0
	3
	6

	Kapurthala
	18
	10
	101
	72
	25
	13
	48
	51

	Ludhiana
	198
	177
	464
	362
	488
	366
	378
	340

	Mansa
	10
	4
	13
	9
	91
	86
	46
	28

	Moga
	224
	159
	0
	0
	48
	23
	0
	0

	Mohali
	29
	32
	1
	1
	45
	57
	0
	0

	Muktsar
	0
	0
	0
	0
	8
	0
	0
	0

	Nawanshahr
	28
	19
	0
	0
	41
	29
	0
	0

	Patiala
	50
	47
	0
	0
	111
	98
	0
	0

	Ropar
	167
	121
	157
	167
	143
	94
	207
	177

	Sangrur
	22
	25
	0
	0
	31
	12
	0
	0

	Tarantaran
	89
	59
	226
	127
	48
	235
	79
	55

	State
	1932
	1638
	2224
	1778
	1474
	1455
	1305
	1162


Table: 4- Single Teacher School
	District
	2007-08
	2008-09

	
	Pry
	U. Pry
	Pry
	U. Pry

	Amritsar
	0
	0
	83
	7

	Barnala
	18
	0
	12
	1

	Bathinda
	0
	0
	16
	0

	Faridkot
	0
	0
	6
	0

	Fatehgarh Sahib
	75
	0
	19
	0

	Ferozepur
	78
	0
	114
	4

	Gurdaspur
	0
	0
	231
	3

	Hoshiarpur
	5
	0
	146
	6

	Jalandhar
	105
	5
	70
	2

	Kapurthala
	0
	3
	32
	1

	Ludhiana
	0
	0
	79
	3

	Mansa
	0
	4
	7
	1

	Moga
	0
	0
	20
	5

	Mohali
	0
	0
	56
	0

	Muktsar
	0
	0
	23
	0

	Nawanshaher
	48
	12
	30
	7

	Patiala
	160
	5
	134
	4

	Ropar
	0
	0
	68
	0

	Sangrur
	91
	0
	53
	5

	Tarntaran
	37
	18
	36
	16

	Punjab
	617
	47
	1235
	65


Table: 5- Completion Rate

	District Name
	2007-08
	2008-09

	
	Boys
	Girls
	Boys
	Girls

	Amritsar
	66.27
	68.48
	93.81
	96.44

	Barnala
	0
	0
	94.15
	95.33

	Bathinda
	89.10
	88.28
	88.33
	92.98

	Faridkot
	80.26
	85.21
	85.88
	90.49

	Fatehgarh Sahib
	89.33
	89.29
	93.68
	94.61

	Ferozepur
	101.03
	98.73
	91.97
	92.68

	Gurdaspur
	117.29
	118.32
	101.78
	100.07

	Hoshiarpur
	96.86
	96.15
	97.64
	100.65

	Jalandhar
	91.10
	93.37
	92.17
	94.46

	Kapurthala
	90.90
	91.93
	90.01
	93.31

	Ludhiana
	84.49
	88.43
	101.72
	102.12

	Mansa
	81.34
	83.27
	91.71
	93.33

	Moga
	79.21
	85.07
	91.86
	92.97

	Mohali
	100.28
	98.22
	98.89
	99.79

	Muktsar
	76.92
	75.92
	73.15
	76.93

	Nawanshahr
	92.64
	94.25
	93.84
	97.46

	Patiala
	92.06
	92.64
	96.24
	97.58

	Ropar
	96.57
	99.63
	98.98
	99.11

	Sangrur
	75.15
	75.45
	98.65
	99.65

	Tarn Taran
	81.95
	81.59
	91.08
	90.76

	Total
	90.95
	92.07
	94.27
	95.78


Table: 6- Dropout Rate

	District Name


	2007-08
	2008-09

	
	(Pry)
	(Upper Pry)
	(Pry)
	(Upper Pry)

	
	Boys
	Girls
	Boys
	Girls
	Boys
	Girls
	Boys
	Girls

	Amritsar
	8.98
	8.84
	3.35
	-2.19
	2.07
	1.53
	1.37
	-1.24

	Barnala
	0
	0
	0
	0
	-0.91
	-4.32
	6.76
	8.30

	Bathinda
	5.05
	4.60
	9.36
	6.10
	0.92
	-0.22
	6.61
	4.47

	Faridkot
	7.47
	5.53
	11.76
	8.25
	2.51
	1.69
	4.38
	3.26

	Fatehgarh Sahib
	11.21
	9.21
	-27.89
	-33.91
	6.84
	4.34
	4.26
	7.24

	Ferozepur
	1.73
	1.78
	3.82
	1.36
	0.47
	-0.17
	1.45
	1.71

	Gurdaspur
	8.81
	8.04
	-7.57
	-7.00
	4.02
	3.40
	-6.16
	-7.95

	Hoshiarpur
	12.22
	12.33
	15.47
	14.37
	6.09
	4.30
	7.66
	9.33

	Jalandhar
	7.70
	6.11
	8.24
	9.76
	3.37
	1.97
	6.23
	5.76

	Kapurthala
	7.14
	5.97
	8.90
	11.57
	3.83
	3.06
	5.71
	8.48

	Ludhiana
	19.42
	16.78
	13.53
	11.81
	4.38
	3.29
	6.85
	5.48

	Mansa
	2.69
	1.36
	9.52
	10.35
	0.68
	-0.62
	6.81
	6.55

	Moga
	10.17
	8.88
	10.20
	9.71
	0.25
	0.11
	5.19
	4.13

	Mohali
	8.66
	10.08
	8.35
	10.19
	6.69
	6.60
	3.81
	4.64

	Muktsar
	-7.78
	-4.24
	6.08
	-1.09
	-3.52
	-2.50
	3.73
	-0.27

	Nawanshahr
	15.29
	14.57
	10.38
	16.63
	7.04
	5.54
	3.94
	8.88

	Patiala
	2.91
	2.35
	5.47
	4.89
	0.87
	-0.86
	4.69
	5.20

	Ropar
	7.50
	6.39
	6.93
	7.83
	5.43
	4.86
	4.73
	7.24

	Sangrur
	31.53
	31.08
	33.96
	35.13
	1.28
	0.80
	5.36
	6.50

	Tarn Taran
	15.10
	15.56
	15.04
	8.17
	1.50
	1.46
	10.05
	-0.99

	Total
	8.27
	7.55
	7.30
	6.31
	2.54
	1.60
	4.46
	3.99


Table: 7- GER & NER

	District Name
	2007-08
	2008-09

	
	Primary
	Upper Primary
	Primary
	Upper Primary

	
	GER
	NER
	GER
	NER
	GER
	NER
	GER
	NER

	Amritsar
	85.21
	82.00
	71.74
	69.00
	100.08
	82.35
	88.18
	63.17

	Barnala
	72.72
	57.43
	61.87
	52.55
	96.03
	75.83
	77.73
	51.63

	Bathinda
	92.25
	80.75
	76.00
	63.00
	103.28
	77.62
	76.28
	50.83

	Faridkot
	104.45
	87.31
	83.10
	80.66
	104.58
	83.16
	79.65
	56.48

	Fatehgarh Sahib
	61.55
	81.27
	77.92
	40.77
	89.67
	72.24
	79.03
	55.12

	Ferozepur
	80.80
	55.20
	43.60
	40.50
	92.81
	73.47
	64.76
	45.60

	Gurdaspur
	28.59
	23.82
	58.83
	53.24
	82.55
	69.37
	87.80
	63.99

	Hoshiarpur
	65.69
	58.36
	46.24
	43.13
	79.81
	65.05
	73.91
	51.83

	Jalandhar
	93.97
	89.00
	81.19
	74.00
	88.55
	69.51
	77.20
	51.28

	Kapurthala
	104.00
	94.47
	88.05
	74.19
	112.02
	88.69
	94.69
	67.35

	Ludhiana
	55.00
	50.00
	50.26
	50.26
	84.47
	66.69
	66.75
	46.34

	Mansa
	91.00
	67.00
	62.00
	48.00
	100.13
	76.78
	75.89
	51.56

	Moga
	90.32
	69.66
	74.93
	53.57
	101.71
	74.96
	78.46
	53.13

	Mohali
	45.01
	49.12
	44.18
	36.20
	84.85
	68.76
	78.47
	54.10

	Muktsar
	91.47
	75.39
	72.86
	68.24
	92.78
	72.37
	61.31
	42.99

	Nawanshaher
	99.00
	83.00
	93.00
	88.00
	100.25
	80.58
	93.22
	62.89

	Patiala
	109.24
	84.71
	91.33
	59.64
	107.68
	85.34
	90.45
	63.87

	Ropar
	74.72
	72.96
	76.37
	74.65
	83.16
	66.86
	82.39
	58.77

	Sangrur
	84.89
	74.13
	74.43
	61.85
	98.98
	77.29
	84.67
	57.90

	Tarntaran
	98.64
	95.07
	73.78
	63.12
	95.37
	77.08
	68.23
	50.41

	State
	81.43
	71.53
	70.08
	59.73
	93.22
	74.09
	77.60
	54.10


Table: 8- Transition Rate
	District Name
	2007-08
	2008-09

	
	Boys
	Girls
	Boys
	Girls

	Amritsar
	82.69
	80.55
	85.86
	83.57

	Barnala
	0
	0
	102.71
	101.08

	Bathinda
	96.65
	95.99
	100.82
	100.99

	Faridkot
	79.36
	78.04
	87.20
	89.15

	Fatehgarh Sahib
	80.52
	89.10
	82.43
	88.25

	Ferozepur
	92.86
	83.13
	91.81
	85.72

	Gurdaspur
	81.12
	78.55
	89.95
	87.66

	Hoshiarpur
	85.80
	86.84
	87.49
	91.10

	Jalandhar
	92.27
	96.19
	91.00
	96.15

	Kapurthala
	83.04
	89.71
	84.20
	86.57

	Ludhiana
	81.04
	84.31
	91.56
	92.22

	Mansa
	89.66
	84.32
	90.89
	88.74

	Moga
	78.22
	82.62
	92.31
	94.60

	Mohali
	86.73
	87.56
	90.59
	93.70

	Muktsar
	86.29
	83.14
	85.01
	86.70

	Nawanshahr
	80.34
	88.51
	87.85
	91.17

	Patiala
	93.45
	93.23
	94.69
	94.02

	Ropar
	90.95
	93.56
	91.55
	92.22

	Sangrur
	73.69
	70.01
	98.46
	95.50

	Tarn Taran
	81.52
	66.63
	88.07
	77.56

	State
	87.25
	86.17
	90.91
	90.49


Table: 9- Pupil Teacher Ratio

	District
	2007-08
	2008-09

	
	Pry
	U. Pry
	Pry
	U. Pry

	Amritsar
	45.01
	30.42
	34.40
	22.72

	Barnala
	52.75
	33.13
	46.59
	27.51

	Bathinda
	52.03
	36.64
	40.25
	17.81

	Faridkot
	34.49
	21.12
	31.47
	14.09

	Fatehgarh Sahib
	30.30
	28.19
	24.32
	22.46

	Ferozpur
	36.68
	26.09
	36.96
	23.09

	Gurdaspur
	29.91
	23.59
	26.25
	22.11

	Hoshiarpur
	27.36
	18.39
	24.03
	16.11

	Jalandhar
	30.08
	21.17
	29.73
	20.07

	Kapurthala
	30.00
	21.68
	25.46
	18.08

	Ludhiana
	40.70
	21.97
	33.61
	18.64

	Mansa
	39.83
	29.36
	36.76
	22.33

	Moga
	47.59
	27.44
	41.48
	18.88

	Mohali
	29.76
	22.19
	24.34
	19.05

	Muktsar
	47.23
	21.42
	42.38
	13.74

	Nawanshahr
	29.97
	24.88
	25.75
	21.40

	Patiala
	35.60
	27.01
	32.42
	18.45

	Ropar
	27.01
	23.81
	22.98
	21.40

	Sangrur
	35.30
	24.56
	37.64
	23.57

	Tarantaran
	40.87
	32.02
	34.18
	28.13

	State
	35.89
	24.60
	31.83
	19.93


4. Components wise Appraisal:

(I) Access
· State policy on opening of new schools

Primary schools: Policy for opening of new primary school has changed last year and according to the new policy there are three conditions for opening of a new primary school which are given below.
· There should not be a Primary School within a radius of 1-1.5 Km.

· Minimum 20 children of eligible age

· Kenals of land should be available. 

Upper Primary School

1. There should not be an Upper Primary School within a radius of 3 Km.

2. Minimum 20 children of eligible age.

3. Sufficient land for building infrastructure such as class rooms, toilet, drinking water facilities etc. 

Upper Primary Schools for Girls only

There are 283 upper primary schools for girls only but state does not have a policy for opening girls’ only upper primary schools 

· Availability of Schooling facilities:
Table: Information on Schools

	Category
	Govt.
	Aided
	Private
	Total

	Primary
	13400
	90
	648
	14138

	Up. Primary
	5569
	407
	1889
	7865


Table: Habitation and Access (Primary)

	SNo.
	Name of District
	Total No. of Habitations
	Habitations Covered by
	Habitations without Primary Schools / EGS (within 1 KM)
	Habitations without Primary Schools / EGS

	
	
	
	Primary 
School (within 1 KM)
	EGS (within 1 KM)
	
	Habitations eligible for PS as per state norms
	No. of Children in such (Col. 7) Habitations 
	Habitations not eligible for PS but eligible for EGS
	 Habitations not eligible for PS/EGS

	1
	2
	3
	4
	5
	6
	7
	8
	9
	10

	1
	Amritsar
	1007
	1003
	0
	4
	4
	91
	0
	0

	2
	Barnala
	221
	221
	0
	0
	0
	0
	0
	0

	3
	Bathinda
	414
	412
	0
	2
	2
	95
	0
	0

	4
	Faridkot
	248
	248
	0
	0
	0
	0
	0
	0

	5
	Fatehgarh Sahib
	531
	520
	0
	11
	11
	228
	0
	0

	6
	Ferozepur
	1404
	1395
	0
	9
	9
	632
	0
	0

	7
	Gurdaspur
	1539
	1537
	0
	2
	2
	105
	0
	0

	8
	Hoshiarpur
	1671
	1668
	0
	3
	3
	85
	0
	0

	9
	Jalandhar
	1192
	1190
	0
	2
	2
	110
	0
	0

	10
	Kapurthala
	793
	776
	0
	17
	8
	360
	0
	9

	11
	Ludhiana
	1146
	1146
	0
	0
	0
	0
	0
	0

	12
	Mansa
	328
	304
	0
	24
	24
	1022
	0
	0

	13
	Moga
	387
	387
	0
	0
	0
	0
	0
	0

	14
	Mohali
	432
	430
	0
	2
	2
	91
	0
	0

	15
	Muktsar
	319
	319
	0
	0
	0
	0
	0
	0

	16
	Nawanshaher
	529
	528
	0
	1
	1
	65
	0
	0

	17
	Patiala
	1099
	1097
	0
	2
	2
	100
	0
	0

	18
	Ropar
	773
	770
	0
	3
	3
	130
	0
	0

	19
	Sangrur
	765
	765
	0
	0
	0
	0
	0
	0

	20
	Tarntaran
	532
	532
	0
	0
	0
	0
	0
	0

	 
	Total
	15330
	15248
	0
	82
	73
	3114
	0
	9


Table: Habitation and Access (Upper Primary)

	S. No.
	Name of District
	Total No. of Habitations
	No. of Habitations having UPS facility in 3 KM Area
	No. of Habitations without UPS facility in 3 KM area
	No. of eligible schoolless habitations for UPS as per distance and population norms
	No. of Primary Schools
 (Govt. & Govt. Aided)
	No.of Upper Primary School 
(Govt. & Govt. Aided)
	Primary and Upper Primary Ratio
	No. of UPS eligible as per 2:1 ratio
	Gap in UPS

	1
	Amritsar
	1007
	949
	58
	58
	889
	386
	2.3
	444
	58

	2
	Barnala
	221
	221
	0
	0
	190
	118
	1.61
	95
	0

	3
	Bathinda
	414
	402
	12
	12
	390
	261
	1.5
	195
	0

	4
	Faridkot
	248
	248
	0
	0
	256
	162
	1.58
	128
	0

	5
	Fatehgarh Sahib
	531
	500
	31
	31
	460
	199
	2.3
	230
	31

	6
	Ferozepur
	1404
	1340
	64
	64
	1158
	394
	3.1
	589
	212

	7
	Gurdaspur
	1539
	1451
	88
	88
	1559
	516
	3.1
	780
	264

	8
	Hoshiarpur
	1671
	1607
	64
	64
	1288
	468
	2.75
	644
	176

	9
	Jalandhar
	1192
	1181
	11
	11
	1000
	479
	2.1
	500
	21

	10
	Kapurthala
	793
	762
	31
	31
	561
	249
	2.25
	280
	31

	11
	Ludhiana
	1146
	1142
	4
	4
	1032
	578
	1.79
	516
	0

	12
	Mansa
	328
	318
	10
	10
	294
	178
	1.5
	147
	0

	13
	Moga
	387
	383
	4
	4
	382
	242
	1.6
	191
	17

	14
	Mohali
	432
	379
	53
	53
	421
	156
	2.7
	210
	54

	15
	Muktsar
	319
	314
	5
	5
	339
	204
	1.74
	170
	0

	16
	Nawanshaher
	529
	503
	26
	26
	448
	215
	2
	224
	9

	17
	Patiala
	1099
	1054
	45
	45
	1022
	371
	3:01
	511
	140

	18
	Ropar
	773
	673
	100
	100
	585
	195
	3.1
	293
	98

	19
	Sangrur
	765
	760
	5
	5
	675
	368
	1.83
	338
	0

	20
	Tarntaran
	532
	494
	38
	38
	541
	237
	2.28
	271
	38

	 
	Total
	15330
	14681
	649
	649
	13490
	5976
	2.26
	6756
	1149


A. Primary 
No new primary schools were sanctioned to the state except upgradation of 128 EGS centres to primary school. 
Number of EGS centers upgraded to PS till now
	2006-07
	2007-08
	2008-09
	Total

	88
	09
	31
	128


	EGS Upgradation (cumulative upto 2008-09)

	Sanctioned
	128

	Actually Upgraded
	128

	Facilities provided in upgraded EGS Centres (PS)

	Buildings : Sanctioned
	128

	Buildings : Completed
	   104                                (81% of the sanctioned)

	Teacher : Sanctioned
	256

	Teacher : Provided
	241

	TLE : Sanctioned
	128

	TLE : Provided
	128


State has reported 15330 habitations out of which 15248 (99.46%) are covered by primary schools. 82 habitations do not have primary school within a radius of 1 Km. Out of 82 unserved habitations, 73 habitations are eligible for primary school as per state norms and 9 habitations do not qualify  for primary school.  

Table: Status of EGS 
	District
	Total number of EGS functioning
	No. of EGS completing 2 years or more in 2009-10

	At present no EGS is functioning in the state


B. Upper Primary

Status on opening of new upper primary schools sanctioned till 2008-09 under SSA 

	2007-08
	2008-09
	Total

	01
	134
	135


Out of the total habitations 14681 habitations (95.76%) are covered by upper primary schools. 649 habitations which is 4.2% of the total habitations are unserved; but all of them are eligible for upper primary schools as per state norms. The ratio of PS to UPS is 2.26:1. There are 649 habitations which are unserved and eligible for upper primary school and state has proposed an equal number of upper primary school. There is no evidence for systematic mapping by the state for coverage by PS/ UPS 

Observations: 

· State has been reporting different number of habitations during the last three years. As a result there is no consistency in the number of habitations covered by PS/UPS and habitations being uncovered by regular schools. Following table shows different numbers of habitations reported by the state during last three years.  

	2007-08
	2008-09
	2009-10

	14108
	17059
	15330


· State had made a commitment to undertake school mapping exercise to come up with actual requirement of schools in unserved areas by June 2008 but state has not reported any progress in school mapping exercise.

· As per the state norms on distance and population 341 EGS centres were eligible for upgradation to primary schools in 2008-09. However, state had proposed upgradation of only 31 EGS centres to PS, as land was not available in case of 310 EGS centres. The state was advised to find ways and means for land availability so that universal access could be achieved. The PS requirement and availability could only be saturated after the state ensured availability of the land. In 2009-01, state has again proposed upgradation of 54 EGS to PS. State has also proposed 15 new primary schools. State is suggested to first upgrade all its EGS centres and then only it should propose for new primary school. 

· State is again advised to undertake a thorough school mapping exercise so that a clear picture of covered/ uncovered habitations is available and requirement of school is saturated at primary and upper primary level. 
· There is no evidence for systematic mapping by the state for coverage of its habitations by PS/ UPS 

· With the approval of present proposal of PS and UPS, state would saturate its requirement of primary and upper primary schools.

Proposal:

1. Upgradation of 54 EGS to primary school

2. Opening of 15 new primary schools

3. Upgradation of 649 Primary schools to upper primary schools.

Recommendations:

1. Upgradation of 54 EGS to primary school is recommended

2. Opening of 15 new primary schools is recommended but state is advised to upgrade its backlog of EGS centres on priority.

3. Upgradation of 598 primary schools to upper primary schools is recommended in the following districts. 

	SNo.
	Name of Block/
 Municipal Area
	No. of  UPS proposed
	No. of  UPS recommended
	Remarks



	1. 
	Amritsar
	58
	58
	PS to UPS ratio is 2.3 and there is a gap of 58 UPS.  

	2. 
	Bathinda
	12
	9
	Only Sangat block qualifies for one UPS. All other blocks have less than 2:1 ratio and there is no gap in UPS in any other block. 8 UPS are recommended as there are equal numbers of unserved habitations in Villages with 40% SC population.

	3. 
	Fatehgarh Sahib
	31
	28
	Khamano block has proposed for 3 UPS but it has less than 2:1 ratio and has no gap in UPS so 3 UPS are not recommended.

	4. 
	Ferozepur
	64
	55
	7 UPS in Abohar and 2 UPS in Khuian Sarwar are not as these blocks have less than 2:1 ratio and there is no gap in UPS

	5. 
	Gurdaspur
	88
	86
	2 UPS in Dhar Kalan block are not recommended due to favourable PS to UPS ratio and lack of gap in UPS

	6. 
	Hoshiarpur
	64
	64
	PS to UPS ratio is 2.75 and there is a gap of 176 UPS.  

	7. 
	Jalandhar
	11
	11
	PS to UPS ratio is 2.1 and there is a gap of 21UPS

	8. 
	Kapurthala
	31
	24
	7 UPS in Phagwara block are not recommended due to favourable PS to UPS ratio and lack of gap in UPS

	9. 
	Ludhiana
	4
	4
	4 UPS are recommended as there are 5 unserved habitations in Villages with 40% SC population. 

	10. 
	Mansa
	10
	4
	Only Sardulgarh (u) Block qualifies for 4 UPS. All other blocks have less than 2:1 ratio and there is no gap in UPS in any other block

	11. 
	Moga
	4
	3
	3 UPS are recommended as there are equal numbers of unserved habitations in Villages with 40% SC population. 

	12. 
	Mohali
	53
	49
	4 UPS are not recommended. In Derabassi 16 UPS are recommended against proposed 17 UPS and in Kharar 17 UPS are recommended against pjroposed 20UPS. 

	13. 
	Muktsar
	5
	5
	All blocks have less than 2:1 ratio and there is no gap in UPS in any block. But 5 UPS are recommended as there are equal numbers of unserved habitations in Villages with 40% SC population.

	14. 
	Nawanshaher
	26
	16
	2 in Auri, 4 in Banga and 4 in Nawshera are not recommended respectively as these blocks have favourable ratio of PS to UPS and there is no gap in UPS as well. 

	15. 
	Patiala
	45
	45
	 

	16. 
	Ropar
	100
	98
	2 UPS are not recommended. In Anandpur Sahib 17 UPS are recommended against proposed 18 UPS and in Morinda 7 UPS are recommended against the proposed 8 UPS. 

	17. 
	Sangrur
	5
	1
	All blocks have less than 2:1 ratio and there is no gap in UPS in any block but one 1 UPS is recommended for village with 40% Minority population

	18. 
	Tarntaran
	38
	38
	 

	 
	Total
	649
	598
	 


C. Interventions for Out of School Children 

Performance during 2008-09:
Table: Status of Out of School Children

	Age in years
	2008-09
	2009-10

	
	
	Uncovered children from last year
	New Identified OOSC as per survey

	
	B
	G
	Total
	B
	G
	Total
	B
	G
	Total

	6-10
	16053
	13959
	30012
	2864
	2491
	5355
	12868
	11287
	24155

	11-14
	37512
	32933
	70445
	7572
	5177
	12749
	12141
	10869
	23010

	Total
	53512
	46892
	100457
	10436
	7668
	18104
	25009
	22156
	47165


State has covered 95240 children in 2008-09. The coverage has been made under the following interventions.

	Target and Achievement 
	Direct Enrollment
	NRBC
	RBC
	Total

	Target
	30012
	71436
	1200
	102648

	Achievement 
	24657
	69576
	1007
	95240

	% Achievement
	82.15
	97.39
	83.91
	


Observations:
1. 18104 out of school children who could not be covered in 2008-09, include 14402 migratory children and 3509 children who have by now crossed the 14 years of age.

2. Among the covered children state has reported the coverage of those children also who were not identified during HHS conducted in Jan 08. As the state was unaware about the presence of 12694 out of school children, planning for the coverage of these children was not done while formulating AWP&B 2008-09. These children were later identified by NGOs / department and were subsequently covered under AIE interventions.  As a result despite coverage of out of school children being around 95 thousand and there being only 5 thousand OOSC left, yet around 17 thousand children identified and reported in the PAB in 2008-09 remained uncovered.

3. A total of 69 thousand children are reportedly covered in NRBC but among these 17665 children (25%) have actually been directly enrolled in regular schools. These children were planned to be covered under bridge courses at the time of appraisal. PAB had, therefore, approved funds for their coverage under NRBC but state directly admitted 17665 children in regular schools without providing any bridging interventions. The fund allocated for their bridging interventions has been used for providing uniform, shoes, stationeries etc. to these children. This is an issue of concern as the state has not only deprived these children from the bridging support required to enable them to complete elementary education within 14 years of age, but it has also made a kind of exclusion by providing these children what is not provided to a child attending regular school.

4. The number of children actually covered in NRBC is, thus, 51911. 
5. State has not been able to mainstream any child from bridge courses residential as well as non residential. 

Data on the children mainstreamed from bridge course to regular schools:
Table: Progress & Mainstreaming

	Children enrolled in AI/bridge courses during 2008-09
	Children mainstreamed till 2008-09
	Children proposed to be enrolled in AI/bridge courses in 2009-10
	Children proposed to be mainstreamed in 2009-10

	51911
	00
	61146
	61146


Status of out of school children in 2009-10:
	Category
	Age group
	Population
	Out of school Children
	% of OOSC w.r.t  popn.

( 6-14 yrs)
	% of OOSC w.r.t  total OOSC of the state

	All Communities
	6-10
	2631000
	33993
	1.29
	72.05

	
	11-14
	1746459
	13172
	0.75
	27.95

	
	Total
	4377459
	47165
	1.07
	100

	Scheduled Caste
	6-10
	1019738
	20776
	2.03
	44.04

	
	11-14
	575950
	9279
	1.61
	19.67

	
	Total
	1595688
	30055
	2
	63.72

	Muslims
	6-10
	N.A
	428
	N.A
	0.90

	
	11-14
	N.A
	364
	N.A
	0.77

	
	Total
	N.A
	792
	N.A
	1.67


Observations:
As equity is the corner stone of SSA, state is required to give a focused attention to its marginalised sections. As is evident from the table above, share of scheduled cast children among out of school children far exceeds their share in eligible age group. While share of SC children in school age group is 36% only, but their share in out of school children is 64%.  Most of the SC children who are out of school belong to 6-10 years age group, considering the fact that state has universal access at primary level the high share of SC children in OOSC clearly indicates that there is an issue of ‘social access’ which state needs to address on priority. Strong community mobilisation to sensitise parents to send their children in school and to ensure that there are no single teacher school in SC concentrated areas may be some of the measures to address this issue of equity. It may also be important for the state to sensitise teachers during teacher training. 

While SSA encourages involvement of NGOs it also, at the same time, underlines the need that this involvement should be purposeful with necessary check and balances and must contribute in achieving the goal of UEE. State has involved NGOs for running bridge courses and the task of identifying the children who may require bridging intervention was also left to the same NGOs. As a result NGOs reported more number of out of school children than the number reported by household survey which was done just three months back.

State has given the task of running bridge courses to district Red Cross Societies as part of NGO involvement. These societies neither have mandate nor experience for education and particularly accelerated education where situation is more challenging and dynamic. This is probably the reason why state could not mainstream any child from bridge courses to regular schools.  It will be in the interest of the state if it builds the capacities of its own personnel (involving teachers including retired teachers, volunteers etc.) and conduct bridge courses on its own or atlest monitor the NGOs rigorously. The TSG at the national level can provide all technical support if state decides to take such initiative.
The state had decided to close down all the 973 EGS centres w.e.f. 1st April 2008. 43880 children who were enrolled in these EGS centres were to be mainstreamed in the regular schools. The state had committed to develop a plan for tracking these children so that effective mainstreaming and transition could take place. It has also committed to maintain a separate record for at least six months to ensure the regularity of these children, in attending schools. However, state has neither tracked these children nor has it maintained a separate record of these children to ensure regularity in attending schools. State has now reported that the decision to close down all its EGS centres has adversely affected its enrolment and all EGS centres should have not been closed as now children are forced to cross some barriers like rivers, road etc to reach regular school.

State has planned to give cash stipend to children who would be enrolled in bridge courses under AIE. Since cash incentive to anyone (teacher, children or anybody else) is not allowed, state is advised to refrain from giving cash incentives to children.

Last year state had planned for the coverage of migrating children albeit it could not cover any of them but this year state has just not planned for education of children of migratory labourers. Discussion with state team has revealed that State is reluctant to spend money on children that do not belong to the state of Punjab. This is one issue which has been constantly discussed with the state that it needs to have a rights based approach for achieving UEE not only in the state but also in the country as a whole.

Proposal of the State:
	No. of OoSC as per HHS
	No. of Out of School Children proposed to be covered under different strategies in 2009-10

	
	No. of Children to be directly enrolled in School
	No. of Children to be enrolled in NRBC
	No. of NRBC/AIE Centre
	No. of Children to be enrolled in RBC
	No. of RBC Centre
	Total No. of Children to be enrolled 
	Total No. of Centres

	47165
	8054
	36811
	1841
	2300
	46
	47165
	1887

	Cost and Duration
	Nil
	Rs. 3000/ child for 1 Year
	
	Rs. 10,000/ child for 1 Year
	
	
	


	Total Children to be continued
	Total Centres to be continued
	Proposal for continuing children in 2009-10

	
	
	No. of Children to be continued in NRBC
	No. of NRBC Centre


	No. of Children to be continued in RBC
	No. of RBC Centre


	No. of Children to be continued in NRBC
	No. of NRBC Centre



	
	
	17087
	854
	1007
	20
	3941
	150

	Costing and duration
	Rs. 3000/ child for 1 Year
	
	Funds not proposed.

Children will continue till Nov./ Dec. 09
	
	Funds not proposed.

Children will continue till Aug. 09
	


Time Frame of the AIE Activities: 2009-10
	Activities
	Apr

09
	May

09
	Jun

09
	Jul

09
	Aug

09
	Sep

09
	Oct

09
	Nov

09
	Dec

09
	Jan

10
	Feb

10
	Mar

10

	Identification of bridge course centers I, II & III and Bridge Course volunteers.
	√
	
	
	
	
	
	
	
	
	
	
	

	Identification of scholastic ability of Out of School Children and their priority.
	√
	
	
	
	
	
	
	
	
	
	
	

	 Printing of Bridge Course books.
	√
	
	
	
	
	
	
	
	
	
	
	

	Enrollment drive for Bridge Course I, II & III.
	√
	
	
	
	
	
	
	
	
	
	
	

	Training of Bridge Course volunteers.
	   √
	
	
	
	
	
	
	
	
	
	
	

	 Monthly Review Meeting of AIE coordinators.
	√
	√
	√
	√
	√
	√
	√
	√
	√
	√
	√
	√

	Disbursement of TLM and other material.
	
	√
	
	
	
	
	
	
	
	
	
	

	Starting of Bridge Course I, II and III.
	
	√
	
	
	
	
	
	
	
	
	
	

	Monitoring of mainstreaming of children enrolled during 2008-09 in formal schools.
	
	
	√
	√
	√
	√
	√
	√
	√
	√
	√
	√

	Quarterly assessment of learning levels. 
	
	
	
	√
	
	
	
	√
	
	
	
	√

	Painting and quiz competitions
	
	
	
	
	
	
	
	√
	
	
	
	

	Final evaluation of out of school children.
	
	
	
	
	
	
	
	
	
	
	
	    √

	Mainstreaming of children of 2009 in April 2010.
	
	
	
	
	
	
	
	
	
	
	
	


Recommendations:
	SNo.
	Name of Scheme
	No. of Centres
	No. of Children to be covered
	Unit Cost

	1
	During Enrolment Drive  
	-- 
	8054
	

	2
	NRBC 

(Fresh OSC 7-8 yrs)
	806
	16101
	@ Rs. 30,00/ Child for six months

	3
	NRBC 

(Fresh OSC 9-14 yrs)
	1099
	21960
	@ Rs. 30,00/ Child for one year

	4
	RBC (Fresh OSC)
	21
	1050
	@ Rs. 10,000/ Child

	Total
	1926
	47165
	

	5
	Children to be continued  for one year in NRBC 
	854
	17087
	@ Rs. 1,500/ Child

	6
	Children to be continued  for six months in NRBC 
	198
	3941
	No amount proposed and recommended

	7
	Children to be continued for one year in RBC.
	20
	1007
	


(II) School Infrastructure
A. Civil Works
Overview of the performance of last year and the bottlenecks, if any.

Civil works allocation approved by PAB for AWP&B 2008-09 is Rs.6404.877 lakh including spillover of previous year. The State has incurred expenditure Rs.5892.68 lakh leaving a spillover of Rs.512.197 lakh. The progress report shows spillover of Rs.482.417 lakh. The State has to reconcile these figures. The %age expenditure works out to 92%. The physical completion rate works out to 100.47%. The State team informed that extra completion rate has been actually done in the field and the achievement is more than the target set by PAB. This needs to be reconciled/ verified. State claim to have completed all civil works but there was no technical hand at any level. However State has recently appointed district engineers for all the 20 districts. After detailed analysis it was observed that there are still 2BRCs, 1CRC, 47 new school buildings, 56 building less schools, 96 classrooms 9 verandahs not started and 6 components in progress, for which funds have been spent in earlier years.

Table: 1 Cumulative Progress up to 2008-09 (as on 31st Dec. 08)

(Rs. in lakh)
	SNo.
	Activities
	State Target
	PAB

Target
	Completed
	In progress
	Financial 
	Expenditure

	1
	BRC/ URC
	142
	142
	127
	13
	40585.6565
	40063.46

	2
	CRC
	1300
	1300
	1189
	113
	
	

	3
	New School Building / Branch schools
	307
	534
	204
	51
	
	

	4
	Building Less School
	238
	
	162
	11
	
	

	5
	Upgraded Primary to Upper primary
	134
	134
	13
	121
	
	

	6
	Additional Class Rooms Primary
	7679
	16744
	7117
	518
	
	

	7
	Additional Class Rooms UPS
	8761
	
	8152
	586
	
	

	8
	Drinking Water
	17531
	17628
	18267
	34
	
	

	9
	Drinking Water
	97
	
	88
	9
	
	

	10
	Toilet/ Urinals
	250
	17781
	156
	94
	
	

	11
	Building As Learning Aid(BALA)
	12641
	
	12551
	72
	
	

	12
	Kitchen shed for Mid-Day-Meal
	88
	
	68
	20
	
	

	13
	Headmaster Room UP
	534
	
	544
	 
	
	

	14
	Verandah
	125
	
	116
	9
	
	

	15
	Furniture for upper primary
( No. of Students)
	76548
	
	44710
	31838
	
	

	 
	 
	126375
	
	93464
	33489
	
	


Source: Progress report ending 31st December 2008.

The cumulative outlay upto 2008-09 is Rs.40585.6565 lakh with an expenditure of Rs 40063.46 lakh. The %age expenditure works out to 99%. The State team informed that most of the balance funds shown in the progress report are the contingency provided in the unit cost which has not been spent. The completion rate works out to 74% as on 31st December 2008. The %age expenditure as on 30th September 2008 was 96%. The State is steadily and regularly incurring the expenditure.   

Table: 2 Physical and financial progress AWP&B (fresh works) during 2008-09 (as on 31st Dec. 08)

(Rs. in lakh)
	SNo.
	Activities
	Targets 
	Completed 
	In Progress 
	Financial 
	Expenditure 

	1
	CRC
	146
	62
	84
	6056.1010
	5890.92

	2
	New School Building PS
	31
	1
	30
	
	

	3
	Upgraded Primary to UPS  
	134
	13
	121
	
	

	4
	Additional Class Rooms Primary
	711
	196
	515
	
	

	5
	Additional Class Rooms Upper Primary
	910
	324
	586
	
	

	6
	Toilets/Urinals
	179
	108
	71
	
	

	7
	Separate Girls Toilets
	71
	48
	23
	
	

	8
	Drinking Mater Facility
	97
	88
	9
	
	

	9
	Furniture for Govt. UPS

( No. of students)
	76548
	44710
	31838
	
	

	 
	 TOTAL
	78827
	45550
	33277
	
	


Source: Progress report ending 31st December 2008

The allocation for AWP&B 2008-09 (fresh works) approved by PAB is Rs.6056.1010 lakhs. The State has incurred expenditure of Rs.5890.92 lakhs which is 97% and completion rate is 58%. The financial achievement and completion rate of the State is substantially high as compared to other States.  

 Table: 3 Tentative Cumulative Physical & Financial Progress as on 31st March 2009 

(Rs. in lakh)
	SNo.
	Activities
	Unit Cost 
(in lakhs)
	Sanctioned till Date (Cumulative)
	Completed (Cumulative)
	In Progress (Cumulative)
	Expenditure


	1
	BRC/ URC
	6.00
	142
	138
	2
	852.000

	2
	CRC
	2.00/2.50
	1300
	1305
	1
	2673.000

	3
	New School Building / Branch schools
	3.00/3.50/
4.25/4.75
	307
	258
	2
	1030.500

	4
	Upgraded Primary to Upper primary
	6.02
	134
	134
	 
	806.680

	5
	Building Less School
	3.00
	238
	181
	1
	708.000

	6
	Additional Class Rooms Primary
	1.20/ 1.70/
2.50
	7679
	7688
	 
	11914.500

	7
	Additional Class Rooms Upper Primary
	1.20/ 1.70/
2.50
	8761
	8665
	 
	14359.700

	8
	Toilet & Drinking Water
	0.35/
	17531
	18322
	 
	6135.850

	9
	Toilet/ Urinals
	0.45
	250
	250
	 
	112.500

	10
	Drinking Water
	0.25
	97
	97
	 
	24.250

	11
	Building As Learning Aid (BALA)
	0.02
	12641
	12641
	 
	252.820

	12
	Kitchen shed for Mid-Day-Meal
	0.65
	88
	88
	 
	57.200

	13
	Headmaster Room (UP)
	1.20
	534
	544
	 
	640.800

	14
	Verandah
	1.00/1.20
	125
	116
	 
	141.660

	15
	Furniture for upper primary (No. of Students)
	0.005
	76548
	76548
	 
	382.740

	Total
	
	126375
	126975
	6
	40092.20


Source: State team report

The allocation upto 2008-09 approved by PAB is Rs.40585.6565 lakhs. The State has shown tentative expenditure of Rs.40064.20 lakhs, which is 99%. The completion rate works out to 100.47%, although 6 components are in progress and 208 tentatively not started on 31st March 2009. The State need to be reconciled the target and completion rate with each and every district to arrive at actual position on the ground.   

The actual cumulative physical and financial progress as on 31st December 2008 has been compared with the tentative progress achieved as on 31st March 2009 which is as under:

Period          Targets
     completed
     In Progress     Not Started          Financial











Achievement











(in lakh)

31.12.08       126375

93464

33489



40063.46

31.03.09       126375
            126975
       6

208

40064.20

The State is showing in tentative progress report of 31st March 2009, 6 components in progress and 208 components yet to start but without any financial spill over.Ther appear to be some anomaly in financial achievement. 

Table: 4 Tentative AWP&B 2008-09 Physical & Financial Progress as on 31st March’09

(Rs. in lakh)
	SNo.
	Activities
	Target for 2008-09
	Completed 
	In Progress 
	Expenditure as on 31st March, 2009

	1
	CRC
	146
	146
	-
	365.000

	2
	New School Building 
( Primary)
	31
	31
	-
	147.250

	3
	Upgraded Primary to Upper primary 
	134
	134
	-
	806.680

	4
	Additional Class Rooms Primary
	711
	711
	-
	1777.500

	5
	Additional Class Rooms Upper Primary
	910
	910
	-
	2275.000

	6
	Toilets/Urinals
	179
	179
	-
	80.550

	7
	Separate Girls Toilets
	71
	71
	-
	31.950

	8
	Drinking Mater Facility
	97
	97
	-
	24.250

	9
	Furniture for Govt. UPS

( No. of students)
	76548
	76548
	-
	382.740

	 
	 TOTAL
	78827
	78827
	 -
	5890.920

	Approved Annual Works Plan (Fresh) F.Y. 2008-09
including spill over
 (Rs. In lacs) 
	Expenditure on Civil Works (Rs. In lacs) 
	Percentage Expenditure 

	
	
	

	
	
	

	
	
	

	6404.87700
	5890.920
	91.98%


Source: State Plan AWP&B 2008-09

The State has fresh allocation of Rs.6056.1010 lakhs for 2008-09 and including spillover, works out to Rs.6404.877 lakhs. The State has shown expenditure of Rs.5890.920 lakhs which is 91.98%. The spillover for 2009-10 will be Rs.513.957 lakhs. The completion rate of the components of 2008-09 has been shown ass 100%. If tentative progress of 100% is actually achieved on 31st March, it will be commendable 

The comparison of progress as on 31st December 2008 and as on 31st March 2009 for works approve in AWP&B 2008-09 are as under.

Period          Targets
     completed
     In Progress     Not Started             Financial











   Achievement











   (in lakh)

31.12.08
78827

45550

33277

----

5890.92

31.03.09
78827

78827

-----

----

5890.92

The spillover of AWP&B 2007-08 consisting of 1 BRC, 459 CRCs, 9 Primary school buildings, 1421 additional classrooms and 11441 BALA units have been completed as intimated by the State through E-mail dated 05.03.09. The State has complied with commitment made in PAB 2008-09.

As already mentioned above, State will be tentatively completing all civil works components of AWP&B 2008-09.

Table: 5 Details of Physical and financial spill over for 2008-09 (as on1/04/09)

(Rs. in lakhs)
	SNo.
	Activities
	Physical
	Total
	Total fin.
 

	1. 
	
	Work in progress
	Work not started
	
	

	2. 
	BRC
	2
	2
	4
	

	3. 
	CRC
	1
	
	1
	10.950

	4. 
	New School Building ( Primary)
	2
	47
	49
	14.821

	5. 
	Building less primary
	1
	56
	57
	

	6. 
	Upgraded Primary to UPS 
	
	
	
	24.120

	7. 
	Additional Class Rooms Primary
	
	96
	96
	203.826

	8. 
	Additional Class Rooms UPS
	
	
	
	222.882

	9. 
	Toilets/Urinals
	
	
	
	2.417

	10. 
	Separate Girls Toilets
	
	
	
	0.959

	11. 
	Drinking Mater Facility
	
	
	
	0.728

	12. 
	Verandah
	
	9
	9
	

	13. 
	kitchen sheds
	
	
	
	1.716

	Total
	6
	210
	216
	482.419


Source: State Report

The State team informed that spillover budget of 482.419 lakhs pertain to 3% contingencies only. 

State has almost completed the targets of civil works components barring 2 BRC, 47 New Primary Schools, 56 Building less PS, 96 ACR and 9 Verandah which are yet to start. As per progress report of AWP&B of 2007-08 & 2008-09, all components have been completed. This shows that the spillover components are for earlier years for which funds have been disbursed but works have not been started for one reason or the other.

The appraisal team suggests that State should immediately take up these components to avoid any financial problem at later stage.

Table: 6 Assessments of Gap & Proposals and appraisal team recommendations

	Total requirement
	Status as on 

1-04-2009
	Proposed in 

2009-10
	Gap
	Appraisal team recommendation
	Remarks

	CRC
	199
	185
	14
	185
	If budget is available

	Up gradation of EGS to PS
	82
	69
	13
	69
	Priority

	Saturation of special focus categories SC/ST habitations as worked out by the States (PS)
	6
	6*
	0
	0
	Priority

	New Upper Primary School
	649
	649
	0
	588
	Priority

	ACR
	6448
	4035
	2413
	1833
	After saturation of schools buildings

	Toilet 
	2174
	115(U)
	2059
	115
	After above priorities

	Girls Toilet
	3451
	142
	3309
	142
	After above priorities

	Drinking Water
	591
	24 (U)
	567
	24
	After above priorities

	Major Repairs
	1468
	1468
	0
	0
	Guidelines are not fulfilled

	Boundary Wall Primary
	795260                  ( in mtrs)
	795260                  ( in mtrs)
	0
	0
	After completion of gaps, toilets and DWS

	Boundary Wall Upper Primary
	519056

( in mtrs)
	519056

( in mtrs)
	0
	0
	


Source: State Report

The State has priorities the selection of location of various components provided in the district plan as per MHRD guidelines. 

The requirement of common toilet, Girls toilets and DWS has been worked out for the State but has proposed only for urban areas and Girls toilets. The State is coordinating with the PHE department for convergence of the facilities in the primary and upper primary schools.

The State has completed all the targets of 2007-08 & 2008-09, however some of the components sanctioned earlier before 2006-07 are yet to start.

State has sufficient capacity to build PS, UPS and ACR but they need the technical personals at block and State level to provide resource support to the community so that work is carried out as per design and drawings.

The State has already completed 3620 classrooms in 2007-08 and shall be completing tentatively 4156 classrooms during 2008-09.

· The State can complete the targets recommended by appraisal team for 2009-10 

· The State has 1499 cluster resource coordinators but PAB has approved 1300 buildings for CRC. 199 CRC buildings are yet to be approved. However first priority will be school infrastructure.

· The guidelines for major repairs are not fulfilled.

Table: 7 District wise proposal/recommendation of the major component is appended below
	Name of the District
	Proposal
	Recommendation by appraisal team

	
	EGS up gradation and New PS
	New UPS
	ACR
	EGS up gradation and New PS
	New UPS
	ACR

	Amritsar 
	4
	58
	259
	4
	58
	101

	Barnala
	0
	0
	179
	0
	0
	68

	Bathinda
	2
	12
	321
	2
	9
	132

	Faridkot
	0
	0
	81
	0
	0
	81

	Ferozepur
	9
	64
	558
	9
	55
	110

	Fatehgarh Sahib
	7
	31
	35
	7
	28
	35

	Gurdaspur
	2
	88
	466
	2
	86
	130

	Hoshiarpur
	3
	64
	127
	3
	64
	99

	Jalandhar
	2
	11
	107
	2
	11
	107

	Kapurthala
	8
	31
	251
	8
	24
	85

	Ludhiana 
	0
	4
	102
	0
	4
	102

	Mansa
	24
	10
	240
	24
	4
	75

	Moga
	0
	4
	234
	0
	4
	140

	Mohali
	2
	53
	52
	2
	38
	0

	Muktsar
	0
	5
	411
	0
	5
	136

	Nawanshahr
	1
	26
	40
	1
	16
	40

	Patiala 
	2
	45
	149
	2
	45
	149

	Ropar
	3
	100
	90
	3
	98
	0

	Sangrur
	0
	5
	201
	0
	1
	201

	Tarn Taran
	0
	38
	132
	0
	38
	42

	Total
	69
	649
	4035
	69
	588
	1833


As per MHRD guidelines the priority for school infrastructure is to be for up-gradation of EGS, New PS, New UPS, ACRs, Toilets and Drinking Water facilities, Boundary Walls etc. The gaps are to be taken as per availability of ceiling for civil works.

Analyzed DISE data of 2008-09 (30th September 2008) and the ACR analysis of DISE 2006-07 by TSG for comparison are as under

	SNo.
	Districts
	Gap in Classrooms as per DISE 2008-09/ actual Survey
	Gap in Classrooms as per DISE 2006-07 

	1. 
	Amritsar
	580
	-148

	2. 
	Barnala
	258
	

	3. 
	Bathinda
	321
	32

	4. 
	Faridkot
	148
	-17

	5. 
	Ferozepur
	581
	-38

	6. 
	Fatehgarh Sahib
	89
	-125

	7. 
	Gurdaspur
	619
	-4

	8. 
	Hoshiarpur
	246
	-2

	9. 
	Jalandhar
	383
	-4

	10. 
	Kapurthala
	251
	-20

	11. 
	Ludhiana
	370
	-10

	12. 
	Mansa
	326
	-2

	13. 
	Moga
	246
	-1

	14. 
	Mohali
	127
	103

	15. 
	Muktsar
	415
	-34

	16. 
	Nawanshahr
	65
	-79

	17. 
	Patiala
	385
	89

	18. 
	Ropar
	187
	-135

	19. 
	Sangrur
	484
	30

	20. 
	Tarn Taran
	367
	512

	Total
	6448
	766


There are substaintail variations in the DISE data for ACR. The gaps in ACR were discussed with State team and SPD, it was informed that there has been increase in enrollment and also DISE data has been collected very carefully during the current year. The gap is near actual and has to be relied upon. The appraisal team is taking DISE data worked out by State of 2008-09 for all intent and purposes for AWP&B 2009-10.  

Table: 9 PS & UPS SANCTIONED YEARWISE
	Schools
	2001-02
	2002-03
	2003-04
	2004-05
	2005-06
	2006-07
	2007-08
	2008-09
	Total Sanctioned
	Schools opened

	PS
	
	
	
	
	
	88
	9
	31
	128
	128

	UPS
	
	
	
	
	
	
	1
	134
	135
	135


Table: 10 PS & UPS BUILDINGS SANCTIONED YEARWISE

	Schools

Buildings
	2001-02
	2002-03
	2003-04
	2004-05
	2005-06
	2006-07
	2007-08
	2008-09
	Total Sanctioned

	PS New
	
	
	
	
	
	88
	9
	31
	128

	PS Re Cons
	
	
	
	
	
	
	
	
	

	UPS New
	
	
	
	
	
	
	1
	134
	135

	UPS Re Cons
	
	
	
	
	
	
	
	
	


Note: As per Statement above, the State has already saturated school buildings upto 2008-09 and no backlog has been left for 2009-10.

Unit Cost: - The State has proposed revised unit cost as given in the plan. The revise unit cost and unit cost approved in 2008-09 are given below:

Table: 11 Proposed revised rates for civil works based on revise PWD rates. (Unit Cost)

	Name of work
	Plinth area (Sqm)
	Plinth area Rate
( in Rs.)
	Total Unit Cost
( in lacs)
	Less (10% contractor profit)
= iv-(10% of iv)
	3% cost for supervision & Monitoring
=3% of v
	Total unit cost (In Lakhs)
	Previous Unit Cost (In lakhs)
	Proposed Unit cost for 2009-10

	i
	ii
	iii
	iv
	v
	vi
	vii
	viii
	Ix

	Upper pry. school
	220.37
	5922/
	13.05
	11.75
	0.35
	12.10
	6.200
	9.270

	Pry School
	158.27
	6407/
	10.14
	9.13
	0.27
	9.40
	4.893
	6.180

	CRC/ ACR 
	89.88
	5786/
	5.20
	4.68
	0.14
	4.82
	2.575
	2.575

	Toilets
	9.10
	16483
	1.50
	1.35
	0.04
	1.39
	0.450
	0.515

	Girls toilets
	9.10
	16483
	1.50
	1.35
	0.04
	1.39
	0.450
	0.515

	HM room (UP)
	55.39
	8215/
	4.55
	4.10
	0.12
	4.22
	 
	1.545

	Verandah
	16.72
	5144/
	0.86
	0.77
	0.02
	0.80
	 
	0.618

	DWS
	 
	 
	 
	 
	 
	 
	0.250
	0.309

	Major Repair
	 
	 
	 
	 
	 
	 
	 
	As per estimate 

	Boundary wall PS
	 
	 
	 
	 
	 
	 
	 
	0.00845 per mtr.

	Boundary wall  UPS
	 
	 
	 
	 
	 
	 
	 
	0.00845 per mtr.

	Electrification 
	 
	 
	 
	 
	 
	 
	 
	0.750

	Electrification UP
	 
	 
	 
	 
	 
	 
	 
	0.900

	Furniture
	 
	 
	 
	 
	 
	 
	0.005
	0.005


Source: State Plan

The State has revised unit cost of Primary school, Upper primary school, HM Rooms, electrification and Boundary wall. The State team has not brought any notification for the new unit cost. The matter was discussed with SPD on 06.03.09 who happened to be in Delhi. He informed that unit cost has already been approved by the Secretary School Education Punjab on the file. He further informed that he was not aware of the procedure that the unit cost is also to be notified. He assured that unit cost will be got notified at the earliest possible and requested for providing new unit cost. The unit cost of UPS includes sanitation block, kitchen shed and 3 classrooms with HM rooms. The primary school will have 2 classrooms, toilet block, kitchen shed. All ACRs, UPS, PS also include Bala elements in the unit cost. The State has provided 3% contingency charges for third party evaluation.

The electrification of primary and upper primary schools appears to be high and some model estimates on pilot basis may be prepared to arrive at average unit cost. Until the exercise is done, the item of electrification is not to be taken in the AWP&B 2009-10. 

Appraisal team recommends new unit cost in the AWP&B 2009-10, except electrification.

B. Major Repairs 

Table: 12 Proposals for Major Repairs
	SNo.
	Name Of District`
	Proposal  for 2009-10

	
	
	Physical
	Financial

	1
	Amritsar
	77
	41.64

	2
	Bathinda
	25
	64.64

	3
	Barnala
	37
	71.08

	4
	Faridkot
	16
	8.23

	5
	Ferozepur
	115
	167.75

	6
	Fatehgarh Sahib
	82
	223.70

	7
	Gurdaspur
	349
	308.18

	8
	Hoshiarpur
	149
	370.44

	9
	Jalandhar
	73
	92.49

	10
	Kapurthala
	61
	31.27

	11
	Ludhiana
	22
	30.11

	12
	Mansa
	16
	27.82

	13
	Moga
	30
	53.15

	14
	Muktsar
	45
	66.52

	15
	Mohali
	21
	15.68

	16
	Nawanshar
	29
	59.95

	17
	Patiala
	133
	113.71

	18
	Ropar
	30
	23.96

	19
	Sangrur
	94
	141.18

	20
	Tarn Taran
	64
	100.15

	Total
	1468
	2011.64


· The State has prepared estimate for major repair for all district. Appraisal team has seen some of the estimates and these are of routine type, without applying the technical requirement for such repairs. Photographs of these buildings have also been taken and brought for appraisal teams. The details required as per guidelines for year of construction and name of the school has also be given, however these are not part of the district plan.

· The decentralized system of technical and financial assessment and approval for major repairs is not in place at the district level.

· The State has not developed repair manual for carrying out major repair.

· As major repairs need special attention and technical supervision at block level which is not available presently.

As the above three parameters are not met with, appraisal team do not recommend the major repair components for 2009-10. 

C. Furniture:

Table: 13 Proposals for Furniture

	Name of the District
	Proposal

	
	Physical
	Financial

(in lakh)

	
	No. of Upper Primary Schools
	No. of Students
	

	1
	Bathinda
	24
	17.17

	2
	Ferozepur
	226
	106.17

	3
	Gurdaspur*
	473
	303.79

	4
	Hoshiarpur
	310
	208.82

	5
	Jalandhar
	115
	65.95

	6
	Kapurthala
	68
	22.75

	7
	Ludhiana
	159
	88.18

	8
	Muktsar
	89
	42.24

	9
	Mohali
	26
	17.82

	10
	Nawanshar
	85
	57.37

	Total
	1575
	186046
	930.23


SFD A & B districts –* Gurdaspur - SFD A

The furniture can only be approved if the allocation of the district is within 24% of the AWP&B. The State has large infrastructure gaps in up-gradation of EGS, UPS and Classrooms. In case in particular district where the allocation is below 24%, the furniture item can be give. 

Detail of SFD A and B district if any

The State has Gurdaspur and Ropar district with adverse PS : UPS ratio where 50% allocation can be given mainly for UPS. The State has no SFD B category district having more than 3000 classrooms gaps. 
Table: 14 Management Structure in Civil work

	Post
	Sanctioned
	Filled
	Vacant

	State level

	Executive Engineer
	1
	
	Recruitment is in  process

	Deputy Manager (CW)
	1
	1
	

	Asstt. Manager (CW)
	4
	1
	

	Expert
	
	
	

	Junior Engineer
	
	
	

	District Level

	Sub Divisional Engineer
	20
	20
	

	District Resource Persons
	24
	24
	

	Asst. Engineer
	
	
	

	Coordinator
	
	
	

	Block level

	Junior Engineer
	
	
	

	Block Resource Persons
	216
	216
	

	Total
	266
	262
	


State has approved 5 non technical personals at State level, 24 district resource persons at district level 216 block resource persons at block level. Appraisal teams recommend that instead of non technical personals at State and block level. The State may recruit Technical personals as per MHRD guidelines at all levels to provide necessary technical resource support and adequate technical supervision for large components being sanctioned during 2009-10.  State has recently recruited only 20 SDEs one for each districts.

Third Party Evaluation:
State has recruited recently district engineers for all the districts but has neither technical personals at State level and block level. The State has not been able to engaged third party evaluation so far. The system leaves the civil works constructions at the mercy of non technical people. The State should immediately employ technical personals at all levels and also start third party evaluation without further delay. 

School Mapping:
The school mapping has been not started so far. The State team informed that process has initiated for taking up school mapping. 
 

Environmental assessment:


The Joint Secretary-II had advised through D.O.No3-6/2008-EE.16 dated November 17, 2008, advised all the State and UTs to completed school environmental assessment of 1/3rd of the school during the current financial year as per commitment made to the Development Partners to meet their funding conditions. The State has not initiated the environmental assessment so far. 

Asset Register:


The State team informed that the asset register school wise, compiled at block and district level have been completed. The State was advised to send the register to the Divisional Head looking after Punjab State.

Issues:
· As per spill over works at Table 5 the State has 2 BRCs, 47 New School Buildings, 56 Buildings-less schools, 96 Classrooms and 9 Verandah still not started from target approved by PAB before 2006-07 and 6 components in progress. As per State report funds have since been disbursed to VDCs since long. These components must be started immediately to avoid any problems with the passage of time.

· As per Table 14 the State has non technical personals 5 at State level 24 at district level and 216 at block level to look after civil works. These personals can be replaced with technical personals for providing necessary technical resource support and adequate supervision for civil works components.

·  State need to monitor the building maintenance funds more effectively as some of the photographs shows that buildings have not been maintained for many years. 

(III) Quality Related Issues

1. Information about Learning Achievement (LA) Surveys:

a. Nature and frequency of Learning Achievement Surveys in the State

Learning achievement of students has been analyzed based on DISE and NCERT’s learning achievement survey findings and also based on quality monitoring formats collected quarterly. Brief reflections are as under. 

Feedback from DISE: Learning achievement trends are reflected in the under mentioned table, available since 2003-04. 
Learning achievement as per DISE
	DISE refer. Year
	Class V
	Class VII

	
	Passed
	Passed with >60%
	Passed
	Passed with >60%

	DISE 2003 - 04
	135409
	20635
	82893
	16881

	DISE 2004 - 05
	294764
	64083
	156515
	23951

	DISE 2005 - 06
	248471
	56094
	134475
	25832

	DISE 2006 – 07
	254519
	51596
	154199
	22813

	DISE 2007 - 08
	236763
	78193
	127859
	16792


The data reveals no clear trends in the pass percentage as well as in the percentage of students scoring < 60% at class V and VII levels. The up and down trend is sporadic and indicates that the State does not have any strategic intervention, which could be identified as a key to usher in a clear quality road map

Findings of NCERT study on learning achievement (BAS and MAS): The NCERT study on learning achievement of students at the end of class III, V, and VII/ VIII reveals the following picture.

	    
	Language
	Maths
	EVS
	Social Science

	
	BAS
	MAS
	BAS
	MAS
	BAS
	MAS
	BAS
	MAS

	Class III
	54.29
	66.98
	53.89
	58.07
	
	
	
	

	National Average
	63.12
	
	58.25
	
	
	
	
	

	Class V
	58.04
	57.75
	49.62
	48.43
	50.18
	49.69
	
	

	National Average
	58.37
	60.31
	46.51
	48.46
	50.30
	52.19
	
	

	Class VII
	
	
	
	
	
	
	
	

	National Average
	54.24
	51.24
	30.50
	38.76
	37.78
	39.87
	34.04
	40.89

	Class VIII
	25.61
	59.41
	32.57
	41.97
	26.51
	41.32
	22.53
	45.92

	National Average
	53.86
	56.13
	39.17
	41.50
	41.30
	41.75
	46.19
	46.94


Source: NCERT's BAS and MAS

The Appraisal Team has looked at the findings of the NCERT’s Base Line Achievement Survey for Classes III, V and VIII for a broad idea about the performance of students. Following table provides the information along with the national mean averages. 

Learning Achievement of students on NCERT’s BAS

	State
	Class III
	Class V
	Class VIII

	
	Language
	Maths
	Language
	Maths
	EVS
	Language
	Maths
	Sc.
	S. Sc

	Punjab
	54.28
	53.89
	59.23
	49.62
	50.18
	25.42
	32.51
	26.31
	22.35

	National Mean Avg
	63.12
	58.25
	58.57
	46.51
	50.30
	52.45
	38.47
	40.54
	45.00


Source: NCERT’s BAS findings

The above table reflects over all performance of the children in different subjects and the key observations are as under:

· At class III level the children have low performance as against the National mean.

· In class V the performance is slightly better or comparable to the National average.

· Achievement level in class VIII is although poor in all the subjects as compared to the national average, hence it needs improvement at all levels in each subjects.

Following table compares the findings of the BAS and MAS of NCERT for class V. 

Learning Achievement of students in NCERT’s BAS and MAS

	State
	EVS
	Language
	Mathematics

	
	BAS
	MAS
	BAS
	MAS
	BAS
	MAS

	Punjab
	50.18
	49.69
	58.04
	57.75
	49.62
	48.43

	Weighted Mean
	50.30
	52.19
	58.57
	60.31
	46.51
	48.46


Source: NCERT’s BAS and MAS findings

The above table indicates that there is a decreasing trend in the performance of students in MAS over BAS. 

The trends emerging out of the above reflections that the State needs to improve the performance of schools and students, on a continuous basis through organized pedagogical renewal processes and also suggests, that academic support system and monitoring mechanism needs to be strengthened on priority.

Parrho Punjab Programme: 
1. The State started a massive campaign in 2008-09 to improve the competencies, particularly in language and mathematics at primary and upper primary levels , adopting the following strategies.
 
· All the primary teachers were trained on special teaching methods to achieve the goal of 15% learning enhancement in reading, writing & arithmetics for primary children. 

· The teachers were thoroughly trained to undertake baselines and identify the learning levels of children. 

· Baseline for primary children as done by the school teachers in the beginning of academic session 2008-09 revealed that 23.3 children in standard-I could only read letters, 25% children in standard-III could read paras and 46% children of standard-V could read stories. 

So far as numerical skills were concerned, 14.6% children of standard-I could recognize numbers, 18% children of standard-III could perform subtraction and 29% children could perform division. 

· Supplementary reading material was developed with the help of primary school teachers for LEP. This included colorful reading cards, letter and number charts, posters, school registers, problem books and teaching manual for teachers. 

· The primary school children were divided into 5 different groups on the basis of their performance levels in reading of languages and numeric’s. 

· Specialized intensive teaching was imparted to the focus groups by the trained school teachers.

· Mid term evaluation of the programme was done by the block master trainers during November, 2008 which showed a significant improvement in the learning levels of the children. For example :   Number of letter readers of class-I had increased by 19.5 PP, number of para readers of class-III had increased by 8% and that of story readers of class-V had increased by 13%. 

As regards the mathematical skills, the children of standard-I who could recognize numbers had increased by 5%, number of students of standard-III who could perform subtraction had increased by 8% and the number of students of standard-V who could perform division had increased by 12%.

· Final Evaluation of the Programme has been planned for first week of March and it is expected that there will be further improvement in learning amongst primary children.

2. Modalities and Strategies under Parrho Punjab Programme: 

Basic Model: 

· All teachers (over 98%) were trained in special teaching methods to take up learning issues at the school level. 

· Teachers were given simple learning goals in reading, writing and arithmetic. 

· Goals were thrashed out in these meetings and teachers took up the LEP agenda as per the goals.

· At the end of the trainings teachers went to the schools to do a quick evaluation of their schools/classes. 

· This helped teachers to know where the school stood with respect to the goals and helped them identify which children needed focus.

· Teachers were supplied with supplementary reading material aligned to the training.

· Monitoring and support of teachers with fortnightly visits to help teacher achieve goals.

Specialized Academic Leaders at District and Block levels : 

· SSA Punjab appointed Parrho Punjab District Coordinators from the teachers’ cadre in each district. To support them, Assistant District Coordinators were appointed.

· In each block, 3 to 5 Block Master Trainers were chosen. These BMTs are enthusiastic primary school teachers with a good knack for training. 

The results of the programme yielded a success rate which was beyond expectation from base line to mid term assessment. The findings are reflected in the following table giving a district wise comparison from base line to mid term

Findings from other learning achievement surveys in the State (subject wise, class wise, district wise learning achievement):  District wise

	Parrho Punjab State Report Card - MID TEST

	PUNJAB 

	District-wise Comparison of Baseline vs Mid Test 

	District Name
	No. of Schools
	Reading
	Math

	
	
	Std 1 - Ability to Read Letters
	Std 3 - Ability to Read Para
	Std 5 - Ability to Read Stories
	Std 1 - Ability to Recg Nos.
	Std 3 - Ability to Subtract
	Std 5 - Ability to Divide

	
	
	Base-line
	Mid-test
	Base-line
	Mid-test
	Base-line
	Mid-test
	Base-line
	Mid-test
	Base-line
	Mid-test
	Base-line
	Mid-test

	Gurdaspur
	1452
	14.4
	31.1
	17.2
	23.8
	36.0
	49.0
	11.5
	18.4
	12.8
	19.3
	20.0
	28.7

	Faridkot
	238
	14.7
	38.1
	12.6
	20.6
	38.1
	52.8
	6.9
	8.9
	9.4
	16.6
	25.6
	36.6

	Moga
	346
	30.3
	44.8
	27.1
	30.9
	44.8
	58.1
	22.9
	23.4
	20.6
	26.0
	32.0
	40.4

	Ludhiana
	838
	21.6
	37.7
	24.0
	31.3
	43.8
	55.2
	13.4
	17.5
	16.7
	23.8
	24.4
	35.4

	Fatehgarh Sahib
	439
	18.9
	44.5
	22.9
	31.8
	46.0
	59.6
	8.0
	10.6
	14.0
	24.9
	26.2
	44.2

	SAS Nagar
	380
	18.3
	38.1
	21.2
	28.1
	40.5
	50.9
	13.4
	15.7
	18.5
	24.5
	33.5
	44.4

	Muktsar
	300
	25.4
	42.4
	25.0
	32.8
	56.0
	65.6
	15.5
	23.4
	14.8
	24.7
	32.5
	46.3

	Bhatinda
	362
	18.9
	47.3
	24.5
	36.7
	44.5
	64.3
	6.6
	16.6
	11.8
	29.0
	22.6
	44.2

	Barnala
	169
	27.7
	46.0
	28.2
	36.6
	50.7
	62.1
	10.8
	17.1
	17.5
	26.8
	29.5
	40.1

	Sangrur
	631
	20.2
	38.7
	26.4
	32.6
	48.2
	58.2
	9.0
	13.3
	14.4
	22.4
	26.9
	39.2

	Mansa
	260
	30.6
	50.4
	32.5
	42.8
	58.7
	73.1
	19.2
	27.0
	21.2
	32.8
	42.2
	54.3

	Amritsar
	763
	29.8
	39.4
	29.4
	32.2
	46.4
	53.9
	25.1
	32.2
	22.7
	23.7
	30.6
	35.2

	Patiala
	939
	23.8
	39.3
	25.9
	34.2
	49.9
	59.7
	17.1
	24.9
	22.5
	29.3
	31.8
	41.8

	Kapurthala
	427
	17.2
	36.0
	15.8
	23.6
	37.1
	52.5
	11.4
	11.8
	11.7
	20.4
	20.8
	34.3

	Hoshiarpur
	1260
	24.0
	50.4
	32.7
	45.7
	52.4
	66.4
	14.1
	26.4
	23.5
	35.2
	34.5
	48.8

	Taran Taran
	496
	23.7
	42.7
	21.3
	26.7
	37.2
	45.8
	17.9
	27.3
	15.9
	20.2
	20.5
	29.6

	Jalandhar
	924
	29.0
	40.0
	28.0
	33.0
	49.2
	59.1
	22.4
	18.6
	23.8
	28.8
	31.9
	40.6

	Nawan Shehar
	435
	23.5
	48.2
	26.7
	37.5
	42.5
	62.4
	15.1
	17.7
	22.2
	30.3
	29.4
	48.3

	Ropar
	479
	26.2
	50.3
	31.0
	45.3
	53.0
	68.2
	16.1
	27.5
	25.2
	37.9
	40.6
	54.2

	Ferozepur
	1075
	26.7
	44.6
	26.2
	29.5
	50.8
	60.9
	16.1
	15.2
	18.3
	26.6
	32.7
	45.5

	Punjab Total*
	12213
	23.3
	42.5
	24.9
	32.8
	46.3
	58.9
	14.6
	19.7
	17.9
	26.2
	29.4
	41.6

	* Please note "Punjab Total" is an average of the district data and not calculated directly. The difference is minor. 


The following table reflects the over all picture of the comparative difference in improving the competencies in reading, writing and Mathematics from class I to class V, which is quiet encouraging and based on the success, the state has planned to further strengthen the initiative in2009-10.

	MID TEST

	Dec 10th
	Enrolment
	Reading (%ge)
	Writing 
(%ge)
	Math (%ge)

	
	
	
	
	

	Class
	Total Tested Children
	%ge from Baseline
	Story
	Para
	Word
	Letter
	Beginner
	Can Write
	Cannot Write
	Division 
	Subtrac-tion
	Addition
	Number Recg
	Beginner

	
	
	
	
	
	
	
	
	
	
	
	
	
	
	

	
	
	
	
	
	
	
	
	
	
	
	
	
	
	

	Std 1
	248062
	99.2
	0.1
	0.4
	5.4
	35.0
	59.1
	6.6
	93.4
	0.1
	0.3
	2.0
	17.9
	79.6

	Std 2
	248067
	95.4
	1.9
	6.8
	22.0
	43.4
	26.0
	15.4
	84.6
	0.2
	5.1
	14.4
	30.5
	49.8

	Std 3
	265657
	97.1
	14.3
	18.0
	26.7
	30.3
	10.6
	34.8
	65.2
	3.4
	22.0
	24.6
	24.4
	25.6

	Std 4
	255787
	97.3
	35.8
	21.6
	21.1
	16.9
	4.6
	54.8
	45.2
	17.5
	33.2
	22.5
	14.7
	12.0

	Std 5
	241244
	97.7
	58.1
	18.5
	13.3
	8.3
	1.8
	71.7
	28.3
	40.1
	31.5
	16.0
	7.4
	5.0

	Total 
	1258817
	97.3
	21.8
	13.1
	17.8
	26.9
	20.4
	36.6
	63.4
	12.0
	18.5
	16.1
	19.1
	34.3


	BASELINE

	Dec 10th
	Enrolment
	Reading (%ge)
	Writing 
(%ge)
	Math (%ge)

	
	
	
	
	

	Class
	Total Tested Children
	Story
	Para
	Word
	Letter
	Beginner
	Can Write
	Cannot Write
	Division
	Subtrac-tion
	Addition
	Number Recg
	Beginner

	
	
	
	
	
	
	
	
	
	
	
	
	
	

	
	
	
	
	
	
	
	
	
	
	
	
	
	

	Std 1
	250017
	0.1
	0.2
	3.6
	19.6
	76.5
	15.6
	84.4
	0.1
	0.3
	1.2
	13.9
	84.6

	Std 2
	259993
	1.1
	4.3
	20.4
	38.7
	35.6
	31.1
	68.9
	0.2
	3.6
	12.1
	31.8
	52.3

	Std 3
	273602
	9.4
	16.0
	29.3
	29.8
	15.5
	45.2
	54.8
	2.1
	16.1
	25.3
	29.3
	27.3

	Std 4
	262878
	26.3
	22.7
	26.1
	17.7
	7.1
	59.5
	40.5
	11.6
	29.0
	25.7
	20.1
	13.7

	Std 5
	247028
	46.5
	22.8
	18.3
	9.4
	3.0
	72.6
	27.4
	29.0
	32.0
	21.2
	11.4
	6.3

	Total 
	1293518
	16.5
	13.3
	19.8
	23.3
	27.2
	45.0
	55.0
	8.5
	16.3
	17.3
	21.5
	36.4


b. Learning difficulties identified in different subjects where children score low and need more academic support are as under:

(i) Class I and II: identification of letters and numbers.

(ii) Class II: addition and Subtraction.

(iii) Class III & IV: flow and reading, division and multiplication.

(iv) Class V: English reading, expression, vocabulary and division 3 digits onwards.

(v) Class VI, VII and VIII : vocabulary, flow and reading in comprehension conceptual understanding

(vi) Difficulty in understanding the historical events and developments and in relating the history to the real life situations.

c. Major Factors affecting Learning Achievement:

Attendance of teachers, attitude of teachers, adequate use of teaching aids, participatory approach of teaching learning, moral and academic home support, periodic assessment of the learning levels by the class teachers and appropriate remediation for the weak areas are some of the important factors effecting the learning achievements of students. Regular orientation and familiarity of the teacher with innovative and effective ways of teaching boosts up the learning amongst the students.

d. Vision of quality education and effective classroom in different subjects:

Overall highlighting points, reflecting the vision of the State regarding quality education are listed below:-
(i) The state visualizes the kind of classrooms, schools and quality education where every school building is complete, beautiful, clean and well planted, classrooms are fully furnished with appropriate seating for students and teachers, black boards, innovative teaching learning aids, and computers & projectors etc.. 

(ii) The kind of education where children learn the art of free communication and expression and become confident to compete with the world outside.

(iii) The quality where teacher comes fully prepared with all the essential teaching aids, transacts the business with the complete devotion, interacts and communicates openly with children, pays individual attention to the children, adopts participatory approach for teaching learning, make quick assessment of the learning acquired by every student in every subject and takes requisite remediation in the class in routine. 

(iv) The quality where every child loves to read write and perform numerical functions.   The quality where every need of the child is given due care and importance.

(v) The kind of quality education where children don’t have to depend on rote memory.  

(vi) Such pattern of examination which tests the logical reasoning of the child.

(vii) The quality, which leaves no scope for copying in the examination, rather the child should be confident enough to write exams and perform independently to secure good scores in all the subjects.

Overall goals regarding Quality Improvement in the next 3 years:
(i) 100% children at primary level should be able to fluently read and write.

(ii) The pass percentage at class V & VIII to be 100%.

(iii) The percentage of first divisionary to go up by 50% at least.

Nature of desired pedagogic processes and learning environment for each subject areas are envisioned as under:

Language:
Model reading and writing by teacher, emphasis on vocabulary, independent and free reading /writing sessions, constant monitoring by class teacher, interactions by teachers with students to build up their communication skills.

Mathematics:
Intensive practice of fundamental operations, use of black boards by teachers and note books by students, use of graphs, use of mathematical games and activity based learning.

Science:
Exposure to nature, experimentation, demonstration, practical work in classroom and labs, project works, emphasis on drawing, debates and quiz competitions.

Social Science:
Exposure visits, use of maps, reflections on social issues, project works, surveys, debates and quiz competitions.

Arts Education: 
Identification of hidden talents, teaching art and providing a platform for development of art education by way of arranging competitions in schools, blocks, districts and so on, honoring the best performer in public functions, Integration of arts with all school subjects.

e. Development of Verifiable Learning Indicators class-wise and subject-wise:

The State has reported that learning indicators have been developed in each subject area. The appraisal team appreciates the pedagogically sound initiative under taken by the State, which is in a right direction. The following table gives a brief account of the learning indicators identified for different classes in different subjects.

	Class
	Subject
	Learning Indicators / Competencies

	I & II
	Language
	Confidence in speech, flow in reading and writing

	I & II
	Maths
	Number Concept, oral and written problems, identification of mathematical patterns, simple addition and subtraction

	I & II
	EVS
	Observation, classification, drawing and labeling.

	III & V
	Languages (Punjabi, Hindi & English)
	Fluent reading and expressions, sequence of expressions, Comprehension and expression.

	
	Mathematics
	Four Fundamental operations, number concept, oral and written problems solutions.

	
	EVS
	Conceptual Understanding, Mapping Skills, Projects, Field experiments and process skills, drawing and labeling.

	VI & VII
	Languages
	Fluent Reading, comprehension and expressions of different discourses, writing two or three paras about know things and coherent writing and use of language discourses, vocabulary and its usage.

	
	Mathematics
	Basic competencies of multiplication and division, conceptual understanding, problem solving, developing maths problems.

	
	Science
	Conceptual understanding, experimentation, reporting, analysis and inference, drawing, labeling and explanation, project works, questioning and logical reasoning.

	
	Social Science
	Conceptual understanding and reflection on social issues, information acquisition skills, recording, reporting, analysis, inference, mapping skills, project works.


2. Designing of all inputs and related processes:

a. Role of community: 
The State has informed that in order to improve the ownership of the community and invoking the partnership with the school for quality improvement, the VEDCs and Community were involved in the following activities during 2008-09:-

(i) Implementation of all the education programmes in the schools.

(ii) Carrying out all the civil works in the schools.

(iii) Identifying out of school children in the villages.

(iv) Providing land for the upgradeable EGS centres

(v) Bringing out of school children to AIE centres and schools.

(vi) Helping the state govt. machinery to locate CWSN.

(vii) Encouraging the parents of special children to send their wards to the regular schools.

(viii) Appointment of education volunteers in schools and AIE centres.

(ix) Monitoring the classroom process.

(x) Monitoring the regularity of school teachers and students.

(xi) Assisting the school authorities in economical procurement of the items required for school.

Inputs and processes related to community mobilization 

State has planned for a training of 113814 community members for two days during 2009-10. The utilization of the community training grant will be done to impart training to the community leaders and VEDCs members to make them aware of the new educational schemes, welfare schemes, social issues & gender issues and to involve them in the improvement of overall educational scenario. Community will be sensitized towards the improvement in the children attendance, teacher’s attendance and involvement in the school development.

b. Role of Teacher: 

Information on Teachers (as on Dec end 2008)

	
	Sanctioned Post
	Working
	Vacancies

	
	By State
	Under SSA
	Total
	By State
	Under SSA
	Total
	By State
	Under SSA
	Total

	PS
	
	2500
	2500
	
	2400
	2400
	
	100
	100

	UPS
	
	405
	405
	
	405
	405
	
	
	


i.   Status on teacher vacancies and the state policy on filling these vacancies:

As per the DISE 2008 there have been 13409 vacant posts for primary teachers and 8026 for upper primary teachers. But as the state government has recruited around 10,678 primary teachers (10,000 teachers against state govt. posts and 678 primary teacher against SSA posts) and 4405 upper primary teachers (4000 teachers against state govt. posts and 405 against SSA posts), the net vacancies as of now are very small in numbers. The next round of appointments will certainly fill up the gap, if any. 

ii. State policy and steps taken towards teacher rationalization.
State has a well-defined policy for teacher rationalization under which teachers are shifted from concentrated/low PTR schools to the deficient/ high PTR schools. Rationalization of teachers is a constant and regular phenomenon. In the recent past 2000 teacher posts at primary and upper primary level were rationalized.

iii. Performance in reference to appointment of teachers:

Recruitment of teachers

	
	Sanctioned in PAB till 08-09
	Recruited by 

March 09
	Honorarium
	Selected by

	
	Regular
	Para
	Regular
	Para
	Regular
	Para
	State/ Distt./                Community

	Primary
	-
	2500
	-
	2500
	-
	12000 per month
	SSA.Pb

	Up. Primary
	-
	405
	-
	405
	-
	13500 per month
	SSA.Pb


iv. Number of single teacher schools (based on EMIS- data to be provided by MIS) 

As per DISE 2008 there were 1235 single teacher schools at primary level and 65 single teacher schools at upper primary level. Let it be clarified that this was the position prevailing in September 2008.

v. Strategies of the districts/ state for achieving the goal of no school with single teacher in 2009-10

Since 15083 teachers (10678 primary and 4405 upper primary teachers) have been appointed during November- December 2008, virtually there is no single teacher school as of now. However the process of rationalization of teachers and new appointments against the vacancies, if any, will continue during 2009-10.

Information on PTR

	Number of schools in respect of PTR
	State PTR

	>40
	>50
	>60
	>70
	>80
	>100
	

	1625
	785
	421
	241
	239
	235
	25.83


vi. Highlight States/districts with higher PTR

Going by the working no. of teachers as per DISE carried out in September, 2008, few districts namely Barnala (55.42), Bathinda (46.47), Moga (43.35), Muktsar (51.41), Sangrur (40.75) and Tarn Taran (40.32) have higher PTR at primary level. 

In view of sorting out the high PTR issue, as explained above the State govt. made new appointments of 10678 primary teachers done in the month of November-December, 2008 as well as the rationalization carried out during 2008-09. The above mentioned districts have normal PTR at primary level as of now. .Rationalization of teachers posts and appointment against vacancies is regularly followed in the state. In the recent past 2000 teacher posts were rationalized. The teachers were shifted from concentrated/low PTR schools to the deficient/high PTR. Similarly, 10678 primary teachers and 4405 upper primary teachers have been appointed against the vacant posts in the third quarter ending December, 2008.The efforts made by the State towards filling of vacant posts and also taking up rationalization process to sort out the PTR issue is worth commendable and complied with the commitment made in 2008-09.

The following table reflects that State has no requirement of additional teachers on account of high PTR any more.

	Total requirement of Additional teachers ( as per PTR of 40:1)
	Number proposed in 2009-10
	Gap

	-nil-
	-nil-
	          -


Recommendations:

Since the State has the status of over all PTR with in normal range, there is no requirement of additional teachers, hence no additional teacher is recommended.

c. School readiness: 
It is good to note that the over all progress of the state in utilizing the grants has been good. The releases of the grants has been timely and also cent per cent. The following table gives an over all account of the progress as well as the proposal for 2009-10.

Overall progress of Grant Distribution (Teacher grant, School grant, TLE grant)

	Distribution of Grants
	Progress in 2008-09
	Proposal for 2009-10

	
	Physical Target
	Achievement
	Percentage of Achievement
	Phy  

	a. Teacher grant @ Rs. 500/- per teacher
	 
	 
	 
	 

	Primary level
	34246
	34246
	100%
	49361

	Upper Primary level
	39993
	39993
	100%
	51773

	Total
	
	
	
	101134

	b. School grant 
	
	
	
	

	Primary level @ Rs. 5000/-per school
	13285
	13285
	100%
	13559

	Upper Primary level @ Rs. 7000/-per school
	5424
	5424
	100%
	6625

	Total
	
	
	
	20184

	c. TLE grant
	
	
	
	

	New Primary schools@ 20,000/-per school
	31
	31
	100%
	69

	New Upper Primary schools@ 50,000/-per school
	134
	134
	100%
	649

	Total
	
	
	
	718


Source: AWP & B, 2009-10 
Plans for effective utilization of school grant and TLE grant in 2009-10:

It has been planned to use the Teachers grant, school grant and TLE grant for meeting the school specific requirement relating to teaching and learning. The requisite items for the school will be utilized through the concerned VEDCs.

Recommendation/s:

The appraisal team recommends the State proposal for the grants as under:

1. Teachers grant- 76180 teachers (35616 primary + 40564 Upper Primary)

2. School Grant- 19466 schools (13490 PS + 5976 UPS)

3. TLE Grant- 688 new schools ( 69 PS + 599 UPS ) as per SSA norms.

d. Curriculum renewal:

As per the State Plan, the State follows the curriculum developed by Punjab School Education Board. Revision of curriculum is done continuously in phased manner.  The National Curriculum Framework 2005 has been studied by the SCERT, Punjab. The recommendations for certain modifications have been sent to PSEB and to NCERT. The following table gives the over all position of the state in the curriculum related status 

Information about Curriculum/ Syllabus

	Stage
	Curriculum developed by
	Year of renewal
	Whether Published
	Available with Tr. Trainers
	Available with Schools/ Trs.
	Based on 
	Plans for further renewal

	Primary & Upper Primary
	Curriculum has been / is developed by Punjab School Education Board
	Renewal of curriculum of text books is regular phenomena, sum of the orders of text books are modified every year.
	Yes
	Yes
	Yes
	National Curriculum framework, 2005
	Though the modification of the contents of the text books is done on a regular note of state education board but as per the latest information the board has no immediate plan to change any text book for the coming academic session 2009-10.


Textual Materials and Languages in which textbooks are published;

The State has provided following information regarding the progress of free textbook distribution in the State under SSA in 2008-09.Most of the text books are published in regional language that is Punjabi. However in order to meet the requirement of students studying in govt. aided/private schools, a small number of text books is done in Hindi and English languages too.  The state provides text books to only SC children through state budget and to rest of the children the free text book distribution is made out of SSA grants. The work books are included with in the package of the text books. The following tables reflect the details about the text books being used in the State, about the cost of the text books, distribution schedule and other activities.





    Information about Textbooks

	Class
	Textbooks developed by
	Year of Publication 
	Year of renewal
	No. of Books
	Cost of total set of textbooks*
	Plans for renewal

	Class

 I -VIII
	PSEB
	2008-09
	- It is an     ongoing process.

- Regular                       review 
and modification of contents of the text books goes on.
	907385
	20,02,87,745
	Though the modification of the contents of the text books is done on a regular note of state education board but as per the latest information the board has no immediate plan to change any text book for the coming academic session 2009-10.


Source: AWP & B, 09-10                                                     * includes workbooks.

Actual prices of textbooks for classes 1-8 for Punjab: 

The details of the text book and the work books along with the cost involved are given in the table below.

Actual prices of textbooks for classes 1- 8 for Punjab

	Class
	Name of the Textbook
	RATE
	Class wise cost of complete set of books
	Total Cost of complete set of books at primary and upper primary level
	Average Cost of complete set of books at primary and upper primary level

	
	
	
	
	
	

	I
	1    Punjabi Parvesihka
	9.65
	71.11
	491.53
	98.31

	
	2    Punjabi Text Book – 1
	10.87
	
	
	

	
	3    Mathematics - 1 (Punjabi)
	19.07
	
	
	

	
	4    Learn your English – 1
	10.87
	
	
	

	
	5    Workbook-I
	20.65
	
	
	

	II
	1    Punjabi Text Book – 2
	9.99
	64.83
	
	

	
	2    Mathematics - 2 (Punjabi)
	19.07
	
	
	

	
	3    Learn your English – 2
	13.32
	
	
	

	
	4    Workbook – II
	20
	
	
	

	III
	1    Punjabi Text Book – 3
	10.1
	106.05
	
	

	
	2    Mathematics - 3 (Punjabi)
	31.35
	
	
	

	
	3    Environmental Education - 3 (Pbi.) 
	19.43
	
	
	

	
	4    Learn your English – 3
	16
	
	
	

	
	5    Wokbook – III
	29.47
	
	
	

	IV
	1    Punjabi Text Book – 4
	11.75
	114.91
	
	

	
	2    Aao Hindi Sikho – 4
	12.1
	
	
	

	
	3    Environmental Education - 4 (Pbi.) 
	21.53
	
	
	

	
	4    Mathematics - 4 (Punjabi)
	23.7
	
	
	

	
	5    Learn your English – 4
	16
	
	
	

	
	6    Workbook  -  IV
	29.83
	
	
	

	V
	1    Punjabi Text Book – 5
	15.12
	134.63
	
	

	
	2    Aao Hindi Sikho – 5
	16
	
	
	

	
	3    Mathematics - 5 (Punjabi)
	27.69
	
	
	

	
	4    Learn your English – 5
	18.15
	
	
	

	
	5    Environmental Education - 5 (Pbi.)
	25.25
	
	
	

	
	6     Workbook – V
	32.42
	
	
	

	VI
	1    Punjabi Text Book – 6
	12.6
	227.13
	791.08
	263.69

	
	2    Aao Hindi Sikho – 6
	12.6
	
	
	

	
	3    Social Science - 6 (Pbi.)
	32
	
	
	

	
	4    Physical Education - 6 (Pbi.)
	5.6
	
	
	

	
	5    Science - 6 (Pbi.) 
	27.23
	
	
	

	
	6    Mathematics - 6 (Punjabi)
	30
	
	
	

	
	7    Learn your English – 6
	12.6
	
	
	

	
	8    English Grammar – 6
	11.75
	
	
	

	
	9    Geometrical Drawing and Chitrkala - 6 (Pbi.)
	13
	
	
	

	
	10   Workbook –VI
	40
	
	
	

	
	11   Punjabi Viakaran
	27.23
	
	
	

	
	12   Computer Books – VI
	13.75
	
	
	

	VII
	1    Punjabi Text Book – 7
	14.75
	259.71
	
	

	
	2    Aao Hindi Sikho – 7
	15.16
	
	
	

	
	3    Learn your English – 7
	13.3
	
	
	

	
	4    English Grammar – 7
	17.5
	
	
	

	
	5    Mathematics - 7 (Punjabi)
	27
	
	
	

	
	6    Science - 7 (Pbi.) 
	40
	
	
	

	
	7    Social Science - 7 (Pbi.)
	41.5
	
	
	

	
	8    Physical Education - 7 (Pbi.)
	6.2
	
	
	

	
	9    Geometrical Drawing and Chitrkala - 7 (Pbi.)
	12.6
	
	
	

	
	10   Workbook – Vi
	39
	
	
	

	
	11   Punjabi Viakaran – VII
	16
	
	
	

	
	12   Computer Book- VII
	16.70
	
	
	

	VIII
	1    Punjabi Text Book – 8
	16.25
	304.24
	
	

	
	2    Aao Hindi Sikho – 8
	20.98
	
	
	

	
	3    Learn your English – 8
	14.27
	
	
	

	
	4    English Grammar – 8
	20.96
	
	
	

	
	5    Mathematics - 8 (Punjabi)
	27.9
	
	
	

	
	6    Science - 8 (Pbi.) 
	27.71
	
	
	

	
	7    Social Science - 8 (Pbi.)
	40.5
	
	
	

	
	9    Physical Education - 8 (Pbi.)
	9.6
	
	
	

	
	10   Geometrical Drawing and Chitrkala - 8 (Pbi.)
	16.9
	
	
	

	
	11   Science - 8 (Pbi.) Supplementary Part 2 Environment
	22.92
	
	
	

	
	12   Workbook – VIII
	51.5
	
	
	

	
	13   Punjabi viakaran –8
	16
	
	
	

	
	14   Computer Book-VIII
	18.75
	
	
	

	Total
	1282.61
	1282.61
	362


Source: AWP & B, SSA, Punjab 2009– 10

As informed by the State the distribution of the text books was completed till May in 2008-09, but now in 2009-10 the state is fully geared to complete the distribution process with in April it self, well in the beginning of the session .

Timeliness of Distribution of Free Textbooks:

	Stage
	Academic session begins from
	Date of distribution 

in 2008-09
	Proposed date for distribution in 2009-10

	PS
	1st April  
	April, May
	1st April  2009

	UPS
	1st April  
	
	


Source: AWP & B, 09-10

The following table reflects the over all status of the progress in 2008-09 and also the proposal made for 2009-10

Target, Achievement & Proposal

	
	Target for 2008-09
	Achievement during 2008-09
	Proposal for 2009-10

	
	Physical
	Financial
	Physical
	Financial
	Physical
	Financial

	PS
	1330531
	890.529
	1330531
	890.529
	1360650
	1223.404

	UPS
	749777
	1112.250
	749777
	1112.250
	822205
	1232.655

	Total
	
	
	
	
	2182855
	


Source: AWP & B, 09-10
Proposal: The State has proposed for grant of FTB to 2182855 non SC children from class I to class VIII covering 1360650 children at primary level and 822205 children at upper primary level.

Comments:

· It has come to the notice of appraisal team that the state has proposed to seek FTB support including the work books in the package of text books, which is permissible under norms.

· It has further been noticed that the State provides text books to SC children out of the state budget, but work books are not provided. This implies that work books are not included in the text book package, which is contradictory to the norms.

· This need to be stressed that work books must be provided to SC children as well as a State commitment. 

Recommendation: 

Out of the state proposal, the appraisal team assessed the exact number of the children in Govt. sector schools and recommended for 954123 children the FTB support including the work books in the package as under:

1.  Primary schools:   coverage for 543349 children @ 110/- per child.

2.  Upper primary schools: coverage for 410774 children @ 250/- per child.

PAB may like to approve.

e. Use of Teaching Learning Materials:
In addition to the text books work books are being used by 100% govt. primary and upper primary schools. Supplementary and graded material was also used by all the primary schools during 2008-09. 

State has emphasized on the preparation of contextual TLM, it’s appropriate use in the class rooms and accordingly the teacher preparation during teachers training have been designed for 2009-10.

During the entire teacher-training programme during the current academic session the school teachers were advised to lay special focus on preparation/purchase of subject specific teaching aids out of the TLM grant. They were exhorted to ensure the judicious use of all such aids in the classroom. They have been sufficiently sensitized by repeated appeals that the teaching methodology and the use of adequate teaching aids has a direct bearing on the learning levels of children. All the VEDCs have been informed of the various items required for practical teaching of subjects like Maths and Science. It will be insured that teachers make it a point to purchase all such requisite materials/aids out of the TLM grant.

f. f. Active pedagogy: 

The State has informed that no study was earlier conducted or teacher’s instructional time, student learning opportunity time or the active student participation existing in the schools; but for 2009-10 the state has planned and initiated the process to have assessment on these parameters. All the DIETs/GISTCs have been involved to physically visit the schools and monitor the classroom process to take note of the actual time used by the teacher for instruction, the time for which students remains engaged in independent learning and the time for which interaction between the teacher and students as well as the student’s participation in the class takes place. The visiting officers/teams will also observe the teaching methodology adopted by the class teacher. They will impart model teaching to correct the erring teachers. The findings of the study will pave a way to make the requisite shifts in teacher’s instruction time, students learning opportunity time and active student participation time etc. 

The State appears to be confident that the activities planned like,
Teacher’s training, preparation of effective teaching learning aids, preparation of supplementary reading materials for children, demonstrative and interactive methods of teaching, experimentation and activity based teaching are likely to impact the over all shift in the class room processes from teacher centric to child centric ones.The pace and extent of learning as well as achievement levels of children will get enhanced sufficiently. They will be able to develop the sense of logical reasoning and will get enabled to explore the world.

g. Learning Enhancement Programme : 

Progress of Learning Enhancement Programme (LEP) for 2008-09: 

With a view to improve the achievement of children in primary & upper primary schools in the State, following initiatives were taken up by the State under LEP during 2008-09.

· Execution of Parrho Punjab Programme to promote reading & numerical skills of primary children by 15% by the end of 2008-09. 

· Promotion of Maths and Science Education at upper primary level through Competitive Tests, Continuous Comprehensive Evaluations, Strengthening of Science & Maths labs and rigorous training of Science & Maths teachers etc. 

· Implementation of Pilot Project on English “Angrezi A – Z”. 

· Establishment of Reading Corners in the schools. 

· Special drives for community awareness in mobilization. 

Parrho Punjab Programme 2008-09: The state conducted this massive  drive in 2008-09 and achieved a phenomenal success in achieving the targets planned for the academic year. An overview of the same is as under;  
· All the primary teachers were trained on special teaching methods to achieve the goal of 15% learning enhancement in reading, writing & arithmetic for primary children. 

· The teachers were thoroughly trained to undertake baselines and identify the learning levels of children. 

· Baseline for primary children as done by the school teachers in the beginning of academic session 2008-09 revealed that 23.3 children in standard-I could only read letters, 25% children in standard-III could read paras and 46% children of standard-V could read stories. 

So far as numerical skills were concerned, 14.6% children of standard-I could recognize numbers, 18% children of standard-III could perform subtraction and 29% children could perform division.

· Supplementary reading material was developed with the help of primary school teachers for LEP. This included colorful reading cards, letter and number charts, posters, school registers, problem books and teaching manual for teachers. 

· The primary school children were divided into 5 different groups on the basis of their performance levels in reading of languages and numeric. 

· Specialized intensive teaching was imparted to the focus groups by the trained school teachers.

· Mid term evaluation of the programme was done by the block master trainers during November, 2008 which showed a significant improvement in the learning levels of the children. For example:   Number of letter readers of class-I had increased by 19.5 PP, number of para readers of class-III had increased by 8% and that of story readers of class-V had increased by 13%. 

As regards the mathematical skills, the children of standard-I who could recognize numbers had increased by 5%, number of students of standard-III who could perform subtraction had increased by 8% and the number of students of standard-V who could perform division had increased by 12%.

· Final Evaluation of the Programme has been planned for first week of March and it is expected that there will be further improvement in learning amongst primary children.

ii. Modalities and Strategies under Parrho Punjab Programme: 

· All teachers (over 98%) were trained in special teaching methods to take up learning issues at the school level. 

· Teachers are given simple learning goals in reading, writing and arithmetic. 

· Goals were thrashed out in these meetings and teachers took up the LEP agenda as per the goals.

· At the end of the trainings teachers went to the schools to do a quick evaluation of their schools/classes. 

· This helps teacher to know where the school stands with respect to the goals and helps them identify which children need focus.

· Teachers were supplied with supplementary reading material aligned to the training.

· Monitoring and support of teachers with fortnightly visits to help teacher achieve goals.

iii. Specialized Academic Leaders at District and Block levels

· SSA Punjab has appointed Parrho Punjab District Coordinators from the teachers’ cadre in each district. To support them, Assistant District Coordinators have also been appointed.

· In each block, 3 to 5 Block Master Trainers have been chosen. These BMTs are enthusiastic primary school teachers with a good knack for training. 

Teacher training 
· All teachers of Punjab were trained for ten days during 2008-2009 on special teaching methods to achieve goals of the LEP. 
· First training of 3 days in July 2008 (completed in three weeks all over Punjab); second training of 4 days in December 2008 (completed in four weeks all over Punjab) and third training of 3 days in Jan-Feb 2009 (completed in 3 weeks all over Punjab).
· Two-tier model of training adopted to minimize transmission loss. First a State-level training teams train 850 Block Master Trainers at the district level. Thereafter these BMTs train all teachers (over 42000 teachers) at the Block Level.
· Content of training: Each training is planned well in advance to ensure good quality and relevant content is provided to the teacher. 

Supplementary Reading Material

· Special material was developed for the LEP. All trainings were based on this material. This includes Reading Cards (of various difficulty levels), Letter and Number charts, Posters, School register, Math word-problems book, Games manual for Teachers, Teaching manual for teachers.

· Material developed through help of primary school teachers. All SRM for children is colourful and printed on good quality paper.

Evaluation

· Evaluation played a strong role in the LEP. All children were periodically assessed for their ability in reading, writing and arithmetic. 

· For baseline (July-Aug 2008), teachers conducted evaluation themselves. For mid-test (Nov 2008), this was conducted by Block Master Trainers in all schools. Similar plan for end-test (March 2009).

· Data from each school is entered centrally at Chandigarh. School, Block, District and State Report Cards distributed at all relevant levels. This helps educational administrators in identifying where the problems are and develop local solutions.

· External evaluation was also organized using a 50-school sample per district (statistically relevant sample size). 

Monitoring and Support

· Constant school visits to monitor the program and support teachers. 

· Combining visits by various personnel, each school gets visited on average once a fortnight regarding LEP progress.

· Visitors also assess children’s ability in reading, writing and arithmetic.

· Four consultants at division level have been appointed to monitor the progress of 'Parrho Punjab' project.

iv. Learning Outcomes: 

· As per the expected outcomes, the learning in primary children should enhance by at least 15%in languages and mathematics by the end of the academic session 2008-09. 

· Going by the 4 months time impact of PPP i.e. by the findings of the Mid term evaluation done in October, 2008, number of letter readers of class-I had increased by 19.5 PP, number of para readers of class-III had increased by 8% and that of story readers of class-V had increased by 13% in 4 months time.  

· As regards the mathematical skills, the children of standard-I who could recognize numbers had increased by 5%, number of students of standard-III who could perform subtraction had increased by 8% and the number of students of standard-V who could perform division had increased by 12%.

· Graphic representation of the learning outcomes for Parrho Punjab Programme 2008-09 is as follows :

Project Angrezi A – Z 2008-09: 

[image: image1.emf]Punjab - READING

0

10

20

30

40

50

60

70

std1(ability to

read letters)

std2(ability to

read words)

std3(ability to

read Para)

std4(ability to

read Story)

std5(ability to

read Story)

Series1

Series2


To improve the teaching and learning of English at primary level a pilot project has been done for two districts namely Mansa & Kapurthala. Teacher Training, supplementary material for English and focused teaching have been the key points of the programme. The results are quite positive. 

[image: image2.emf]Punjab - MATH

0

5

10

15

20

25

30

35

40

45

std1(ability to

recognize no.)

std2(ability to

do addition)

std3(ability to

do subtraction)

std4(ability to

do division)

std5(ability to

do division)

Series1

Series2

Reading corners in schools 2008-09: 

Good library books & magazines as purchased from NBT, Punjab text book board and the State Education Board have been supplied to all the primary schools so that children get an opportunity for interesting reading and their comprehensions as well as general awareness is enhanced. 

Another publication titled as Aale Bhole – a monthly magazine for primary school children which is being published under SSA, is also being supplied to all primary schools. 

v. Learning Enhancement Program (Parrho Punjab) Objectives in academic year 2009-10:

After fair success of Parrho Punjab in 2008-09 it was decided by the State to continue the program with a renewed vigor. It has been decided to 

· Focus on children's basic competencies in 3R's i.e. reading, writing and arithmetic

· And add a component of basic English to the ongoing program.

Specific goals in this regard have been set for the year 2009-10 is reflected as per the following tables:

LANGUAGE Goals (Read & Write)
	Class 
	Letters
	Words
	Sentences
	Textbook

	Std I
	50%
	50%
	0%
	

	Std II
	0%
	50%
	50%
	

	Std III
	0%
	0%
	50%
	50%

	Std IV-V
	0%
	0%
	0%
	100%


ARITHMETIC Goals
	 
	Number Recognition
	Addition 
	Subtraction
	Multiplication Tables
	Division

	Std I
	1-100 (100%)
	One digit (50%)
	One digit (50%)
	
	

	Std II
	Up to 1000
(100%)
	Two digit with carry-forward (in writing)
	Two digit with borrow (in writing)
	Up to 5
	

	Std III
	Up to 1000
(100%)
	Three digit with carry-forward (in writing)
	Three digit with borrow (in writing)
	Up to 10
	Two digit no. with single digit

	Std IV-V
	Up to 1000
(100%)
	Three digit with carry-forward (in writing)
	Three digit with borrow (in writing)
	Up to 20
	Three digit no. with single digit


vi. Parrho Punjab 2009-10 – ENGLISH in primary classes :(English as key-component)
It is also proposed that English will be introduced as a key-component state-wide in Parrho Punjab programme in the coming academic year.

At least two teachers will be trained per school to teach English and more teachers will be trained in case of larger schools. Children in Std I-V are taught English using the phonetic model of teaching. Std I children are just given basic introduction to the alphabets and chanting of short sentences.

	Program Outline

	Where?
	All Primary schools in the state

	Who teaches?
	Government school teachers of the state

	Who are taught?
	Children from Std I-V

	Teachers Trained
	During April/May

	Program schedule
	April 2009 – March 2010


Goals of English:

	Class
	Reading & writing Letters
	Reading & writing Words
	Reading and writing Sentences
	Conversation

	I
	Introduction
	
	
	Limited Chanting

	II
	50%
	50%
	
	Limited Chanting

	III
	
	50%
	50% (along with Std III textbook reading)
	Limited Chanting & Question Answers

	IV
	-
	-
	100% (along with Std IV textbook reading)
	Question Answers

	V
	-
	-
	100% (along with Std V textbook reading)
	Question Answers


Strategy:
· Teacher Training:
To achieve the objectives of the program all the primary teachers of the state will be provided training during the month of April and May in the next academic year.

· Supplementary reading material:

Supplementary reading material will also be provided to all the children in all the primary schools.

vii. Objectives of LEP in 2009-10:

Reading is the first and most essential step towards education. Without the ability to read, a child cannot learn and move ahead in the school or in any educational program. Supplementary reading materials and Books are an important input for the child to first practice reading and subsequently acquire proficiency. 

The more children read, the more they want to read. The more they read the more books they need. When children read they do many things: 

· begin to talk about what they have read

· discuss what is interesting

· point out what is unusual

· and begin to link what they have read to what they know.

As they read and as they listen, they begin to make sense not only of what is in the book and what is around them but they begin to explore a wide world beyond their immediate surroundings. Thus, books are an essential ingredient for not only building basic foundations for learning but also for life.

As per the competencies based on textbooks, children are expected to learn to read simple text by the end of their first year in school. Textbooks in the early grades require children to read fluently by the end of Class II. However, available evidence shows that al large proportion of children in the early grades, are still struggling with recognizing letters or decoding words.

Further, a majority of children, especially in rural Punjab come from families where parents are not educated. Most rural homes do not have any reading material apart from textbooks. If children do not learn to negotiate text in the early stages it is becomes hard for them to read textbooks, comprehend and construct meanings.

The biggest challenge in the state of Punjab is to help children read. The approach will be two pronged.

· To get children to begin to achieve basic reading skills

· To reaffirm the skills of new readers through use of non-textbook based reading material.

The Learning Enhancement Programme (LEP) will focus on developing reading at early stages i.e. in class I and II, with priority to enhance learning levels in higher language, science and mathematics.

Planning for Learning Excellence Program (Parrho Punjab) in 2009-2010:
Based on the success of the LEP in 2008-2009, in improving learning outcomes and classroom processes, the program should be continued for the coming year as well. While the programme will retain all the essential features of the previous year, the coming year will have some additional key features as listed below:

Key Features to be added in 2009-2010

· English will be introduced state-wide in the coming academic year.

· Reading hour with Library programme 

· Stress will be given to reading as well as writing of Punjabi. 

· Basic Math skills will be further honed through a fresh infusion of specialist Math content. 

· Supplementary Reading Material will be aligned closer to the textbook.

· For Std I-II Parho Punjab will become a full-day multi-grade pedagogic process and integration of school textbooks. All learning goals of theses classes will be as per the LEP

· Low-achievers in Std III-IV-V will be identified to develop their skills.

· Reading and Math weeks to be organized to work in a focussed way to remedy these two subjects.

viii. The proposal for learning enhancement programme for primary level for 2009-10:-

	Parrho Punjab Programme for Reading & Mathematical Enhancement at Primary Level 

	Activity
	Unit cost
	Physical
	Financial
	Head

	I to III, Supplementary Material for Children (Graded reading/Graded writing/Story books/reading cards)
	Rs. 40 per child
	757989
	303.19
	LEP

	IV to V, Books for EVS and Maths (graded writing)
	Rs. 40 per child
	479138
	191.65
	LEP

	I to V, Additional Books for Reading Hour (Story books/encyclopedia)
	Rs. 1000 per school
	13400 school
	134.00
	LEP

	Training of teachers on LEP strategies
	Rs. 100 per teacher per day
	
	
	Teacher Training 

	Special attention to children with low performance at primary level
	Rs. 2500/- per school 
	13400 school
	335.00
	Remedial Coaching

	Special Summer Reading Program
	Rs. 250 per school
	13400 school
	33.50
	Remedial Coaching

	Data Management & Website
	Rs. 50 per school
	13400 school
	6.70
	Management Cost

	SCIENCE & MATH ENHANCEMENT AT PRIMARY LEVEL

	Provision of Sc. Kit
	Rs.1000/- per school
	13400 schools
	134.00
	School Grant

	Strengthening of Primary Maths Kit.
	Rs.1000/- per school
	13400 schools
	134.00
	LEP

	Continuous and comprehensive evaluation  of achievement levels of class-V children (baseline, monthly, quarterly test and competitive exam) 
	Rs.25/- per- child
	231000 children 
	57.75
	REMS

	Monitoring & Supervision by BRPs, DRPs and District Science Supervisors.
	Rs. 50,000/- per district
	20 districts


	10.00


	REMS


ix. Learning Enhancement Programme (Up. Pry.): 

State has informed that in “Learning Enhancement Programme for Science & Maths” at primary and upper primary level for 2008-09, following activities were taken up : 

1. Establishment of Science & Maths cell at State level to constantly plan & execute and monitor the tasks related to LEP. 

2. Appointment of District Science Supervisors to constantly monitor the teaching -learning in the subjects of Science & Maths. 

3. Development of content matter for training of teacher in Science & Maths. 

4. Intensive training of Science & Maths teachers on innovative teaching methods. 

5. Instituting the system of continuous comprehensive evaluation :  


Monthly test are being taken for children of classes V, VI, VII & VIII in the subjects of Maths & Science to constantly monitor their performance and have assessment of the grey areas. 

6. District & State level competitions:  Competitive tests in the subjects of Maths & Science were conducted for students of class V & VIII at district levels to identify the first three topers in the subjects. These toppers were made to compete at the State level. All the toppers are being honored with suitable cash awards.  

7. Passing the subjects of Science & Maths has been made compulsory for clearance of class-VIII examination. 

8. Establishment of Maths & Science labs in schools :  


Maths labs at primary level and Science & Maths labs at upper primary level are being adequately equipped to enable the students learn by demonstration as well as practical methods. 

x. Proposal for Learning enhancement programme for Upper Prinary 2009-10

Objective: Promotion of Science, Maths & Social Science education:  

Goal: To bring out 10% increase in the achievement levels of children at upper primary level by the end of 2009-10. The inputs planned are as given below:

· Identification of hard spots after the March assessment analysis.

· Preparation of supplementary material. 

· Training of teachers for hard spots. 

· Use of appropriate TLM and supplementary material in the class rooms. 

· Monthly tests of Science, Maths & Social Studies. 

· Structure, Monitoring and tracking of performance. 

· Competitions and test at primary and upper primary level for Science, Maths & Social Science. 

· Involvement of children in celebration of historical days connected with Science, Maths & Social Science. 

· Strengthening of Science & Maths labs. 

· Strengthening the reading corners in schools. 

· Continuation of activities under Parrho Punjab Programme & Angrezi A – Z Project. 
xi. Budget Proposal for Learning Enhancement Programme for Upper Pry Level 2009-10: 

(Figures in lakh)

	SCIENCE & MATHS & SOCIAL SCIENCE ENHANCEMENT AT UPPER PRIMARY LEVEL

	Strengthening of Science labs. 
	Rs. 2000/-

Per School
	5569
	111.38
	out of school grant

	Strengthening of Maths Lab.
	Rs.2000/-

Per School
	5569
	111.38
	out of school grant

	Training of teachers for effective teaching of Science, Maths & Social Science and LEP Strategies
	Rs. 100/- per teacher per day
	
	
	Teacher Training

	Special attention to children with low performance in Science, Maths & Social Science. 
	Rs. 4000/- per school
	5569
	222.76
	Remedial Coaching

	Continuous and comprehensive evaluation  of achievement levels of primary children (baseline, monthly, quarterly test and competitive exam)
	Rs. 25/- Per Child

 
	742301
	185.57
	REMS

	Monitoring & Supervision by BRPs, DRPs and District Science Supervisors. 
	Rs. 50,000/- per district


	20 districts
	10.00


	REMS


Salient features of the Learning Enhancement Programme at primary level

	Goals related to quality improvement in 2009-10
	Major activities under LEP
	Type of materials required
	Expected Learning outcomes
	Coverage (No. of districts, schools & children)
	Unit Cost

	Atleast 15% improvement in reading writing and numerical skills among primary classes.
	Reading, writing and numerical skills promotion campaign for primary classes
	Supplementary Material for Children
	Reading, writing and numerical skills of the primary children will get enhance by at least 15%
	12,37,127 children
	Rs. 50 per child

	
	
	Additional story Books for Reading Hour
	
	13400 school
	Rs. 2000 per school

	Imparting effective teaching to the class
	Training of teachers on LEP strategies
	Modules for teachers training
	The teachers will be ready to take on the task of learning promotion and to use the supplementary material for children
	All primary teachers
	Teacher training

	Eliminating the gap between low and average performers
	Special attention to children with low performance at primary level
	Additional manpower to work as education volunteers
	The low performance will be brought at par with average and better performance
	13400 school
	Project management

	Overcoming the initial hesitations of low performers
	Special Summer Reading Program
	Additional manpower to work as education volunteers
	The low performance will be brought at par with average and better performance
	13400 school
	Rs. 250 per school  -Remedial teaching

	Keeping a track of performance
	Data Management & Website
	Data capture formats, Monitoring registers, website hosting, internet charges etc
	The performance of the children will be assessed.
	13400 school
	Rs. 50 per school

MIS

	Atleast 10% improvement in the achievement in the students in science math and social sciences at upper primary
	Setting up of Science Lab
	Materials for science labs.
	Promotion of science education.
	13400 schools
	Rs.1000/- per school

	
	Strengthening of Primary Maths Lab.
	Materials for maths labs.
	Promotion of maths education
	13400 schools
	Rs.1000/- per school

	
	Continuous and comprehensive evaluation  of achievement levels of class-V children (baseline, monthly, quarterly test and competitive exam) 
	Printing of question papers, answer sheets, software for monitoring learning achievements of children
	Learning achievements of the primary children will be assessed.
	231000 children 
	Rs.25/- per- child

	
	Monitoring & Supervision by BRPs, DRPs and District Science Supervisors.
	Logistic arrangements
	The performance of teachers as well as students will get pushed up.
	20 districts


	Rs. 50,000/- per district

	
	Strengthening of Science labs. 
	Materials for science labs.
	Promotion of science education.
	5569
	Rs. 2000/-

Per School(.school grant)

	
	Strengthening of Maths Lab.
	Materials for maths labs.
	Promotion of maths education
	5569
	Rs.2000/-

Per School

	
	Training of teachers for effective teaching of Science, Maths & Social Science and LEP Strategies
	Modules for teachers training
	The teachers will be ready to take on the task of learning promotion and to use the supplementary material for children
	All subject teachers at upper primary level
	Rs. 100/- per teacher.  teacher training                 

	
	Special attention to children with low performance in Science, Maths & Social Science. 
	Extra manpower to take on the remedial sessions
	The weak children will come at par with average and high performance
	5569
	Rs. 4000/- per school

	
	Continuous and comprehensive evaluation  of achievement levels of primary children (baseline, monthly, quarterly test and competitive exam)
	Printing of question papers, answer sheets, software for monitoring learning achievements of children
	Learning achievements of the primary children will be assessed.
	742301
	Rs. 25/- Per Child

 

	
	Monitoring & Supervision by BRPs, DRPs and District Science Supervisors. 
	Logistic arrangements
	The performance of teachers as well as students will get pushed up.
	20 districts
	Rs. 50,000/- per district




The district wise cost worked out by the State is as under:

Information Learning Enhancement Programme

	Information about Learning Enhancement programme

	

	SNo.
	District
	Cost for Learning Enhancement programme
	% Cost to total outlay of District for LEP

	1
	Amritsar
	113.9
	2.00

	2
	Barnala
	26
	1.93

	3
	Bathinda
	60
	2.00

	4
	Faridkot
	26.00
	1.97

	5
	Fathegarh
	53
	2.00

	6
	Ferozepur
	130
	2.00

	7
	Gurdaspur
	203
	2.00

	8
	Hoshiarpur
	106
	1.99

	9
	Jalandhar
	58.8
	2.00

	10
	Kapurthala
	59
	1.99

	11
	Ludhiana
	59.5
	2.00

	12
	Mansa
	44
	1.99

	13
	Moga
	49.8
	2.00

	14
	Mohali
	40
	1.98

	15
	Muktsar
	56
	1.99

	16
	Nawanshahr
	39.8
	1.99

	17
	Patiala
	80
	2.00

	18
	Ropar
	65.85
	1.99

	19
	Sangrur
	60.85
	2.00

	20
	Tarn Taran
	46.85
	1.98

	 
	State
	1378.35
	2.00


Comments:

· The appraisal team examined the State proposal for LEP during 2009-10 and appreciates the efforts made to integrate the support available under various Quality interventions.

· At primary and upper primary level, out of the various activities proposed, only the following activities are supported under LEP.
	Parrho Punjab Programme for Reading & Mathematical Enhancement at Primary Level 

	Activity
	Unit cost
	Physical
	Financial
	Head

	I to III, Supplementary Material for Children (Graded reading/Graded writing/Story books/reading cards)
	Rs. 40 per child
	757989
	303.19
	LEP

	IV to V, Books for EVS and Maths (graded/ activity writing sheets)
	Rs. 40 per child
	479138
	191.65
	LEP

	I to V, Additional Books for Reading Hour (Story books/encyclopedia)
	Rs. 1000 per school
	13400 school
	134.00
	LEP

	SCIENCE & MATH ENHANCEMENT AT PRIMARY LEVEL

	Strengthening of Primary Maths Kit.
	Rs.1000/- per school
	13400 schools
	134.00
	LEP

	Total
	
	
	762.84
	


Recommendations:

The appraisal team recommends only the activities mentioned in the table above under LEP amounting Rs. 762.35 Lacs out of the proposed 1378.35 lac. Cost. the recommended amount is well with in 2% of the management cost as per norms.

PAB may like to approve.

h. Strengthening learning assessment: 

Following table throws light on the students’ learning assessment system in the State. 

Learning assessment system

	Stage
	No. of tests in a year
	Whether marking or grading system
	No-detention from which class
	Board exam. at which class
	Is there any report card?
	Frequency of sharing with parents

	Primary
	Three quarterly tests plus final exam
	Marking system
	No Detention policy upto class IV
	State level Examination by the Department for class V
	Yes
	Quarterly

	U. Pry.
	Monthly Tests for Science, Maths, Social Science and English plus three quarterly tests plus final exam
	Marking system
	-
	State Board Exam for class VIII, X and XII
	Yes
	Quarterly


Source: AWP & B, 09-10
Status of shift towards Comprehensive and Continuous Evaluation: The monthly System of test for science maths, social science and English for classes V, VI, VII and VIII has been started. Every Monday there is a test for one of the subjects. The course taught till that period is tested. The performance is compiled and analysed to identify the grey areas. The remediation is done by way of repeat and more focused teaching.

Apart from it, district and state level competitive tests in science and maths for class V and VIII have been started and system of awarding the best performers of classes V and VIII has been initiated. 

Plans for strengthening learning assessment in 2009-10: The mechanism of comprehensive and continuous evaluation will be streamlined and strengthened. NCERT’s sourcebooks on learning assessment will be referred to. In addition to that competitive tests and system of awarding the best performers of class V and VIII will be continued.

I. Remedial teaching
Progress for remedial teaching for 2008-09:
In order to improve the reading & numeric skills of primary class children, special coaching programme was started for them under Parrho Punjab Project which is being run with the help and involvement of a non-govt. organization. Remedial Coaching in upper primary schools was imparted to the weak children of classes 6th, 7th & 8th in the subjects of Science, Maths & English. The coaching was imparted for four months from August, 2008 to December, 2008. The target group included students with scores < 55% in the previous annual examinations. The coaching was imparted daily for 2 hours after the school timings. The subject specific educational volunteers were appointed by VEDCs @ Rs. 1800/- per month for the purpose of special coaching. 

The minimum qualification for volunteers was graduation in the requisite subjects. There was a total budget provision of Rs. 516.91 lacs for Remedial Coaching for2008-09. The state has made a good progress in the utilization of remedial support during 2008-09 in all the districts, as per the table given below:

	SNo.
	District
	Budget 

Approved
	No of schools covered for 5% Rural & 10% urban
	Expenditure

 (in Lacs)

	
	
	
	Rural
	Urban
	

	1
	Amritsar
	33.400
	841
	331
	33.400

	2
	Barnala
	8.100
	181
	114
	8.100

	3
	Bathinda
	17.53
	388
	248
	17.53

	4
	Faridkot
	11.095
	249
	154
	11.095

	5
	F.G.Sahib
	16.300
	458
	142
	16.300

	6
	Ferozpur
	40.420
	1103
	367
	40.420

	7
	Gurdaspur
	55.890
	1559
	484
	55.890

	8
	Hoshiarpur
	47.00
	1284
	415
	47.00

	9
	Jalandhar
	39.960
	985
	431
	39.960

	10
	Kapurthala
	21.060
	541
	221
	21.060

	11
	Ludhiana
	42.525
	1013
	515
	42.525

	12
	Mansa
	12.610
	288
	175
	12.610

	13
	Moga
	16.765
	381
	229
	16.765

	14
	Mohali
	14.960
	411
	136
	14.960

	15
	Mukatsar
	14.660
	337
	201
	14.660

	16
	SBS Nagar
	17.550
	444
	190
	17.550

	17
	Patiala
	37.015
	1022
	322
	37.015

	18
	Ropar
	20.680
	582
	168
	20.680

	19
	Sangrur
	28.080
	672
	349
	28.080

	20
	Taran Taran
	21.330
	546
	232
	21.330

	
	Total
	516.99
	13285
	5424
	516.99


The following table shows the consolidated progress of remedial teaching for the state for 2008-09.

Progress of Remedial Teaching:
	Fund allocated in 2008-09
	Physical Target (Children)
	Financial achievement till Feb, 2009
	Financial achievement till Feb, 2009
	% of achievement

	
	
	
	
	Physical
	Financial

	516.990
	103398
	100%
	100%
	100%
	100%


Source: AWP & B, SSA, 2009-10
Plan for Remedial Teaching in 2009-10:

In order to improve the learning levels of students, it is proposed to impart Remedial Coaching to 5% primary and 10% upper primary school children. The coaching will be imparted by school teachers/volunteers/NGOs. The children with less than 50% scores and the ones located in rural and isolated areas would be covered under Remedial Coaching. The proposal for remedial support for mainstream children and that for low female literacy districts is being formulated. The plan so far proposed for 2009-10 is as follows:-

	SNo.
	District
	5% Rural Students
	10% Urban Students
	Total Students
	Unit Cost
	Total Budget

( in Lacs)

	
	
	
	
	5% Rural & 10 % urban(Classes 1-8)
	
	

	1
	Amritsar
	5798
	3369
	9167
	Rs.500/-
	Rs.45.83500

	2
	Barnala
	1937
	956
	2893
	Rs.500/-
	Rs.14.46500

	3
	Bathinda
	4332
	1451
	5783
	Rs.500/-
	Rs.28.91500

	4
	Farigkot
	2172
	992
	3164
	Rs.500/-
	Rs.15.82500

	5
	Ferozpur
	7656
	1224
	8880
	Rs.500/-
	Rs.44.40000

	6
	F.G.Sahib
	2007
	712
	2719
	Rs.500/-
	Rs.13.59500

	7
	Gurdaspur
	7447
	947
	8394
	Rs.500/-
	Rs.41.97000

	8
	Hoshiarpur
	6056
	925
	6981
	Rs.500/-
	Rs.34.90500

	9
	Jalandhar
	5389
	2874
	8263
	Rs.500/-
	Rs.41.31500

	10
	Kapurthala
	3000
	622
	3622
	Rs.500/-
	Rs.18.11000

	11
	Ludhiana
	7200
	3662
	10862
	Rs.500/-
	Rs.54.31000

	12
	Mansa
	3300
	639
	3939
	Rs.500/-
	Rs.19.69500

	13
	Moga
	4189
	625
	4814
	Rs.500/-
	Rs.24.07000

	14
	Mohali
	2224
	598
	2822
	Rs.500/-
	Rs.14.11000

	15
	Mukatsar
	3370
	938
	4308
	Rs.500/-
	Rs.21.54000

	16
	SBS Nagar
	2457
	340
	2797
	Rs.500/-
	Rs.13.98500

	17
	Patiala
	5654
	2119
	7773
	Rs.500/-
	Rs.38.86500

	18
	Ropar
	2834
	360
	3194
	Rs.500/-
	Rs.15.97000

	19
	Sangrur
	5403
	1551
	6954
	Rs.500/-
	Rs.34.77000

	20
	Taran Taran
	4260
	430
	4690
	Rs.500/-
	Rs.23.45000

	
	Total
	86685
	25334
	112019
	Rs.500/-
	Rs.560.09500


Proposal: State has proposed Rs. 560.09 Lacs for remedial support.

Comments: Based on the proposal the appraisal team observed that:

· There are five districts namely, Barnala, Ferozpur, Mansa, Muktsar and Sangrur, where the female literacy has been below the National average. 

· Taking in to account the SSA norms of 5% rural and 10% urban eligibility consideration for remedial teaching 26974 children are entitled.

· In addition to the above category, there are 42878 mainstreamed children, mainly girls, SC and special focus group children, who essentially need constant remedial support to retain them in the schools.

· This is to suggest that the remedial programme must be focused and involvement of experienced and dedicated teachers will be essential.

· State must ensure that the programme is intensively run for a period of six months in two phases. The intervening phase has to be utilized towards the mid term assessment and according to the feed back received the strategies may be modulated.

· The mainstreamed and high aged children need more focus to keep track of their attendance and achievement through the intervention.

Recommendation: The appraisal team recommends remedial support for 69852 children under SSA norms with a unit cost of Rs. 500/- per child.

j. Teacher preparation: 

To know about progress of teacher training in the State it is important to know the overall readiness of the different Teacher Education Institutions (TEIs) in the State. The following table indicates the break up of existing TEIs in the State other than the BRCs and CRCs. 

Govt. Teacher Education Institutions. The tables given below gives an over view of the teacher training institutes available along with their intake capacity.

	SNo.
	Institution
	Number
	Course offered

	1.
	DIET
	17
	ETT

	2.
	DRC
	
	

	3. 
	BTC
	
	

	4.
	Pre Primary Teacher Training Centre
	
	

	5.
	In Service Training Centers
	12
	Training of upper primary teachers.


Source: AWP & B, 09-10

Annual Intake Capacity of Teacher Education Institutions
	SNo.
	Courses offered
	Type of Institution
	Total Institutions
	Annual Intake Capacity

	1.
	D. Ed.
	
	
	

	2 (a)
	B. Ed.
	
	
	

	   (b)
	B. Ed.
	
	
	

	3.
	M. Ed.
	
	
	

	4.
	E.T.T
	DIETs plus 

Private Teacher Education Institutions (Pvt. TEIs)
	17-DIETs

24-Private TEIs
	1250 plus 

1200

	Total Annual Intake Capacity
	2450


Source: AWP & B, 09-10

ii.  In-service training:
Nature and focus areas of Training Modules (for Trainers and Teachers) developed in 2008-09: Modules for the training of teachers for the subjects of Science, Maths, Hindi, English, Punjabi and Social Science were prepared during 2008-09. The following table provides information about the progress of teacher training during 2008-09.
Progress of In-service Teacher Training (during 2008-09) till 31st Jan, 2009

	Type of training
	Duration of training


	Months in which undertaken (during vacations or working days)
	Total number of  In-service teachers
	Target- No. of teachers

(during 08-09)
	Teachers trained

(Up to Jan end, 2008 in trainee days)
	Percentage of Achievement

	Primary
	10 days &

06 Monthly Meetings
	working days
	34246
	34246
	518328 days
	75.67

	Upper Primary
	05 days &

06 Monthly Meetings
	working days
	39993
	39993
	418519 days
	52.32

	Total
	
	
	74239
	74239
	936847
	63.09


Source: AWP & B, 09-10

The details of the training programmes informed by the State are narrated below.

Training of primary teachers:

· All teachers of Punjab were trained for ten days during 2008-2009 on special teaching methods to achieve goals of the LEP. 
· First training of 3 days in July 2008 (completed in three weeks all over Punjab); second training of 4 days in December 2008 (completed in four weeks all over Punjab) and third training of 3 days in Jan-Feb 2009 (completed in 3 weeks all over Punjab).
· Two-tier model of training adopted to minimize transmission loss. First a State-level training teams train 850 Block Master Trainers at the district level. Thereafter these BMTs train all teachers at the Block Level.
· Content of training: Each training is planned well in advance to ensure good quality and relevant content is provided to the teacher. 

Training of Upper Primary Teachers:

· Contents: - The Contents of each subject (used during the training for the year 2008-09) were designed while keeping in view the difficulty level of the students. These contents (subject wise) are as per   Annexure  ‘A’

· Processes: - Based on these contents the Modules were prepared by the experienced teachers and training was imparted to the resource persons (40 from each district)by DIETs/GISTCs related to SS, Hindi and Punjabi as for as English is concerned around 300 resource persons were trained from RIE.Around 100 primary and upper-primary resource persons were trained by Navnamriti  Bombay. Resource persons imparted training to 32159 In-service Teachers as per time frame given below.

Teacher Training Calendar:

 A phase wise teacher training calendar observed for training in various subjects was carried out by the State involving the resource faculty from GISTC and DIETS. The schedule for four phases is given below.

Subjects covered: - Math, Hindi, Punjabi, Science, Social Science

	Phase
	Date
	Subject

	Phase -1
	20.10.08 to 25.10.08

22.10.08 (Wednesday) Meeting
	As per Micro plan given by GISTC/DIETs

	Phase -2
	30.10.08 to 04.11.08
	As per Micro plan given by GISTC/DIETs

	Phase -3
	06.11.08 to 14.11.08

12.11.08(Wednesday) Meeting)
	As per Micro plan given by GISTC/DIETs

	Phase -4
	17.11.08 qo 22.11.08

20.11.08  (Wednesday) Meeting
	As per Micro plan given by GISTC/DIETs


English language has been given special focus in the teachers training:
	Phase
	Date
	Subject

	Phase -1
	25.11.08 to 01.12.08

26.11.08 (Wednesday) Meeting 
	As per Micro plan given by GISTC/DIETs

	Phase -2
	02.12.08 to 08.12.08

03.12.08 (Wednesday)
	As per Micro plan given by GISTC/DIETs

	Phase -3
	15.12.08 qo 20.12.08

17.12.08 (Wednesday) Meeting
	As per Micro plan given by GISTC/DIETs

	Phase -4
	06.01.09 qo 13.01.09 

07.01.09 (Wednesday) Meeting
	As per Micro plan given by GISTC/DIETs


· Computer Training was also imparted to the teachers to develop the skill related to IT.

· Divisional teams, district science supervisors, DIET and GISTCs faculty DRPs, BRPs and CRPs were put on the job to visit schools to see whether the training imparted to the teachers is bring replicated or utilized in the classroom process.

The following table reflects the break up of in- service training.

Break-up of In-service Trainings conducted during 2008-09

	Activity
	Target Group
	Duration in days
	Physical Target
	Level

	Training to resource persons
	Primary & upper primary math teachers
	3
	100
	state level

	Training to resource persons
	Primary teachers
	3
	850
	district level

	Training to primary teachers
	Primary teachers
	10
	34246
	block level

	Training to master trainers
	Upper primary English teachers
	5
	300
	state level

	Training of math
	Maths Teachers
	5
	4400
	block level

	Training of Punjabi
	Punjabi teachers 
	5
	4796
	block level

	Training of Hindi
	Hindi Teachers
	5
	4081
	block level

	Training of yoga
	Sport Tecahers
	5
	3023
	block level

	Training of English
	S.S Teachers 
	5
	9732
	block level

	Training of computer
	Subject Teachers 
	4
	2226
	block level

	Monthly meetings & trainings
	all subject teachers
	6
	39993
	block level

	Monthly meetings & trainings
	Primary teachers
	6
	34246
	cluster level


The Training Programme under SSA is implemented by training the Key Resource Persons at State Level by National experts. The DIETs / GISTCs are the nodal agencies of the Training Programme. Training to Master Trainers is imparted at District level. Training to Primary and Upper Primary teachers is given at Block/ Cluster level under the supervision of DIETs / GISTCs. Monthly meetings are held to provide necessary guidelines and directions and also to get the feedback of the progress in Teachers’ Training. Various teacher training programmes organized during 2008-09 have been as follows:

· A special teacher training workshop for a group of 100 teachers of Primary & Upper Primary teachers by the Navnimriti, Pune.

· Training of master trainers in English at State Level by Regional Institute of English, Chandigarh and preparation of Modules in English with the help of RIE.

· General training imparted to Centre Head Teachers/Block Primary Education Officers for 5 days.

· 1 day general training imparted to batch of 40 teachers each from all the districts through EDUSAT.  Resource persons from college cadre gave guest lectures through EDUSAT.  DGSE also interacted with teachers & gave valuable guidance.

· 1 day training session conducted by SSA Punjab for PTI & DPEs in which coaches from National Institute of Sports imparted training.DGSE, Director SCERT, Deputy Director Sports, Teacher Training team & all AEOs Sports also provided guidelines for improving the level of games in all the schools of Punjab.

· 5 days general training program organized at DIET Naura Nawanshahar for 100 teachers (Primary & Upper Primary) in 2 batches by IL&FS team.

· Different Workshops were organized at State level for preparation  of modules in the subject of Math, Science, S.S, Hindi, Punjabi, English in which subject lectures from DIETs/ GISTCs & from school cadre participated.

· 1 day workshop for AWP&B for 2009-10 was organized for all District Education Officers and District Coordinators at MGSIPAP Chandigarh. Five consultants from TSG Edcil provided necessary instructions for AWP&B for 2009-10.SSA officers also attended the workshop.

· 90 teachers attended training at ORC New Delhi.
· All Primary teachers of Punjab were trained for ten days during 2008-2009 on special teaching methods to achieve goals of the LEP.
· At Upper Primary level 33103 teachers were trained in interactive way. Five day Subject Training was imparted to Upper Primary Teachers of SS, Science, Mathematics, Punjabi and Hindi.  Apart from this five days subject training was imparted to SS Masters for English Language.
· Five days Yoga and Sports Training was imparted to Physical Education Teachers.
· Four days computer training was imparted to subject teachers to improve their expertise in the field of IT.  Training to all Primary teachers under Parrho Punjab Project. First training of 3 days in July 2008 (completed in three weeks all over Punjab); second training of 4 days in December 2008 (completed in four weeks all over Punjab) and third training of 3 days in Jan-Feb 2009 (completed in 3 weeks all over Punjab).
· Two-tier model of training was adopted to minimize transmission loss. First a State-level training team trained 850 Block Master Trainers at the district level. Thereafter these BMTs trained all Primary Teachers at the Block Level.
· Content of training: Each training was pre planned to ensure good quality and Relevant content matter was provided to the teachers.

Proposal for in-service training for 2009-10: 
The state has planned the teacher training programme for 2009-10 as under:

1.  20 days In-service training to primary and upper primary teachers.

· Teacher Training on subject matter for five days.

· Training through exposures to other institutions for five days.

· Monthly Meetings and trainings at cluster level for 10 days.

2. 30 days training of new recruits (In house).

3. 10 days training of BRPs (In house). 

Process:
1. First round of training will involve five days subject training to all teachers. The subject training for five days to each and every teacher will be imparted at district and block level with the help of DIETs / GISTCs and lecturers of senior secondary schools.

Time Frame for five days In Service Training will be as follows:
	SNo.
	No of Phase
	From – to

	1. 
	Phase -1
	15 April -   20 April, 2009

	2. 
	Phase -2
	21 April -   25 April, 2009

	3. 
	Phase -3
	28  April -  04 May, 2009

	4. 
	Phase -4
	06  May  -  12 May, 2009

	5. 
	Phase -5
	14  May  -  19 May, 2009


2. The Second round of 5 days training will involve experiential trainings and exposure visits for the teachers of science, social science, math, Punjabi and Hindi. Primary and upper primary teachers will be made to visit and see the teaching patterns of model schools, CBSE & ICSE board schools and the State Govt. Senior secondary schools to enable them to have tips on effective teaching. 

3. There will be a parallel system of monthly cluster level meetings and interactive sessions for primary and upper primary teachers.

Inputs:
1. Hard spots have been identified in the subjects of English, Science, Social Science, Math, Hindi and Punjabi by the working teachers as per their difficulties. 

2. Modules are being printed.

3. The key resource persons have been identified to impart subject wise training to the teachers at districts and block level.

4. Micro plan for each and every teacher has been prepared.

5. The DIETs and GISTCs faculty has been put on the job to keep a constant liaison with the teachers and resource persons to adequately assess the training needs of the teachers in the field.

Objectives:-


1. The objectives of In-Service teacher training programme and the training of new recruits is to address the class room issues, to make the teaching learning effective and to improve the performance of students.
2. To familiarize the new recruits with effective methods of teaching.
3. To enable BRPs/DRPs to monitor the class room transactions in a meaningful way.
Expected outcome:-

1. The performance of teachers will get impacted.

2. Learning in children will get facilitated.

3. Achievement of children will improve.

4. Monitoring mechanism will be strengthened.

Physical Proposal for 2009-10:

1. 10 days training for 35302 primary teachers.

2. 10 days training for 36814 Upper primary teachers.

3. 10 days training for 3794 primary and upper primary teachers of aided schools.

4. 10 days monthly meetings cum training for 35302 primary teachers.

5. 10 days monthly meetings cum training for 36814 Upper primary teachers.

6. 10 days monthly meetings cum training for 3794 primary and upper primary teachers of aided schools.

7. 30 days training for 13395 new recruits against vacant posts of primary teachers.

8. 30 days training for 7966 new recruits against vacant posts of upper primary teachers.

9. 30 days training for 2076 Primary and Upper Primary new recruits under SSA.

10. 30 days training for 1779 primary and upper primary new recruits of aided schools.

11. 10 days training to 2480 BRPs.

District wise Physical Proposal for Teacher Training for 2009-10 is given as under:

	SNo.
	District
	In-Service Primary Teachers
	In-Service Upper Primary Teachers
	In-Service Primary and Upper Primary Teachers of Private Aided Schools
	Total In-Service P and U P teachers of Govt. and Private Aided Schools.
	New recruits against vacant posts of Primary Teachers
	New recruits against vacant posts of Upper Primary Teachers
	New recruits under SSA
	Primary and Upper Primary New recruits  of Private Aided School
	Total New Recruits of SSA, Govt.  Schools and Aided Schools.
	Block Resource Persons (BRPs)

	1
	Amritsar
	2714
	2260
	352
	5326
	1005
	519
	182
	212
	1918
	160

	2
	Barnala
	522
	672
	27
	1221
	349
	150
	0
	10
	509
	40

	3
	Bathinda
	1346
	2141
	169
	3656
	553
	294
	40
	38
	925
	90

	4
	Faridkot
	1070
	1163
	77
	2310
	214
	175
	0
	24
	413
	40

	5
	Fatehgarh
	1043
	955
	50
	2048
	292
	138
	98
	11
	539
	100

	6
	Ferozpur
	2880
	2338
	158
	5376
	595
	513
	210
	67
	1385
	200

	7
	Gurdaspur
	3470
	2761
	340
	6571
	1186
	521
	268
	84
	2059
	280

	8
	Hoshiarpur
	2844
	3421
	372
	6637
	1104
	750
	198
	201
	2253
	200

	9
	Jalandhar
	2426
	2810
	473
	5709
	1346
	684
	37
	300
	2367
	190

	10
	Kapurthla
	1435
	1308
	159
	2902
	379
	359
	109
	76
	923
	100

	11
	Ludhiana
	2809
	3386
	598
	6793
	1372
	536
	12
	314
	2234
	210

	12
	Mansa
	1217
	1091
	40
	2348
	265
	411
	78
	36
	790
	60

	13
	Moga
	1328
	1659
	105
	3092
	792
	400
	12
	35
	1239
	90

	14
	Mohali
	981
	1047
	103
	2131
	272
	132
	163
	63
	630
	60

	15
	Mukatsar
	1008
	1642
	35
	2685
	620
	212
	15
	21
	868
	70

	16
	Nawanshahr
	1097
	1027
	119
	2243
	337
	468
	80
	42
	927
	90

	17
	Patiala
	2433
	2840
	242
	5515
	880
	309
	139
	81
	1409
	160

	18
	Ropar
	1368
	1087
	119
	2574
	244
	170
	306
	35
	755
	90

	19
	Sangrur
	1831
	2165
	191
	4187
	746
	552
	15
	91
	1404
	140

	20
	Tarantaran
	1480
	1041
	65
	2586
	844
	673
	114
	38
	1669
	110

	Total
	35302
	36814
	3794
	75910
	13395
	7966
	2076
	1779
	25216
	2480


Budget Proposal for Teacher Training for 2009-10 has been proposed by the State for 1919.93 Lacs as per the district wise cost. The details are reflected as under:
	SNo
	District
	Funds required for In -Service Teacher Training for 10 day for Primary and Upper Primary Teachers of Govt. and Private Aided Schools at District and Block  Level @ Rs.100
	Funds required for Monthly Meetings for 10 day for Primary and Upper Primary Teachers of Govt. and  Private Aided Schools at Cluster Level @ Rs.50
	Funds required for Induction Training for 30 day to New Recruits (Primary and Upper Primary)  of Govt. and Private Aided Schools @ Rs. 100
	Funds required for Training of Block Resource Persons (BRPs) for 10 days @ Rs.100
	Total Budget required for Teacher Training for 2009-10

	1
	Amritsar
	5326000
	2663000
	5754000
	160000
	13903000

	2
	Barnala
	1221000
	610500
	1527000
	40000
	3398500

	3
	Bathinda
	3656000
	1828000
	2775000
	90000
	8349000

	4
	Faridkot
	2310000
	1155000
	1239000
	40000
	4744000

	5
	Fatehgarh
	2048000
	1024000
	1617000
	100000
	4789000

	6
	Ferozpur
	5376000
	2688000
	4155000
	200000
	12419000

	7
	Gurdaspur
	6571000
	3285500
	6177000
	280000
	16313500

	8
	Hoshiarpur
	6637000
	3318500
	6759000
	200000
	16914500

	9
	Jalandhar
	5709000
	2854500
	7101000
	190000
	15854500

	10
	Kapurthla
	2902000
	1451000
	2769000
	100000
	7222000

	11
	Ludhiana
	6793000
	3396500
	6702000
	210000
	17101500

	12
	Mansa
	2348000
	1174000
	2370000
	60000
	5952000

	13
	Moga
	3092000
	1546000
	3717000
	90000
	8445000

	14
	Mohali
	2131000
	1065500
	1890000
	60000
	5146500

	15
	Mukatsar
	2685000
	1342500
	2604000
	70000
	6701500

	16
	Nawanshahr
	2243000
	1121500
	2781000
	90000
	6235500

	17
	Patiala
	5515000
	2757500
	4227000
	160000
	12659500

	18
	Ropar
	2574000
	1287000
	2265000
	90000
	6216000

	19
	Sangrur
	4187000
	2093500
	4212000
	140000
	10632500

	20
	Tarantaran
	2586000
	1293000
	5007000
	110000
	8996000

	Total
	75910000
	37955000
	75648000
	2480000
	191993000


Activity wise Budget Proposal for Teacher Training for 2009-10:

	Activity
	Unit Cost
	Duration
	Physical
	Financial

	10 days training for in-service primary and upper-primary teachers of Govt. Schools
	100
	10
	72116
	72116000

	10 day meetings for in-service primary and upper-primary teachers
	50
	10
	72116
	36058000

	30 days training to new recruits under education department
	100
	30
	21361
	64083000

	30 day induction training to new recruits Primary and Upper Primary Teachers under SSA
	100
	30
	2076
	6228000

	10 days training for primary and upper-primary teachers of Aided Schools 
	100
	10
	3794
	3794000

	10 day meetings for primary and upper-primary teachers of Aided Schools
	50
	10
	3794
	1897000

	30 day induction training for New Recruits of Aided Schools 
	100
	30
	1779
	5337000

	10 days training of BRPs
	100
	10
	2480
	2480000

	Total Budget proposal for 2009-10
	19,19,93,000


Total Budget requirement for Teacher’s Training Programme for 2009-10 = 1919.93 lakh.

ii. Induction training: 

State had a poor progress in induction training during 2008-09, which is a very poor show just at 8.8%. The state team informed that this poor achievement is primarily because of the recruitment process getting delayed and also informed that the induction training is already in progress and by the end of March 2009 these newly recruited teachers will be completing the training.

	Stage
	Duration of training (detailed break up)
	Teachers recruited

(up to end Jan. 2009)
	Teachers trained

(up to end Jan. 2009)
	Percentage of Achievement

	Primary & Upper Primary
	30 days
	6409
	38454

(31278 days)
	8.8%

	Upper Primary
	30 days
	2647
	1950

(10749 days)
	

	Total
	15827

(474810)
	7931
	47586

(42027)
	


iii. Training of Untrained Teachers:

State has a policy to recruit only professionally trained teachers; therefore there is no issue on account of untrained teachers in the State.
Progress of Training of Untrained Teachers (during 2008-09)

	Stage
	Total No. of Untrained teachers
	Target for 60 days training
	Teachers trained during 2008-09
	Percentage of achievement

	Primary
	NIL
	NIL
	NIL
	NIL

	Upper Primary
	NIL
	NIL
	NIL
	NIL


Proposals for 2009-10: 

The following table reflects the over all picture on the progress of training during 2008-09 and the proposal for the year 2009-10.

Overall progress and targets for teacher training 

	Type of training
	Target for training in 2008-09
	Achievement
	% of achievement
	Target for 2009-10

	
	Physical
	Financial
	Physical
	Financial
	Physical
	Financial
	Physical
	Financial

	In-service
	74239
	1113.525
	936878
	96857968
	63.09%
	86.98%
	72116
	113865000

	Induction
	15827
	474.810
	42027
	3490583
	8.85%
	7.35%
	25216
	75648000

	Untrained
	NIL
	NIL
	NIL
	NIL
	NIL
	NIL
	NIL
	NIL

	Trg. Of BRCs, CRCs
	2388
	23.880
	2388
	22.556
	100%
	94.45%
	2480


	2480000


Recommendation:

 The appraisal team recommends for the training component as under:-

1. In-service Training: 76180 teachers ( 10 days at BRC @ 100/- + 10 days at CRC level @ 50/- per day).

2. Induction Training: 1935 new teachers ( 30 days) @ 100/- per day.

 PAB may like to approve.

k. Special initiatives for disadvantaged groups (such as MLE for tribal areas):

The state informed that no other language other than Punjabi is spoken in Punjab and there is as such no notified Tribal area, hence there is no need of such an intervention.

l. Effectiveness of CAL and other educational technologies in quality improvement: 

The appraisal team was given to understand that so far CAL has been introduced in 2200 schools benefiting over 35000 children along with 16022 teachers trained. The services of Microsoft and Intel are being used to promote computer education. As reported the interest as well as the comprehension level of children has got a boost through the programme. Children are showing more interest in subjects like science, Maths and social sciences. 
m. Nature of research and action research: 
A study on teacher student absenteeism was carried out and completed for the state of Punjab during 2008-09. The study was done by Punjabi University, Patiala. The revelations are as under:-

	Pupils’ attendance
	Primary Level:             85-90%

Upper Primary level:   91% 

	Teachers’ attendance
	Primary Level:
76%

Upper Primary level:    87% 


The state has planned to carryout more such studies related to learning assessment, impact of interventions on the classroom practices and so on. Some of the studies planned for 2009-10 are as under:

· Baseline Assessment of performance levels of primary children in reading, writing and numerical skills.

·  Evaluation of the impact of Parrho Punjab Programme for 2008-09. 

· Study on Classroom Transaction for primary and upper primary schools. 

·  Continuous and Comprehensive Evaluation of achievement levels of class-V children. 

· Continuous and Comprehensive Evaluation of achievement levels of class-VI, VII & VIII children. 

3. Academic support systems
i. Block Resource Centers: 

As per the discussion held with the State team it was reported that the Block Resource Centers have been set up to function as sub-district academic support centers at the block level. These are headed by Block Education Officers who are assisted by Block Resource Persons (BRPs) and the supporting staff. The Block Resource Persons are the supervisors and SSA implementing officers for a cluster of 8 to 10 schools. For the purpose of school education the districts have been splitted into Education Blocks.  There are 216 Education Blocks and 141 CD blocks in Punjab.  There is a Block Education Block.  Allocation of funds under SSA is based on the data and statistics of CD blocks where as the implementation of plan is done as per the Education Blocks. There are URCs either sanctioned or proposed by the state.

The main functions of BRCs are as follows:

· To provide academic support to CRCs & schools.

· Monitoring of classrooms activities and schools.

· Receiving feedback from clusters on various areas.

· To organize different types of trainings.

· To interact with community and other functionaries.

· Organize the assessment camp for children with special needs.

· Maintenance of EMIS to keep close vigil on overall educational development in the block
The following table throws light on the status of Block Resource Centers. 

Information about Block Resource Centers

	Total no. of blocks
	BRCs sanctioned
	BRCs functional
	BRPs sanctioned
	BRPs recruited
	BRC mtgs. held in 2008-09
	CRC/ School visits in 2008-09
	% Effectiveness of BRCs

	141
	141BRCs + 1 URC = 142
	141BRCs + 0 URC = 141
	2388
	2388
	Meetings held every month
	
	


Source: AWP & B, 2009-10 

Major role and functions of BRCCs and BRPs: As stated the BRCs play a major role toward the academic support to the teachers during teachers training and have a continuous feedback from the CRCs. The calendar of activities is reflected in the table below.
Activity Calendar of BRC
	Activities 
	Month
	Venue

	· To provide academic support to CRCs & schools.

· Monitoring of classrooms activities and schools.

· Receiving feedback from clusters on various areas.

· To organize different types of trainings.

· To interact with community and other functionaries.

· Organize the assessment camp for children with special needs.

· Maintenance of EMIS to keep close vigil on overall educational development in the block.
	Every month
	BRC


Source: AWP & B, 2009-10 

It was further revealed that to further strengthen the academic support role , the state has raised about 900 Block master Trainers, who have volunteered to lend academic and monitoring support to the teaching learning process in the schools. The State project Director himself conducts monthly review meeting with the District and block level officers to have a first hand feed back. The appraisal team appreciates the initiative taken by the State.
ii. Cluster Resource Center (CRC):

   The following table reflects about the status of Cluster resource centres:

Information about Cluster Resource Centers

	Total no. of clusters
	CRCs sanctioned
	CRCs functional
	CRCCs sanctioned
	CRCCs in position
	CRC mtgs. held in 2008-09
	School visits in 2008-09
	% Effectiveness of CRCs

	1499
	1499
	1499
	1300
	1499*
	monthly
	-
	-


Source: AWP & B, 2009-10

* 1300 buildings have been constructed for CRCs under SSA but in all the state has 1499 CRCs. All the centres are operational. CRCs, for which buildings are yet to be sanctioned under SSA, are operating from their previous buildings located in govt. primary schools.

Major role and functions of CRCCs and CRPs: As stated by the state representative the CRCs hold monthly meetings with the teachers to assess their problems and the same are discussed in the group as well as with BRCs to address them. They are one of the major link between schools and the academic support system. The CRCCs are selected from among the existing regular teachers. It is a good practice in the State that the deputation of the resource persons is from amongst the experienced teachers only. The calendar of activities at the CRCs is reflected in the table below.

Activity Calendar of CRC
	Activity
	Month
	Venue

	· Provision of academic support to VEDCs & school teachers and schools.

· Monitoring of classrooms activities in schools.

· Collection of progress reports from schools.

· Organize cluster level monthly meetings and trainings for teachers.

· To interact with community and other functionaries.

· Organize the assessment camp for children with special needs.

· Maintenance of EMIS to keep close vigil on overall educational development in the block.
	Montly
	CRC


Source: AWP & B, 2009-10
Capacity Building for BRC/CRC Personnel: 

The following table indicates the type of training programmes undertaken for the BRCs and CRCs during 2008-09, and proposals for 2009-10.





Training of BRC/ CRC personnel
	Target Group
	Training in 2008-09
	Training in 2009-10

	
	Duration
	Focus areas
	Duration
	Focus areas

	BRCC
	10 days
	Training of teachers, Academic support for the schools, monitoring of the classroom transactions, community mobilization, MIS 
	10 days
	Training of teachers, Academic support for the schools, monitoring of the classroom transactions, community mobilization, MIS 

	BRPs
	
	
	
	

	CRCC
	
	
	
	

	CRPs
	
	
	
	


Source: AWP & B, 2009-10 

The following table gives an over all picture of the progress of the training imparted towards the capacity building of the resource persons and also the proposal for 2009-10.

Overall physical progress and targets for BRC/CRCs

	Items
	Target for 2008-09
	Achievement
	% of achievement
	Target for 2009-10

	
	Physical
	Financial
	Physical
	Financial
	Physical
	Financial
	Physical
	Financial

	BRCs
	2388
	23.88 lakh
	2388
	21.05 lakh
	100%
	88.16%
	2480
	24.80 lakh

	CRCs
	1499
	
	1499
	
	
	
	
	


Source: AWP & B, 2009-10

Proposal: 

The State has proposed a training support for 2480 resource persons for 10 days during 2009-10

Recommendation:

The appraisal team recommends 10 days training for 2480 resource persons as proposed.

iii. Resource Groups & Subject Expert Forums:
The State has attempted to strengthen its academic resource groups at different levels. The following table indicates the structure of these resource groups and their major activities.

Information about Resource Groups at different levels

	SNo.
	Resource Groups 

(RGs)
	Whether constituted 

(how many)
	Number of members per RG
	Number of meetings held this year
	3 Key activities undertaken by the Resource Groups this year

	1. 
	State Resource Group (SRG)
	Yes
	36
	Monthly meetings are held
	· Drawing of framework for parrho Punjab project.

· Planning to address gender issues.

· Working out modalities for effective teacher training programme.

	2. 
	District Resource Groups (DRGs)
	Yes
	10-12
	
	· 

	3. 
	Block Resource Groups (BRGs)
	Yes
	15-20
	
	· 

	4. 
	Cluster Resource Groups (CRGs)
	Yes
	8-10
	
	· 


Source: AWP & B, 09-10

Nature of convergence & collaboration among different academic institutions: There is close collaboration with academic institutions like SCERT, SISE, DIETs, GISTCs, Punjab University, Chd, Punjabi Univerisy, Patiala, Regional Institutions, IGNOU, NIAR and Edcil etc. for the programme of teacher’s training, research and monitoring of educational process. GISTCs are the unique feature in the State, which are functional in addition to the DIETS and it is worth appreciating that the State is activating these institutions to have a partnership in building the scenario for academic support to usher in quality improvement.
Performance tracking indicators for CRCs, BRCs, DIETs: State is not yet geared up for performance tracking under ADEPTS. So far no indicators have been identified, which is essential to track the performance at each level so as to ensure an apparatus of accountability and self appraisal. The State has shared its own system of tracking, which is reflected in the table given below.

	10 Major Performances Standards identified for School Teacher
	10 Major Performances Standards identified for CRC Personnel
	10 Major Performances Standards identified for  BRC Personnel

	1    Activities done for Upliftment of level of Education(Max. 2 Marks for every work)
	1    Activities done for Upliftment of level of Education(Max. 2 Marks for every work)
	1    Activities done for Upliftment of level of Education(Max. 2 Marks for every work)

	Activities
	Merit Marks
	Activities
	Merit Marks
	Activities
	Merit Marks

	A. Weekly/Daily Diary
	
	A. Weekly/Daily Diary
	
	A. Weekly/Daily Diary
	

	B. Checking of copies
	
	B. Checking of copies
	
	B. Checking of copies
	

	C. Class test
	
	C. Class test
	
	C. Class test
	

	D. Use of Teaching Aids
	
	D. Use of Teaching Aids
	
	D. Use of Teaching Aids
	

	E. Contribution to avoid

   copying during examination 
	
	E Contribution to avoid

   copying during examination
	
	E. Contribution to avoid

   copying during examination 
	

	k. Over Time
	
	F. Over Time
	
	F. Over Time
	

	2. Work done for 

    development of School/ 

    Institution (Max.2 marks 

    for every work)
	2. Work done for development of School/ Institution (Max.2 marks for every work)
	2. Work done for development of School/ Institution (Max.2 marks for every work)

	
	
	
	
	
	

	B. Morning Assembly
	
	B. Morning Assembly
	
	B. Morning Assembly
	

	C. Class Incharge
	
	C. Class Incharge
	
	C. Class Incharge
	

	D. Fund Incharge
	
	D. Fund Incharge
	
	D. Fund Incharge
	

	E. NCC/Scouts Guides/NSS Incharge
	
	E. NCC/Scouts Guides/NSS Incharge
	
	E. NCC/Scouts Guides/NSS Incharge
	

	F. Contribution towards Beautification of School 
	
	F. Contribution towards Beautification of School 
	
	F. Contribution towards Beautification of School 
	

	G. Contribution towards Discipline
	
	G. Contribution towards Discipline
	
	G. Contribution towards Discipline
	

	H. Contribution of Parent-Teacher Association towards Institution 
	
	H. Contribution of Parent-Teacher Association towards Institution 
	
	H. Contribution of Parent-Teacher Association towards Institution 
	

	I. Contribution towards Co-curricular Activities/Competition of students
	
	I. Contribution towards Co-curricular Activities/Competition of students
	
	I. Contribution towards Co-curricular Activities/Competition of students
	

	J. Contribution towards Educational Tours/ Functions
	
	J. Contribution towards Educational Tours/ Functions
	
	J. Contribution towards Educational Tours/ Functions
	

	3. Increase in Work 

     Efficiency (Max.2 marks for every work)
	3. (Max.2 marks for every work)
	3 (Max.2 marks for every work)

	A. Improvement in Qualification
	
	A. Improvement in Qualification
	
	A. Improvement in Qualification
	

	B. Writings/
	
	B. Writings/
	
	B. Writings/
	

	C. New Teaching Methods
	
	C. New Teaching Methods
	
	C. New Teaching Methods
	

	D. Seminars/ Workshops Attended
	
	D. Seminars/ Workshops Attended
	
	D. Seminars/ Workshops Attended
	

	4. Effectiveness in the development and protection of Scheduled Castes and/or Scheduled Tribes (Applicable in case of official dealing with the development and protection of Scheduled Castes and/or Scheduled Tribes)
	4. Effectiveness in the development and protection of Scheduled Castes and/or Scheduled Tribes (Applicable in case of official dealing with the development and protection of Scheduled Castes and/or Scheduled Tribes)
	4. Effectiveness in the development and protection of Scheduled Castes and/or Scheduled Tribes (Applicable in case of official dealing with the development and protection of Scheduled Castes and/or Scheduled Tribes)

	a. Attitude towards Scheduled Castes and/or Scheduled Tribes
	
	a. Attitude towards Scheduled Castes and/or Scheduled Tribes
	
	a. Attitude towards Scheduled Castes and/or Scheduled Tribes
	

	b. Sensitivity to social justice
	
	b. Sensitivity to social justice
	
	b. Sensitivity to social justice
	

	c. Ability to take quick and effective action to precent and quell atrocities and ensure justice to  Scheduled Castes and/or Scheduled Tribes
	
	c. Ability to take quick and effective action to precent and quell atrocities and ensure justice to  Scheduled Castes and/or Scheduled Tribes
	
	c. Ability to take quick and effective action to precent and quell atrocities and ensure justice to  Scheduled Castes and/or Scheduled Tribes
	

	d. effectiveness in bringing about the development of  Scheduled Castes and/or Scheduled Tribes
	
	d. effectiveness in bringing about the development of  Scheduled Castes and/or Scheduled Tribes
	
	d. effectiveness in bringing about the development of  Scheduled Castes and/or Scheduled Tribes
	

	5.   Evaluation of Teachers (Best Annual result should be considered)


	5.  Evaluation of Teachers (Best Annual result should be considered)


	5.   Evaluation of Teachers (Best Annual result should be considered)



	Merit Marks for result less than 20%
	0
	Merit Marks for result less than 20%
	0
	Merit Marks for result less than 20%
	0

	Merit Marks for result 20% to 40%
	10
	Merit Marks for result 20% to 40%
	10
	Merit Marks for result 20% to 40%
	10

	Merit Marks for 40% upto Board result 
	30
	Merit Marks for 40% upto Board result 
	30
	Merit Marks for 40% upto Board result 
	30

	Merit Marks for upto 10% above the Board result 
	50
	Merit Marks for upto 10% above the Board result 
	50
	Merit Marks for upto 10% above the Board result 
	50

	Merit Marks for 10% above the Board result or 100% result
	60
	Merit Marks for 10% above the Board result or 100% result
	60
	Merit Marks for 10% above the Board result or 100% result
	              60



	1. Total Merit Marks for Annual Result
	Out of 60
	
	1. Total Merit Marks for Annual Result
	Out of 60
	
	1. Total Merit Marks for Annual Result
	Out of 60
	

	2.Merit Marks for Other Contributions
	Out of 40
	
	2Merit Marks for Other Contributions
	Out of 40
	
	2Merit Marks for Other Contributions
	Out of 40
	

	Total Merit Marks
	Out of 100
	
	Total Merit Marks
	Out of 100
	
	Total Merit Marks
	Out of 100
	

	6. Gradation of Teachers
	6. Gradation of Teachers
	6. Gradation of Teachers

	Merit Marks 81-100
	Excellent
	(A)
	Merit Marks 81-100
	Excellent
	(A)
	Merit Marks 81-100
	Excellent
	(A)

	Merit Marks61-80
	Very Good
	(A)
	Merit Marks61-80
	Very Good
	(A)
	Merit Marks61-80
	Very Good
	(A)

	Merit Marks41-60
	Good
	(B)
	Merit Marks41-60
	Good
	(B)
	Merit Marks41-60
	Good
	(B)

	Merit Marks21-40
	Average
	(B)
	Merit Marks21-40
	Average
	(B)
	Merit Marks21-40
	Average
	(B)

	Merit Marks0-20
	Less than Average
	(C)
	Merit Marks0-20
	Less than Average
	(C)
	Merit Marks0-20
	Less than Average
	(C)


The appraisal team insists that the State must identify the performance indicators under ADAPTS for teachers and trainers during 2009-10, which is non negotiable.

5. Public Private Partnerships (PPP) for quality improvement).

The state has not been involving the NGO partners in the SSA interventions, except a few as mentioned below.

· Computer traning for school teachers is done by AIFT, Microsoft and Intel in PPP mode.

· Non govt. organizations were involved to carry out the programme for alternative innovative education/non residential bridge courses and residential bridge courses for out of school children in the age group 8+ to 14.

6. Quality management for quality assurance:

Quality Monitoring Tools (NCERT)
The State team has informed that NCERT Quality monitoring tools are constantly being implemented and Information on Quality Dimensions Reporting Performa, STLF I(a), I(b), III for 1st Quarter up to 30 Sep., 2008 have been sent to NCERT. The state team revealed that during the focus has been on the Parro Punjab movement, yet there has been full implementation of QMT in the State. State has shown further resolve to use the findings of QMT in the quality improvement programme to be carried out in 2009-10.

Overall Quality Initiatives in the State:

(i) Baselines for learning assessment of primary children as done for primary classes in the beginning of academic session 2008-09.

(ii) Implementation of parrho Punjab programme for promotion of reading, writing and numeric skills of primary children.

(iii) Preparation and usage of supplementary reading material and graded material for primary schools.

(iv) Carrying out pilot project for promotion of English teaching learning. The project was named as Angrezi  A-Z.

(v) Establishment of reading corner in the schools. 

(vi) Midterm evaluation of the achievement levels of primary children under parrho Punjab programme.

(vii) Supply of magazines like “Aale Bhole” and “Primary Sikhya” to all the primary schools.

(viii) Preparation and use of teacher training modules for Science, Social Science, Maths, Punjabi and Hindi.

(ix) Steps towards establishment of science and maths labs at upper primary level and maths labs at primary level.

(x) Training of teachers on use of computers.

(xi) Instituting the system of monthly tests for Science and maths for upper primary classes. 

(xii) Competitive tests for girls of classes VI and VII.

(xiii) Award to the three best performing girls of classes V, VI, VII and VIII each, in every block.

(xiv) Launching of district and state level competitive exams for students of class V and VIII for Science and Maths to promote the interest and learning in the subjects.

(xv) Exposure visits for girls under the programme of girl’s education.

(xvi) Yoga training for girls of primary and upper primary schools.

(xvii) Sensitization on gender issues by way of showing mena films in schools and villages.

(xviii) Remedial coaching to the weak children of primary and upper primary classes.

(xix) Holding training programmes for academic and financial management issues for CRCs, BRPs, School Heads and Principals and district level functionaries through EDUSAT.

(xx) Rationalization and filling up the vacancies; Appointment of 10678 primary teachers and 4405 upper primary teachers.

(xxi) Conduction of research studies on teacher student absenteeism, impact of remedial coaching, status of black boards and initiation for the study on classroom transaction: it has been a general endeavor to identify the gray areas.

(xxii) Non residential and residential bridge course for out of school children.

(xxiii) Stringent monitoring and supervision system to monitor the entire education process: The state has constituted divisional monitoring cells. It is also appointed three monitoring coordinators for the entire state. District and block level functionaries have been put on the job to take up regular visits of the schools. Special monitoring registers have been revised and provided at the level of district, block, cluster and schools. The consolidated information helps the state to identify the lapses and subsequently to take corrective measures.

(xxiv) Activation of BRCs and CRCs to perform their roles pertaining to monitoring of schools, provision of academic support to the schools to improve classroom transaction as well as promote learning level of children, providing training to the teachers, supervising the execution of all educational programmes upto grass root level and community awareness & moralization. 

(xxv) Monthly meetings at Block and Cluster levels to provide a platform for experiential trainings for teachers.

Based on the above discussion the Appraisal recommends the following way for activities related to overall quality improvement under SSA.

	SNo.
	Interventions
	Proposed
	Recommended
	Remarks

	
	
	Physical
	Financial (Rs. in lakh)
	Physical
	Financial (Rs.in lakh)
	

	1.
	Teacher recruitment
	
	
	
	
	

	
	New Teachers Salary (P.S.)
	138
	231.84
	138
	-
	

	
	New Teachers Salary (UPS)
	1947
	3855.06
	1797
	-
	

	
	Addl. Teachers against PTR
	0
	0
	0
	-
	

	.
	Recurring
	2905
	5001.90
	
	-
	

	2.
	Training
	
	
	
	
	

	a.
	In service (PS+UPS)
	75910
	1138.65
	76180
	1442.70
	

	b.
	Induction training
	25224
	756.72
	1935
	58.05
	

	
	Training of untrained teachers 
	0
	0
	0
	0
	

	
	Training of BRC, CRC Personnel
	2480
	24.80
	2480
	24.80
	

	5. (a)
	Free Textbooks (PS)
	1360650
	1223.40
	543349
	-
	@110/-unit cost

	    (b)
	Free Textbooks (UPS)
	822205
	1232.65
	410774
	-
	@‘250/-unit cost

	
	Sub Total
	2182855
	2456.05
	954123
	1624.62
	

	6. (a)
	TLM Grant (P)
	49361
	246.805
	35616
	178.08
	

	    (b)
	TLM Grant (UP)
	51773
	258.865
	40564
	202.82
	

	
	Sub Total
	101134
	505.67
	76180
	380.90
	

	7. (a)
	School Grant (P)
	13559
	677.95
	13490
	674.50
	

	    (b)
	School Grant (UP)
	6625
	463.75
	5976
	418.32
	

	
	Sub Total
	20184
	1141.70
	19466
	1092.82
	

	8. (a)
	TLE Grant (P)
	69
	13.80
	69
	13.80
	

	    (b)
	TLE Grant (UP)
	649
	324.50
	599
	299.50
	

	    (c)
	UPS Not covered under OBB 
	
	
	
	0
	

	
	Sub Total
	718
	338.30
	688
	313.30
	

	9
	Remedial teaching
	112019
	560.10
	69852
	349.26
	@ 500/- unit cost

	10.
	LEP
	
	1393.09
	
	762.35
	

	11.
	BRCs
	
	7488.28
	142
	4214.68
	

	12.
	CRCs
	
	123.77
	1499
	113.92
	


(IV) SIEMAT

No proposal for SIEMAT by the State
(V) Inclusive Education

The State of Punjab was slow in the area of IE during the initial years of the programme. Neither the State had involved the NGOs actively in the IE programme nor had it conducted intensive capacity building exercises for functionaries at the various levels to increase awareness on IE. However, now activities like identification, assessment, aids and appliances, training, appointment of resource teachers, etc. have been taken up. But the State needs lot of capacity building in IE and chalk out a sustainable strategy for IE. The state also needs to strengthen monitoring and supervision of IE activities.

Progress in 2008-09:

The physical and the financial progress of the State is given below.

· 73.16% CWSN covered through regular schools, AIE/ EGS and home-based education

· 69 NGOs involved

· 970 teachers trained through 45/90 day training

· Only 56.6% (11021) schools  provided with ramps

· 202 resource teachers appointed

· Only 48.21% CWSN provided aids and appliances

In the year 2008-09, the State had identified 49283 CWSN and the total budget provided the State was 394.27 lakh.  The State was able to spend 223.04 lakh (56.5%).

District wise Progress:

	SNo.
	Name of District
	No. of CWSN identified
	No. of CWSN Enrolled
	No. of CWSN covered through EGS / AIE
	No. of CWSN covered through HBE
	No. of CWSN covered through Resource Rooms
	No. of CWSN provided aids and appliances
	No. of NGOs Involved
	No. of Resource Teachers appointed
	No. of Schools made Barrier Free

	1
	Amritsar
	2584
	2051
	400
	126
	7
	628
	4
	14
	518

	2
	Barnala
	747
	598
	80
	22
	47
	196
	0
	3
	164

	3
	Bathinda
	2504
	2093
	250
	130
	31
	316
	0
	6
	392

	4
	Faridkot
	2145
	1643
	200
	50
	252
	224
	4
	5
	237

	5
	Fatehgarh Sahib
	1491
	1303
	80
	58
	50
	180
	0
	5
	219

	6
	Ferozepur
	5364
	4100
	700
	541
	23
	982
	18
	19
	1108

	7
	Gurdaspur
	3299
	2607
	250
	62
	380
	853
	6
	18
	270

	8
	Hoshiarpur
	3272
	2551
	150
	239
	332
	313
	0
	19
	900

	9
	Jalandhar
	3082
	2464
	150
	236
	232
	699
	6
	16
	1246

	10
	Kapurthala
	1458
	1197
	150
	77
	34
	181
	2
	7
	598

	11
	Ludhiana
	3658
	3143
	200
	175
	140
	776
	2
	19
	885

	12
	Mansa
	1510
	1215
	150
	108
	37
	297
	3
	4
	330

	13
	Moga
	1686
	1211
	150
	146
	179
	299
	0
	6
	535

	14
	Mohali
	1454
	1247
	50
	61
	96
	112
	0
	7
	85

	15
	Muktsar
	3377
	2438
	300
	227
	412
	520
	6
	6
	466

	16
	Nawanshahar
	1579
	1357
	100
	61
	61
	216
	1
	7
	559

	17
	Patiala
	3255
	2519
	300
	319
	117
	471
	5
	14
	1040

	18
	Ropar
	2453
	2242
	100
	81
	30
	190
	0
	7
	603

	19
	Sangrur
	2424
	2210
	200
	14
	0
	740
	11
	11
	554

	20
	Tarn Taran
	1941
	1520
	300
	36
	85
	679
	1
	9
	312

	
	TOTAL
	49283
	39709
	4260
	2769
	2545
	8872
	69
	202
	11021


Financial Progress in 2008-09:

	SNo.
	Activity Description
	Financial 

(Rs. in lakhs)
	Expenditure till January 2009


	% Exp

	1. 
	Assessment & Distribution Camps for children with special needs
	21.60
	22.32
	103.33

	2. 
	Community Awareness including sports tournaments, rallies, educational trips, picnics, screening of media, cultural programs, competitions
	20.00
	19.58
	97.90

	3. 
	Salary of Special Educators appointed @ 1 per PE Block @ Rs. 6500
	168.48
	114.73
	68.10

	4. 
	Salary of district coordinators
	16.80
	6.24
	37.14

	5. 
	Development of TLM for Learning corners @ Cluster level
	1.08
	2.00
	185.19

	6. 
	State & District level workshops/ meetings
	1.00
	1.68
	168.00

	7. 
	Honorarium to Volunteers for CBR, providing HBE, and managing Cluster Resource Room for 9 months
	55.80
	17.11
	30.66

	8. 
	Training of govt. teachers/ BRPs/ IED Coordinators in 3-month RCI Foundation Course/ other Special Courses
	10.00
	8.00
	80.00

	9. 
	Corrective surgery/ therapy/ pre-requisite tests before recommendation/ post operative care
	18.00
	0.20
	1.11

	10. 
	Provision of recommended aids & appliances/ Assistive devices
	75.00
	30.95
	41.27

	11. 
	2-day sensitization training of all teachers on IE
	
	0.00
	0.00

	12. 
	1-day sensitization of all Heads of School
	
	0.0014
	0.00

	13. 
	Sensitization training of VEC/ Panchayat/ community members in IE
	
	0.00
	0.00

	14. 
	Barrier-free access/ Construction of ramps with handrails/ toilet modifications
	
	0.0016
	0.00

	15. 
	Development of Documentaries/ short duration social advertisements/ Training Modules/ Posters/ useful literature & other IEC material
	4.01
	0.14
	3.49

	16. 
	Innovative Pilot projects/ Assessment of LD/ IQ testing for MR/ Research studies
	2.50
	0.00
	0.00

	
	Total
	394.27
	223.05
	56.57%


As of January 2009, the State had expended 56.57%. The anticipated expenditure by March 2009 is Rs. 416.82 lakh against Rs. 394.26 (106.00%). The State has also exceeded expenditure in the 3 activities of assessment camps, development of TLM and workshops. The expenditure on assistive devices is also expected to be more than the amount sanctioned.

Expenditure of Punjab in IE since 2005-06

	Year
	Outlay
	Exp
	% Exp

	2005-06
	467.44 lakh
	459.50 lakh
	98.30%

	2006-07
	446.52 lakh
	178.24 lakh
	39.92%

	2007-08
	393.22 lakh
	310.15 lakh
	78.87%

	2008-09
	394.27 lakh
	223.04 lakh
	56.57%


The State has gradually shown an improvement in expenditure, in the last 2 years as shown above. The State conducted 3-4 workshops on IE in year 2008-09 in different thematic areas related to IE. The anticipated expenditure on IE till March 2009 is 100%. 

Number of CWSN Identified in 2009-10:

The State has identified 70064 CWSN (shown below), which is 1.60 % of the total child population (4377459).

	SNo.
	Category
	No. of CWSN

	1
	Visually Impaired
	13433

	2
	Hearing Impaired
	7529

	3
	Mentally Retarded
	10593

	4
	Orthopedically Handicapped
	18904

	5
	Learning Disability
	14969

	6
	Multiple Disabilities
	3144

	7
	Cerebral Palsy
	1422

	8
	Others
	70

	Total CWSN
	70064


District wise Coverage Plan of CWSN: 2009-10:

	SNo.
	District
	No. of CWSN Identified
	% CWSN against child population
	No. of CWSN enrolled in school
	No. of CWSN to be enrolled in school
	No. of CWSN Proposed to cover through EGS / AIE
	No. of CWSN Proposed to cover through HBE
	No. of CWSN proposed to be cover through Resource Room

	1
	Amritsar
	4852
	1.48
	3272
	868
	0
	356
	356

	2
	Barnala
	1207
	1.16
	946
	135
	0
	47
	79

	3
	Bathinda
	3142
	1.51
	1989
	428
	0
	245
	480

	4
	Faridkot
	2110
	2.08
	1508
	82
	0
	170
	350

	5
	Fatehgarh Sahib
	2464
	2.68
	2077
	0
	10
	120
	257

	6
	Ferozepur
	7035
	2.02
	4625
	55
	158
	501
	1696

	7
	Gurdaspur
	4565
	1.33
	2766
	1005
	260
	94
	440

	8
	Hoshiarpur
	4004
	1.24
	2871
	243
	0
	539
	351

	9
	Jalandhar
	4215
	1.16
	3520
	0
	0
	396
	299

	10
	Kapurthala
	2212
	1.69
	1663
	71
	108
	124
	246

	11
	Ludhiana
	6491
	1.25
	4756
	405
	125
	465
	740

	12
	Mansa
	2169
	1.66
	1422
	219
	75
	136
	317

	13
	Moga
	2514
	1.59
	1770
	236
	0
	234
	274

	14
	Mohali
	2217
	1.88
	1771
	0
	0
	139
	307

	15
	Mukatsar
	3196
	1.92
	2144
	379
	258
	172
	243

	16
	Nawanshahar
	2688
	2.79
	2381
	0
	0
	197
	110

	17
	Patiala
	5610
	1.94
	3940
	437
	0
	477
	756

	18
	Ropar
	2813
	2.37
	2295
	260
	0
	130
	128

	19
	Sangrur
	4509
	1.75
	3116
	905
	0
	188
	300

	20
	Tarn Taran
	2051
	1.12
	1370
	107
	201
	102
	271

	Total
	70064
	1.60
	50202
	5835
	1195
	4832
	8000


The focus of this year on IE would be on the following:

· Salary of resource teachers 

· Conduct of medical camps 

· Provision of aids and appliances

· Community awareness

· Volunteers at the cluster level

· Teacher training

Budget for IE: 2009-10: 

(Rs. in lakhs)
	SNo.
	Activity Description
	Unit Cost 
	Physical
	Financial 
	Time

	1. 
	Assessment Camps for CWSN
	1.04
	20
	20.79
	All year 

	2. 
	Community awareness, including sports tournaments, rallies, educational trips, picnics, screening of media, cultural programs, competitions, celebration of special days like World disabled day, Children's Day, exposure visits, etc.
	1.00
	20
	20.00
	All year

	3. 
	Salary of Inclusive Education Resource Teachers appointed at Block level @ Rs. 7500/- p.m.; fixed TA to be paid from PM head
	0.075
	224
	201.60
	All year

	4. 
	Salary of district special educators at district level for improving quality of program, capacity building of IERTs, effective monitoring and supervision; @ Rs. 12000/- p.m.
	From PM fund


	
	All year

	5. 
	Salary of special education technical personnel at the state level @ Rs. 13000/- p.m.
	From PM fund


	
	All year

	6. 
	Honorarium to IE Volunteers for CBR, providing HBE, and managing Resource Room/ Learning corner, appointed at cluster level 
	0.02
	1274
	305.76
	All year

	7. 
	Helper for Blind IERTs @ Rs. 2000/- p.m. + fixed TA @ 1000/-
	0.03
	6
	2.16
	All year

	8. 
	Setting up of Learning corners @ Cluster level and provision of TLM and necessary material
	0.01
	1274
	12.74
	April- June 2009

	9. 
	Development up of Resource Room @ Block level & provision of TLM & necessary Resource Material
	0.01
	216
	2.16


	April- June 2009

	10. 
	State & District level workshops/ meetings, including 3 at the Sate level (TLM development, etc.)
	From PM fund


	
	All year

	11. 
	Training of govt. teachers/ BRPs/ IED Coordinators in 3-month RCI Foundation Course/ other Special Courses
	0.05
	20
	1.00
	May, September 09 and Jan 2010

	12. 
	Provision of Speech Therapy/ Physio Therapy/ Occupational Therapy & one-week Training to IERTs in provision of therapy.
	0.25
	20
	5.00
	All year

	13. 
	Corrective surgery/ therapy/ pre-operative interventions/ tests before recommendation and post operative care.
	0.50
	20
	10.00
	All year

	14. 
	Provision of recommended aids & appliances/ Assistive devices/ modified furniture/ Braille books
	0.02
	2570 CWSN
	55.09
	July 2009- March 2010

	15. 
	2-day sensitization training of all teachers on IE

	From TT head


	
	May- June, December 2009

	16. 
	1-day sensitization of all Heads of School (HTs/ CHTs)
	0.05
	20
	1.00

	May- June, December 2009

	17. 
	3-day training to govt/ PRI/ ETT school teachers
	0.001 per day
	1000 teachers
	3.00

	May- June, December 2009

	18. 
	Sensitization training of VEC/ Panchayat/ community members in IE
	From CM head
	
	September- Nov 2009

	19. 
	Barrier-free access/ Construction of ramps with handrails/ toilet modifications/ barrier-free water systems
	0.02
	2000
	20.00
	All year

	20. 
	Development of Brochures/ Documentaries/ short duration social advertisements/ Posters/ useful literature & other IEC material
	From PM Head
	
	All year

	21. 
	Innovative Pilot projects/ Assessment of LD/ IQ testing for MR/ Research studies
	3.00
	1
	3.00
	All year

	22. 
	Training to IE Volunteers (5 + 3 days @ Rs 50.00 )
	0.0005
	1274
	5.10
	May- June 2009, Sept- Dec 2009

	23. 
	5- day cross disability training of IERTs @ Rs. 200/- per day
	0.002
	224
	2.24
	May- June 2009

	24. 
	Escort Allowance/ Travel Allowance for 6 months
	0.003 per month
	556
	10.00
	All year

	25. 
	Vocational Project for CWSN @ 1 in each district
	1.00
	20
	20.00
	All year

	26. 
	One computer for IED wing @ district level/ Pen drive to IERTs/ DSE/ IEC
	From PM


	
	April – June 2009

	27. 
	Exposure visits of IECs/ DSEs to other states/ IERTs to special schools
	From REMS


	
	April, Sep- Oct 2009

	28. 
	Child Tracking Software
	From REMS
	
	April – May 2009

	29. 
	Special Survey of Urban Wards/ Cities
	From REMS
	
	April – May 2009

	Total
	700.64
	


Recommendation:

The Appraisal Team recommends a total of Rs. 700.64 lakh for 70064 CWSN @ Rs. 1000/- as the State has shown 78.87% actual expenditure on IE in 2007-08. 

The State has no doubt showed a tremendous improvement in IE related activities. The State has improved its identification also. However the state has proposed an amount of Rs.840.77 lakh, which is a hike against the proposed amount of Rs.555.84 lakh in 2006-07, Rs.589.82 lakh in 2007-08 and Rs. 591.396 in 2008-09. The State was not able to spend the entire budget in 2006-07 and 2007-08. Even in 2008-09 the state has shown 56.5% expenditure till January 2009, but is expecting 100% expenditure till March 2009. 

The Appraisal Team did not recommend the following activities as they are not allowed under SSA:

· Fees for CWSN who are enrolled in special schools by SSA

· Salary of State level 3 (IERTs (SSEs). 1 at the State level has been sanctioned
· Stipend for CWSN who start attending school on regular basis

Some of the activities curtailed are:

· Setting up of 2nd Resource Room @ Block level & provision of TLM & necessary Resource Material. Setting up of resource rooms are not allowed under SSA. The Appraisal Team has sanctioned Rs. 2.16 lakh for strengthening of 216 resource rooms

· School readiness/ pre-integration camps to teach ADL skills, inter-personal & social skills and classroom skills. Since the State is hiring volunteers for HBE and has RTs, school readiness, the State should impart school readiness skills to CWSN through them as a part of their job chart. The State has been taking funds for RBCs for CWSN under AIE. The state has covered 1007 CWSN in 2008-09 and have been sanctioned 1000 CWSN for the current year through RBCs. Hence, this activity has been dropped

· Remedial teaching should be undertaken for those out of school CWSN who are being mainstreamed into regular schools either through bridge courses or home based education programme. The state should evolve a strategy for remedial teaching for at least 6 months to give due attention to these children

· Cross disability training of IERTs/ enrolment in short duration CRE continuing education programs / Sports training to IERTs. This has been given @ Rs. 200/- per day for 5 days 

· Exposure visits could be undertaken either under REMS or Project Management

· Holding of TLM Workshops of IERTs/ IEVs. This should be clubbed with the workshops given under the Project Management Head.

It is suggested that the State expends the sanctioned amount of Rs. 700.64 lakh in 9 months in 2009-10 and then submit a supplementary plan for the remaining amount of Rs. 140.13 lakh to the MHRD.

Tasks Ahead: The State should-
· Continue conducting the State/ district level workshops in IE

· Immediately appoint the remaining 22 resource teachers, 970 volunteers and 1 additional good state IE technical person for IE. Details given at Annex- 

· Include the barrier free, evaluation guidelines and thee assessment guidelines circulated to all the States as a part of their teacher training programmes.

(VI) Innovative Activities
a. Early Childhood Care and Education (ECCE)
Progress in 2008-09:

The State was allocated an amount of Rs. 300.00 lakh for 20 districts in 2008-09 for carrying out activities under ECCE and the State incurred an expenditure of Rs. 298.497 lakh.

	District Name
	Total ECCE Centres
	No. of children enrolled (3-4) years
	No. of children enrolled (4-5) years
	Total children enrolled

	
	
	B
	G
	B
	G
	

	Amritsar
	51
	323
	284
	405
	390
	1402

	Barnala
	20
	132
	170
	128
	117
	547

	Bathinda
	77
	592
	622
	738
	711
	2663

	Fatehgarh Sahib
	67
	469
	390
	364
	313
	1536

	Faridkot
	88
	575
	586
	502
	565
	2228

	Ferozepur
	79
	631
	584
	626
	656
	2497

	Gurdaspur
	98
	646
	602
	607
	604
	2459

	Hoshiarpur
	99
	649
	604
	447
	388
	2088

	Jalandhar
	62
	377
	380
	319
	310
	1386

	Kapurthala
	93
	727
	685
	470
	460
	2342

	Ludhiana
	70
	442
	470
	533
	488
	1933

	Mansa
	89
	679
	643
	697
	612
	2631

	Mohali
	20
	138
	139
	136
	123
	536

	Moga
	77
	372
	376
	601
	584
	1933

	Muktsar
	87
	767
	705
	705
	660
	2837

	Nawanshahr
	65
	445
	374
	275
	282
	1376

	Patiala
	53
	363
	381
	339
	327
	1410

	Ropar
	42
	256
	224
	228
	234
	942

	Sangrur
	61
	452
	468
	367
	368
	1655

	Tarn Taran
	37
	214
	200
	362
	321
	1097

	Total
	1335
	9249
	8887
	8849
	8513
	35498


Activities carried under ECCE during 2008-09: 

(Rs. in lakhs)
	SNo.
	Activity
	Budget 
	Expenditure

	1
	Honorarium to ECCE workers
	191.00
	191.000

	2
	Training to ECCE workers
	3.00
	2.235

	3
	Learning Kits to ECCE centres
	41.50
	41.396

	4
	Play material to ECCE centres
	53.50
	53.143

	5
	Early Intervention strategies
	11.00
	10.723

	 Total
	300.00
	298.497


Proposal for 2009-10:

The State informed the appraisal team that as per the convergence instructions issued by the state Education Department in concurrence with the ICDS Department, all the ECCE centres will be handed over to the Ministry of Women and Child Development to promote pre-school education. Hence the existing Anganwadi centres (19656) under ICDS programme and ECCE centres (1335) established under SSA, will jointly (20984) be looked after Ministry of Women and Child Development. ICDS programme will provide honoraria for pre-school teacher, training of Aanganwadi Sevikas for pre-school learning, monitoring and supervision of pre-school centres etc. Only augmentation of pre-school kits/materials to all these pre-school 20984 centres will be supported from SSA funds.

	SNo.
	District
	No. of Anganwari Centres
	No. of ECCE Centres (as on 28.02.09)
	Total AWCs on 1.04.09

	1
	Amritsar
	1400
	51
	1451

	2
	Barnala
	425
	20
	445

	3
	Bathinda
	900
	77
	977

	4
	Faridkot
	425
	88
	513

	5
	Fatehgarh Sahib
	508
	67
	575

	6
	Ferozepur
	1037
	79
	1110

	7
	Gurdaspur
	1939
	98
	2039

	8
	Hoshiarpur
	1546
	99
	1645

	9
	Jalandhar
	1549
	62
	1606

	10
	Kapurthala
	723
	93
	818

	11
	Ludhiana
	1855
	70
	1925

	12
	Mansa
	571
	89
	660

	13
	Moga
	745
	77
	822

	14
	Mohali
	493
	20
	513

	15
	Mukatsar
	725
	87
	812

	16
	Nawanshahar
	622
	65
	687

	17
	Patiala
	1389
	53
	1442

	18
	Ropar
	637
	42
	679

	19
	Sangrur
	1183
	61
	1244

	20
	Tarn Taran
	984
	37
	1021

	Total
	19656
	1335
	20984


Activities for 2009-10: 
 (Rs. in lakh)
	SNo.
	Activity proposed
	Physical
	Unit cost
	Financial

	1
	TLM for Anganwaris
	20984
	0.0075
	157.34

	2
	Play material for Anganwaris
	20984
	0.0045
	94.40

	3
	Tat patties for Anganwaris
	20984
	0.0023
	48.26

	 Total
	300.00


Recommendation: State’s proposal is recommended for approval
b. Girl’s Education

Progress in 2008-09:

The State was allocated an amount of Rs. 300.00 lakh for 20 districts in 2008-09 for carrying out activities under girl’s education and the State incurred an expenditure of Rs. 260.00 lakh.

(Rs. in lakh)
	SNo.
	Activity
	Budget
	Expenditure

	1
	Workshop of Master Trainers & other Trainees toward Capacity building on girl’s education & component of SSA/State schemes. 
	10.00
	10.00

	2
	Activating Meena Manch in the schools and thereby sensitizing PTM (Parent Teacher Manch) through it community leaders
	30.00
	30.00

	3
	Teaching of Life Skills/Vocational Skills (Yoga)
	120.00
	120.00

	4
	Exposure Visits and experience sharing:

· Exposure visits in selected100 schools in a District.

· Heterogeneous grouping of girls and taking them to the adjoining areas/ cities.

Visits to areas like railway stations, airports, banks, industries, printing press, colleges, universities, museums, amusement parks, gardens.
	100.00
	100.00

	5
	Awards to top 3 girls students of each class in each block.
	40.00
	-

	Total

	300.00
	260.00


Proposal for 2009-10:

The State has proposed an amount of Rs. 300 lakh for all the 20 districts, detailed activities of which are given below:

(Rs. in lakh)
	SNo.
	Activity
	Physical 
	Unit Cost 
	Fin

	1
	Workshop of Master Trainers & other Trainees toward Capacity building on girls education 
	20 districts all schools
	Rs. 5000/-
	10.00

	2
	Activating Meena Manch in the schools and thereby sensitizing PTM (Parent Teacher Manch) through it
	100 upper primary schools
	Rs 1500/- per school per district
	30.00

	3
	Teaching of Life Skills/Vocational Skills 
	100 upper primary schools
	Rs. 6000/- per school per district
	120.00

	4
	Exposure Visits and experience sharing: 

· Exposure visits in selected 100 schools in a District.
·  Heterogeneous Grouping of girls and taking them to the adjoining areas/ cities.
	50 primary schools and 50 upper primary schools
	Rs. 5000/- Per school per district
	100.00

	5
	Awards to top 3 girls students of each class in each block. 
	20 districts all school
	Rs.2.00  Lakh Per district
	40.00

	Total
	300.00


Recommendation: State’s proposal is recommended for approval 

c. SC/ST

Progress in 2008-09:

The State was allocated an amount of Rs. 188.00 lakh for 20 districts in 2008-09 for carrying out activities under SC/ST and the State incurred an expenditure of Rs. 130.89 lakh.

No. of beneficiaries: 63,938 (SC girls of classes 6th to 8th class)


(Rs. in lakh)
	Name of the Activity
	Budget
	Expenditure

	Continuation of vocational education (knitting, stitching and embroidery) for SC girls of Upper primary level through 1880 vocational education centres @ Rs. 9.40 lakh per district Training 
	188.00


	130.89



	 Total
	188.00
	130.89


Proposal for 2009-10

	SNo.
	District Name
	No. of Vocational centres
	No. of girl beneficiaries

	1
	Amritsar
	67
	2802

	2
	Barnala
	25
	1027

	3
	Bathinda
	100
	3625

	4
	Faridkot
	137
	4586

	5
	Fategarh Sahib
	134
	3572

	6
	Ferozepur
	100
	3762

	7
	Gurdaspur
	157
	4615

	8
	Hoshiarpur
	100
	3452

	9
	Jallandhar
	100
	4696

	10
	Kapurthala
	103
	3146

	11
	Ludhiana
	33
	1328

	12
	Mansa
	100
	3005

	13
	Moga
	100
	3752

	14
	Mohali
	44
	1344

	15
	Muktsar
	130
	4359

	16
	Nawanshahr
	136
	4595

	17
	Patiala
	87
	2761

	18
	Ropar
	65
	1655

	19
	Sangrur
	75
	2502

	20
	Tarn Taran
	33
	938

	Total
	1826
	61,522


Proposal for 2009-10:

The State has proposed an amount of Rs. 300 lakh for 20 districts, the detailed activities of which is given below:

(Rs. in lakh)

	SNo.
	Activity
	Unit Cost
	Phy
	Fin

	1
	Continuation of vocational centers:

a) Honorarium for 9 months

b) Raw material for vocational centers

c) Maintenance of machines
	Rs. 1000 per month per volunteer

Rs. 1000 per center 

Rs. 1000 per center 
	1826

1826

1826
	164.34

18.26

18.26

	2
	Preparation of questions papers and conduction of tests for SC girls of classes V,VI,VII and VIII
	Rs. 1300 per district
	20
	0.26

	3
	Awards to three toppers of classes V, VI, VII and VIII at every block.

1st position: Rs. 2000/-

2nd position: Rs.1500/-

3rd position: Rs.1000/-
	Rs. 18000 per block
	216
	38.88

	4
	Exposure visits for SC children in SC concentrated schools.
	Rs. 4000 per school
	75 schools per district
	60.00

	Total
	300.00


Recommendation: State’s proposal is recommended for approval
Observation:

The appraisal team observes that the State has proposed activities under Girl’s education and SC/ST in continuum of the activities proposed in the previous year. It is therefore suggested that the State should plan and evolve different and target specific activities under innovations for these heads in the coming years, in order to address the needs of these focus group children more significantly. 

d. Computer Aided Learning 

Programme  started


:
2004 - 05

1. Mode of implementation

:
BOOT/ Exercised by the state

2. Achievement before 2008 - 09



a. Schools covered

:
2000


b. Students benefited

:
926606


c. Teachers trained

:
13164


d. Systems provided

:
11904


e. Content CDs available

	Subject
	Class

	· Multimedia educational content CDs on curriculum based hard spots in Mathematics, English, Science & Social Science for class VI to VIII developed in collaboration Educomp, IL&FS, JaypeeIT &  HCL

· 51 CDs of  Mathematics, English & Science procured from APF, Microsoft & IGNOU
	VI to VIII


3. Progress during 2008-09

a. Physical Progress-

	PAB Approval

(Schools to cover)
	Achievement 

As on 31st Jan 09
	% Achievement

	300
	300
	100%


b. Financial Progress -

	PAB Approval
	Achievement 

As on 31st Jan 09
	% Achievement

	1000
	875.00
	87.5%


Expenditure as on date – 1000.00 lakh

c. Number of Beneficiaries
:357108

d. Activities in 2008 – 09 (Row 1 to 4 Fresh Activities, Row 5 Recurring Activities)

	SNo.
	Activities
	Details
	Achievement

	
	
	
	Phy
	Fin

	1.
	Infrastructure 

· IT Infrastructure (PC, Printers, IT peripherals)

· Non IT Infrastructure (Ceiling, Flooring, Electrification, Computer Table, Chair)
	Each UP school provided with five computers under BOOT model (i.e. one Server computer and four Desktop Computers), 2 KVA UPS, Printer, Stablizer and networking  devices @ Rs.2.49 lacs to be paid in two years i.e., 1.245 lacs per year

Furnishing of computer lab @ Rs. 0.555 lacs


	300

300
	373.50

166.50



	2.
	Teacher Training under CAL
	Teacher Training in collaboration of Microsoft and Intel
	4609


	Nil

	3.
	Content/ Software Development


	Development and supply of multimedia content for class VI to VII in Punjabi language on the Punjab Government syllabus for the subject of Science, Mathematics and English in collaboration with Punjab EDUSAT Society. (The estimates as mentioned is based on the cost of similar work got done by state of Gujrat.)
	139 Modules
	125.00

	4.
	Recurring Activities

· Maintenance of Infrastructure

· Refresher Training to Teachers
	Annual Maintenance Contract for the existing computer labs in 2000 schools @ 5% of the cost of hardware installed therein (Total cost of hardware installed in 2000 schools is approx 6000 lacs.) The estimate also includes upkeep of electrification and furniture provided in 2000 labs.

Imparted by Microsoft and Intel
	2000 Schools

Nil
	335.00

Nil



	Total
	1000.00


4.  Proposal for 2009-10:

a. Physical -

· No. of schools/centres to be covered during 2009-10:
2500

· No. of beneficiaries to be covered under CAL: 

357108 
b. Detailed Activity Wise break up for 2009-10 - (Row 1 to 4 Fresh Activities, Row 5 Recurring Activities)

	SNo.
	Activities
	Details
	Achievement

	
	
	
	Phy
	Fin

	1.
	Infrastructure
	Nil
	Nil
	Nil

	2.
	Teacher Training under CAL
	Training by Microsoft and Intel
	Nil
	Nil

	3.
	Content/ Software Development
	
	Nil
	Nil

	4.
	Recurring Activities

· Maintenance of Infrastructure

· Support for Additional Infrastructure 
	Annual maintenance contract for the existing computer labs in 2500 schools @ nominal 5% of the cost of hardware installed therein (Total cost of hardware installed in 2500 schools is approx 75 crores.) although the market rate of contract for maintenance varies from 8 to 10 % for desktop computers/printers and approx 20% for the UPS and voltage stabilizer but we have taken 5% rate as the subsidized cost. The estimate also includes upkeep of electrification and furniture provided in 2500 labs.

Additional multimedia equipment & hardware for the schools where CAL labs already exist in the boot model for 3 years as follows:-

LCD TVs 42” @ 0.6 lacs per unit cost for 1 year Rs.600.00 /3=Rs.200 lacs

DVD players @ Rs.0.075 lacs per unit cost for 1 year Rs.75.00/3 = Rs.25 lacs

Integrated Computer cum Projectors @ Rs.1 Lac per unit 

cost for 1 year  Rs.1200.00/3 = Rs.400 lacs
	2500

1000

1000

1200


	375.00

200.00

25.00

400.00

	Total
	1000.00


5. Time Frame

	
	Activity

	April 2009


	Training by Microsoft and Intel
	Maintenance by HCL / GCL
	Tendering for LCD TVs & DVD players and Integrated Computers cum Projectors

	May


	Training by Microsoft and Intel
	Maintenance by HCL / GCL
	Tendering for LCD TVs & DVD players and Integrated Computers cum Projectors

	June
	Training by Microsoft and Intel
	Maintenance by HCL / GCL
	Installation of Multimedia equipments

	July



	Training by Microsoft and Intel
	Maintenance by HCL / GCL
	Installation of Multimedia equipments

	August


	Training by Microsoft and Intel
	Maintenance by HCL / GCL
	Operation of  equipments to show multimedia content to children

	September


	Training by Microsoft and Intel
	Maintenance by HCL / GCL
	Operation of  equipments to show multimedia content to children

	October


	Training by Microsoft and Intel
	Maintenance by HCL / GCL
	Operation of  equipments to show multimedia content to children

	November


	Training by Microsoft and Intel
	Maintenance by HCL / GCL
	Operation of  equipments to show multimedia content to children

	December


	Training by Microsoft and Intel
	Maintenance by HCL / GCL
	Operation of  equipments to show multimedia content to children

	January 2010
	Training by Microsoft and Intel
	Maintenance by HCL / GCL
	Operation of  equipments to show multimedia content to children

	February


	Training by Microsoft and Intel
	Maintenance by HCL / GCL
	Operation of  equipments to show multimedia content to children

	March
	Training by Microsoft and Intel
	Maintenance by HCL / GCL
	Operation of  equipments to show multimedia content to children


6. Progress & Proposal:


Computer Aided Learning had been operational in the STATE since 2004 – 05 and by 2007 – 08 the state had expanded the programme up to 2000 schools benefitting a total of 926606 students. The state have a strength of 13164 trained teachers on use of CAL resources. 

In 2008 – 09 the progress of the state is as follows,

1. CAL has been provided to 300 schools under BOOT model in collaboration with HCL benefitting a total of 357108 students. 

2. 4609 teachers have been trained under CAL on effective use of CAL resources in classroom transaction process.

3. IT infrastructures @ one Server computer and four Desktop Computers), 2 KVA UPS, Printer, Stabilizer and networking devices have been provided to the 300 schools. Furnishing of the computer labs also have been done in all 300 schools. 

4. e – Teaching Learning materials in science, mathematics & English for class VI to VII in Punjabi language on the Punjab syllabus are in the process of development in collaboration with Punjab EDUSAT Society & will be supplied to each school.

5. The students of class VI to VIII are using educational content CDs on identified hard spots from the regular curriculum. The students also undertake certain projects from their curriculum to effectively use the CAL resources. The teachers are using the CAL resources for effective teaching learning process.

6. The annual maintenance contacts of the computer labs in 2000 schools have been done.

In 2009 – 10, the proposed activities are, 

1. Provide additional multimedia equipment & hardware to the schools where CAL labs already exist in the boot model for 3 years as follows:-

a. A unit of 42” LCD TV & DVD player to 1000 schools @ Rs.0.675 lacs.

b. Integrated Computer cum Projectors @ Rs.1.00 Lac to another 1200 schools.

c. Undertake Annual maintenance contract for the existing computer labs in 2500 schools @ nominal 5% of the cost of hardware installed therein (Total cost of hardware installed in 2500 schools is approx 75 crores.)

7. Observations:


The followings are the representations of state regarding expansion of CAL activities in 2009 – 10. 

a. Besides Computer Aided Learning activity under SSA, the state government has also provided computers & computer labs to schools. 

b. As a result of the above almost all the schools have computer labs which are simultaneously used for computer aided learning where CAL has been undertaken.

c. As there are no schools further to be undertaken with CAL, the following two types of additional equipments to schools to be provided, which are to be used as teacher’s tool during the classroom transaction process.

i. A unit of 42” LCD TV & DVD player to 1000 schools @ Rs.0.675 lacs.

ii. Integrated Computer cum Projectors to 1200 schools @ Rs.1.00 lacs.

d. The state is of view that the impact of two different types of systems may be experimented.

8. Recommendation:

While the state’s representation is that, all the schools have been undertaken with CAL, data from district plans reveal that there are many schools where CAL has not been undertaken yet. 

Coverage of CAL in UP schools as found in district plans in some randomly taken districts are as given below.

i. Amritsar – 76 out of 346

ii. Faridkot – 71 out of 154

iii. Gurdaspur – 184 out of 478

iv. Roopnagar – 79 out of 178

v. Sangrur – 138 out of 349

(On the basis of these district plans, it gives an impression that that the representation on saturation of schools regarding CAL may not be factual. As with these five districts the no. of uncovered schools becomes 957 & it may be more if all the districts are taken into account. The Computer Aided Learning activity is basically meant for the students and priority should be given more to provide interactive systems of joyful learning to students on the hard spots from their curriculum with the help of computers and multimedia content CDs.)

Besides the proposal for maintenance of the IT equipments, the appraisal team recommends the proposed activity of the state to provide multimedia equipments to be used as teacher’s aid for augmented teaching learning processes. However the state should find out more cost effective solutions instead of integrated computer cum projectors for the proposed activities which will enable the state to expand computer aided learning to more number of schools. It is highly suggested that, priority should be given to provide CAL to maximum number of schools benefitting maximum students. 

(VII) Girls Education
a. National Programme for Education of Girls at Elementary Level (NPEGEL) 
National Programme for Education of Girls at Elementary Level (NPEGEL) programme is being implemented in 02 EBBs and 08 clusters of 01 District. 

Physical Progress during 2008-09:

(Rs. in lakh)

	SNo.
	Activities
	No. of MCS
	Unit Cost
	No. of girls Covered
	Financial Achievement

	1
	Maintenance of school

· Part time instructors for MCS for imparting training to the girls in the vocational trades like cutting, embroidery, tailoring, paining, flower making and also for music and shabd gyan etc. To enhance the retention of girls in school system.

· Bicycle was provided to class 6th girls.

· Uniforms were given to BPL girls.
	8
	0.20
	1400
	1.40

	2
	Award to Best teacher/ schools – 8 awards to the best performance for promoting girls education, ensuring their enrollment and retention for school in each block. Besides 8 awards for the best teachers one for each cluster.
	8
	0.05
	48 schools and teachers covered
	0.13578

	3
	Remedial coaching was imparted to girls to enhance their achievement levels in Mathematic, English and Science.
	8
	0.20
	1400
	0.42

	4
	Learning through open school/ payment of examination fee for girls – Examination fee was reimbursed to the girls of class 8th.
	8
	0.50
	550
	0.218

	5
	Teacher training- was imparted to sensitize teacher towards gender and girls; health specific issues. 
	8
	0.04
	120
	0.11005

	6
	Community mobilization – Seminars were organized to generate awareness against female foeticide. 
	8
	-
	-
	0.306

	
	Total
	8
	0.60
	1600
	2.58983


Financial progress:


                   (Rs. in lakh)

	Year
	Out lay approved
	Total Fund Available
	Expenditure
	% of Expenditure against Outlay Approved

	2004-05
	82.73
	NA
	16.10
	19.46

	2005-06
	60.00
	NA
	9.00
	15.00

	2006-07
	5.10
	NA
	9.00
	176.47

	2007-08
	4.80
	NA
	3.00
	62.50

	2008-09
	5.106
	NA
	4.80
	94.01

	Total
	157.736
	-
	41.90
	26.56


During the year 2008-09, the State was sanctioned a budget of Rs. 5.106 lakh. The achievement is Rs. 4.80 lakh (94%).
Activity Proposed for 2009-10:












(Rs. in lakh)

	SNo.
	Activities
	No. of MCS
	Unit Cost
	Financial Proposal
	Total girls to be covered 

	1
	Maintenance of school

· Part time instructors for MCS for imparting training to the girls in the vocational trades like cutting, embroidery, tailoring, paining, flower making and also for music and shabd gyan etc. To enhance the retention of girls in school system.

· Bicycle was provided to class 6th girls.

· Uniforms were given to BPL girls.
	8
	0.20
	1.600
	1600

	2
	Award to Best teacher/ schools – 8 awards to the best performance for promoting girls education, ensuring their enrollment and retention for school in each block. Besides 8 awards for the best teachers one for each cluster.
	8
	0.05
	0.400
	48 Schools



	3
	Remedial coaching was imparted to girls to enhance their achievement levels in Mathematic, English and Science.
	8
	0.20
	1.600
	1600

	4
	Learning through open school/ payment of examination fee for girls – Examination fee was reimbursed to the girls of class 8th.
	8
	0.50
	0.400
	800

	5
	Teacher training- was imparted to sensitize teacher towards gender and girls; health specific issues. 
	8
	0.04
	0.320
	200

	6
	Additional Incentives
	8
	0.480
	0.480
	800

	7
	Community mobilization – Seminars were organized to generate awareness against female foeticide. 
	8
	-
	0.306
	In all clusters

	
	Total
	8
	
	5.106
	1600


The State has proposed an amount of Rs. 5.106 lakh for 8 clusters of 2 blocks level activities for 2009-10.

Recommendation: The Appraisal Team recommends an amount of Rs. 5.09 lakh for 2 blocks including 8 clusters. Out of it, Rs. 0.29 lakh is for management cost.
b. Kasturba Gandhi Balika Vidyalaya (KGBV) 

Under the scheme of Kasturba Gandhi Balika Vidyalaya (KGBV), residential schools at upper primary level (Class VI to VIII) are set up for out of school girls predominantly belonging to SC, ST, OBC and minority communities in educationally backward blocks of the country. 

Status of KGBV

	Model
	No. of KGBVs sanctioned
	No. of KGBVs operational
	No. of girls enrolled

	
	
	
	SC
	ST
	OBC
	BPL
	Min
	Total

	III
	03
	03
	68
	0
	20
	0
	12
	100


Observations:

· All the sanctioned 03 KGBVs are made operational under Model-III. Comprising 66.66% of the targeted enrollment.

· All KGBVs run by SSA Society.

· Out of 03 KGBV sanctioned having over 20% population in Muslim 01 and 02 are in SC dominated blocks.

· Enrollment Status in Muslim is 24% and SC is 47%.

· Out of 03 KGBVs buildings, 2 buildings are completed and 1 is under progress.

Financial Progress:
	SNo.
	Year
	Outlay Approved
	Total Fund Available
	Expenditure till January, 2009
	% of Expenditure against Outlay Approved
	% of Expenditure against Total Fund Available

	1
	2004-05
	43.40
	32.55
	0.00
	0.00%
	0.00%

	2
	2005-06
	0.00
	43.84
	21.23
	0.00%
	48.43%

	3
	2006-07
	0.00
	15.45
	16.04
	0.00%
	103.82%

	4
	2007-08
	15.04
	20.81
	8.38
	55.72%
	40.27%

	5
	2008-09
	70.02
	5.80
	45.90
	65.55%
	791.38%

	
	Total
	128.46
	118.45
	91.55
	71.27%
	77.29%


Above table reflects low expenditure incurred by the State. During the year 2008-09, the State was sanctioned a budget of Rs. 70.02 lakh. The achievement is Rs. 45.90 lakh (65.5 %) up to January, 2009.

Proposal for 2009-10:

(Rs. in lakh)
	SNo.
	Activity
	Physical
	Unit Cost
	Financial 

	
	Non-Recurring Cost**
	
	
	

	1
	Construction of Building(additional cost for KGBV at Sangrur)
	1
	12.50
	12.50

	2
	Boundary Wall for 2 hostels(for one of Sangrur and one of Ferozpur)
	2
	a)1.0 for Sangrur

b)3.0 for Ferozpur
	4.00

	3
	Furniture/ Equipment including Kitchen Equipment (for Sangrur)
	1
	2.50
	2.50

	4
	Bedding (for Sangrur)
	1
	0.50
	0.50

	
	TOTAL (A)
	
	
	19.50

	
	Recurring Cost
	
	
	

	5
	Maintenance per girl @ Rs 750 per month
	3
	4.50
	13.50

	6
	Stipend for girl student @ Rs 50 per month
	3
	0.30
	0.90

	7
	TLM, Stationery
	3
	0.30
	0.90

	8
	Examination fee
	3
	0.01
	0.03

	9
	Salaries
	3
	3.60
	10.80

	10
	Vocational Training
	3
	0.30
	0.90

	11
	Electricity/Water Charges
	3
	0.36
	1.08

	12
	Medical care @ Rs 750/- child
	3
	0.38
	1.14

	13
	Maintenance
	3
	0.20
	0.60

	14
	Miscellaneous 
	3
	0.20
	0.60

	15
	Preparatory Camps
	3
	0.10
	0.30

	16
	PTAs/School functions
	3
	0.10
	0.30

	17
	Capacity Building
	3
	0.30
	0.90

	
	TOTAL (B)
	3
	10.65
	31.95

	
	GRAND TOTAL=A+B
	
	
	51.45


· The State has required addition cost for the foundation of the building as it has gone down by 10-11 ft. because of soft land at the construction site. 

· The State has proposed a total amount of Rs. 51.45 lakh 
Recommendation for 2009-10:

· The Appraisal Team did not recommend additional amount for additional construction of boundary wall for 2 hostel, furniture equipment and bedding cost amounting to Rs. 19.50 lakh because it does not qualify KGBVs financial norms.

· The appraisal team recommended recurring grant of Rs. 39.15 lakh.

Issue/s:

· Capacity of KGBVs not fully utilized.

(VIII) Research, Evaluation, Monitoring and Supervision:
PAB approved an outlay of Rs. 243.217 lakh under REMS at a unit cost of Rs.1300/- per school for 18709 schools during 2008-09. Expenditure under REMS till January, 2009 has been 66.53 lakh. However a large number of payments are to be done during February and March. So, it is anticipated that almost 100% expenditure will be incurred under this component.

The research studies for all the districts were done uniformly in a centralized fashion. Activities carried out under REMS during the year are given below:- 

Progress during 2008-09: 
3. Study on Teacher Student Absenteeism for primary and upper primary schools was done by Punjab University, Patiala.  The study was initiated during 2007-08 and was completed by the first half of 2008-09. As per the report of the study, student absenteeism at primary level has been 15% in the rural schools and 20% in the urban schools. The student absenteeism at upper primary level has been reported to be 9% in rural and urban schools. Overall teacher absenteeism has been reported to be 18%. In case of primary teachers it has been 24% and in case of upper primary teachers it has been 13%.

4. Study on Assessment of Status of Schools with respect to blackboards, toilets and drinking water facility was done by SCERT, Punjab during 2008-09. The report is still awaited. 

5. Study on Impact of Remedial Coaching was got done for upper primary schools through SCERT, Punjab. 

6. Study on Classroom Transaction in primary and upper primary schools is presently under way. It is being carried out by Punjabi University, Patiala and will be completed by May, 2009. 

7. Baselines for identification of learning levels of primary class children were done under Parrho Punjab Programme. The findings revealed that 23.3 children in standard-I could only read letters, 25% children in standard-III could read paras and 46% children of standard-V could read stories. 


So far as numerical skills were concerned, 14.6% children of standard-I could recognize numbers, 18% children of standard-III could perform subtraction and 29% children could perform division. 

8. Data on different infrastructural and educational items was collected for every primary and upper primary school for DISE. 3rd Party Evaluation for DISE was also done. Compilation and analysis of the DISE data was done at State Head Quarter. The reports generated on various data items have been utilized for the formulation of Annual Work Plan for SSA, 2009-10. 

9. Supervision & Monitoring for Classroom Transactions and Learning Enhancement Programmes was done by the Divisional Supervisory Groups, District Science Supervisors, Asst. District Science and Maths supervisors, District level Monitoring Cell both for primary and secondary education and the State Project Officers on regular basis. 

10. Regular Monitoring & Supervision of the Schools was being carried out by Block & Cluster Resource Persons and the same is reviewed on monthly basis at district level.

11. System of evaluation for tracking the improvement in learning levels for primary as well as upper primary level was institutionalized by way of monthly tests.

12. Mid term evaluation of the learning achievements of primary children was done as part of Parrho Punjab Programme. The evaluation was carried out by the Block Master Trainers during November, 2008 which showed a significant improvement in the learning levels of the children. For example:   Number of letter readers of class-I has increased by 19.5 PP, number of para readers of class-III has increased by 8% and that of story readers of class-V has increased by 13%. The mathematical skills, of the children of standard-I, who could recognize numbers has increased by 5%, number of students of standard-III who could perform subtraction increased by 8% and the number of students of standard-V who could perform division increased by 12%.

13. Supervision and monitoring of the educational programmes and the classroom transactions was done by state project officials, district project officials, divisional monitoring teams, District Science Supervisors, BRPs and CRPs.

14. The process of monitoring was further strengthened by taking services of four retired but experienced officials of Education Dept., one each at Divisional Level as consultants. 

Proposal 2009-10:

The State has proposed an amount of Rs. 262.39 lakh for 20184 Primary/Upper Primary Schools @ of Rs. 1300/- per school.

The break up of REMS proposed for 2009-10 is as follows:-

	
	State Level

@ Rs. 300/- per school
	District Level

@ Rs. 1000/-  per school
	Total Proposed Funds

	Research & Evaluation
	Rs. 20.184 lakh @ Rs  100/- per school
	Rs. 181.66 lakh @ Rs 900/- per school
	Rs. 201.84 lakh

	Monitoring & Supervision
	Rs. 40.368 lakh @ Rs. 200/- per school
	Rs. 20.184 lakh @ Rs 100/- per school
	Rs. 60.552 lakh


Following activities are proposed in 2009-10 under REMS:





(Rs. in lakh)

	State Level activities

	SNo.
	Activity
	Financial

	1
	Research & Evaluation
	

	1.1
	Research study on classroom transaction 
	4.80

	1.2
	Baseline Studies to evaluate initial learning levels of children
	10.384

	1.3
	Evaluation of Parrho Punjab programme
	5.00

	Subtotal
	20.184

	2
	Supervision & Monitoring
	

	2.1
	Monitoring and supervision of schools
	40.368

	Subtotal
	40.368

	Total
	60.552

	District Level activities

	SNo.
	Activity
	Financial

	1
	Research & Evaluation
	

	1.1
	Continues comprehensive evaluation of learning levels of children of primary and upper primary classes.

· Extra Teaching

· Special Teaching

· Monthly Test

· Quarterly Test

· Competitive Test 

· Final Evaluation
	181.66



	2
	Supervision & Monitoring
	

	2.1
	Monitoring and supervision of schools
	20.184

	Total
	201.844

	Grand Total
	262.396


Recommendation: State’s proposal is recommended for approval
(IX) Community Mobilization 
Progress in 2008-09:

	PAB Approval (2008-09)
	Achievement (upto 31st Jan,09) 
	Percentage %

	Phy
	Fin
	Phy
	Fin
	Phy
	Fin

	98954
	59.372
	98512
	59.102
	99.55
	99.54


Major Activities Conducted During 2008-09

· The state has put lot of efforts in 2008-09 in systematically mobilizing the communities. Decentralization of physical and financial powers upto Village Education and development committees is constantly followed as per the guidelines of SSA.

· In State of Punjab VEDCs trainings for the year 2008-09 were organized from 30th October 2008 till Mid December. As reported by the state the community trainings were provided by Block Resource Persons at the school level. Meena CDs were shown during these trainings. Tremendous response was received. VEDCs were trained on different educational and civil works matters with the use of Training  modules namely Paswak de Kamman Kajan lai Nem, Tips for construction (Nirman Sabandhi Sujhao), Architectural & Structural Drawings for Civil Works under SSA, Paswak Agwai and the booklet on  Parrho Punjab Programme etc. 

· It was also observed that the VEDC members were adequately motivated to carry out quality civil works in the schools, to monitor the quality of education as well as promote the education of girls, SCs and children with special needs in the villages. They were familiarized with the schemes of Alternative Innovative Education, Residential Bridge Course and Inclusive Education for Disabled children etc.  They were encouraged to bring all out of school children in the school system. 

· Publicity Campaign to mainstream Out of School Children was organized and 100% enrollment was achieved:  Public Campaign was carried out in all the Districts of Punjab by using CDs, Leaflets, Banners and Posters etc. The Campaign was carried out in 2 Phases   (i) by DEO (EE) and DEO (SE). 

· A Radio Classroom Programme based on subject contents as well as general issues of life was broadcasted for the school children of Classes I-V. The programme was broadcasted from 4 channels of All India Radio. The program received an overwhelming response from the community. 
· State has established clear linkages of VEDCs with PRI institutions. Every VEDC has 2 panch members in the committee. All the PRI members and community leaders work in close tandem with each other to implement the SSA programme and to supervise all the activities.VEDC  in coordination with the panch members are actively involved in decision making for the school matters for carrying out civil works, appointment of  education volunteers for the schools and AIE centers, procurement of material for the schools and monitoring of classroom transactions and keeping a close watch on the regularity of teachers and students

Proposal for 2009-10:

Community Training

	Target 2009-10

	Phy
	Fin

	99060
	59.436


All the activities as undertaken during 2008-09  for training the community on covering Out of school children, encouraging education of girls/SCs, education of CWSN and carrying out civil works activities etc. would be carried out during 2009-10.

Highlights of the proposal for community mobilization for 2009-10:
1. Training Material / Modules will be prepared at state level. 

2. Community training will be done at school level.

3. All the block resource persons and cluster resource persons will be oriented by state and district level officials to under take the training session for community in the schools so as to meet the objectives of the programme.

4. Community leaders will be familiarized with the plan of action for schools for 2009-10.

5. They will be made aware of the education programme like remedial coaching, parrho Punjab, non residential bridge course, residential bridge course, exposure visits and awards for SC children and girls & radio class programme.

6. They will be sensitized for social and gender equality.

7. They will be called upon to locate and admit all out of school & special children in schools in village.

8. Radio broad cast on academic issues, moral issues, child behavior pattern and adult education etc.

9. SSA publicity campaign for villagers with the use of audio visual CDs and projectors.

Time Schedule for community mobilization activities:
1. Preparation of training modules for community

- April, 2009 

2. Two days training for community members at school level 
- May, 2009
3. SSA publicity campaign 




- April-May-July-August 2009

4. Radio broadcast 





- July-August-September 2009

5. Identification of OOSC and CWSN. 



- Throughout the year

Observation: 

The progress in community training during 2008-09 is appreciable. Community members were trained on various issues like educational and civil works matters with the use of Training modules namely Paswak de Kamman Kajan lai Nem, Paswak Agwai and the booklet on  Parrho Punjab Programme. 
State should develop Community Training Modules focusing more on the quality aspects like learning outcomes of students, classroom teaching and learning processes, community school linkages, parent’s participation in Academic activities of school etc. 
State has given the details about the programmes be organized under community mobilization with clear time frames.
State has not reported clearly about the Topics of the community training programme and the expected outcomes of the trainings.
Recommendation: State’s proposal is recommended for approval. 
(X) Involvement of NGO

GIAC meeting was held thrice during 2008-09 (19th May’08, 25th June’08 and 22nd October’08).



Table: Status of NGO Involvement

	Functional Area
	No. of NGOs involved during 2008-09
	No. of NGOs likely to be involved during 2009-10

	1. IED
	69
	69

	2. AIE/AS interventions
	21
	Depends on the interest and response of the NGOs 

	Total
	90
	


 (XI) Project Management 

The State has provided following information regarding staffing at different levels.

Staff Position

	Office
	Staff sanctioned
	Staff filled

	SPO
	72
	72

	DPO
	670
	670


Source: AWP & B, SSA, Punjab 2009 – 10

The State has provided information about the posts in the State Office as indicated in the following table.

Positions in State Office

	SNo.
	Designation
	No. of Posts

	1.
	State Project Director
	1

	2.
	Deputy State Project Director
	2

	3.
	ASPD
	4

	4.
	Section Officer
	1

	5.
	Cashier
	1

	
	Contractual staff
	

	1.
	Deputy Manager
	7

	2.
	Chief controller of Account
	1

	3.
	Deputy Director Planning
	1

	4.
	XEN(Civil works)
	1

	5.
	Assistant Manager
	15

	6.
	Asst. Manager (Internal Audit)
	2

	7.
	Accountant
	5

	8.
	Accountant (Internal Audit)
	4

	9.
	Comp. Programmer
	2

	10.
	Stenographer
	7

	11.
	Data Entry Operator
	18


Source: AWP & B, SSA, Punjab 2009 – 10

Similarly the State has provided information about the posts in the District Offices as indicated in the following table.

Positions in District Offices

	DPO
	Positions
	No of Posts

	1.
	Assistant project Coordinator (G)
	20

	2.
	Assistant project Coordinator (F)
	20

	3.
	Accountant 
	29

	4.
	Sub Divisional Engg.(Civil Works)
	20

	5.
	Data Entry Operator (2)
	49

	6.
	Assistant Block Coordinators
	216

	7.
	Block office Assistant
	216

	8.
	DRP
	100


Source: AWP & B, SSA, Punjab 2009 – 10

At State Level:

(Rs. in lakh)

	Intervention
	Proposal (Rs)
	Recommendation

	Salary 
	198.84
	385.32

 

	Office equipment Including Laptops, Computers and its accessories
	21.14
	

	Office Contingencies & Internal Audit  of SSA Head office , Districts , VEDC & Schools  & Telephone/Net, Water, Electricity, building rent, taxi Charges etc 
	125.00
	

	Office Furniture 
	60.00
	

	Media Activities at State Level
	414.06
	

	MIS Operation & Maintenance/Capturing DISE data
	11.00
	

	Capacity Building Workshop
	17.28
	

	Total
	847.32
	


At District Level:

(Rs. in lakh)

	Intervention
	Proposal (Rs)
	Recommendation

	Salary 
	830.20
	1133.00

	Office equipment Including Laptops, Computers and its accessories 
	916.89
	

	Office Contingencies & Internal Audit  of SSA Head office , Districts , VEDC & Schools  & Telephone/Net, Water, Electricity, building rent, taxi Charges etc 
	200.00
	

	Office Furniture 
	120.00
	

	Media Activities at State Level
	20.00
	

	MIS Operation & Maintenance/Capturing DISE data
	35.00
	

	Total
	 2122.09
	


· The proposed amount for management and MIS is recommended as per the 6% limit of management cost.

· All the 3 Directorates of Education DPI (EE), (SE) & Director SCERT at state level are regularly consulted and involved in decision making, planning and implementation of the scheme. 

5. Special Focus Districts
	District
	Weakness
	Strategies proposed by the State
	Suggestions of appraisal team for further improvement

	Bhatinda- 

SFD (D)
	· The SC literacy rate is 47.9% for male and 34.25% for female as against 67.80% general male and 53.7% for general female.

· The District has 30% SC population.

· There are 414 habitations with 412 primary schools with in 1 kilometer. The remaining two habitations are eligible for opening of a new primary school.

· There are 402 upper primary schools and there are 12 habitations without upper primary schools with in 3 kilometer. All the remaining 12 habitations are eligible for opening new upper primary schools.

· The ratio of PS to UPS in 1.5:1. 

· There are 2661 out of school children. 

· There are 16 single teacher schools.
	· The State has not specifically proposed any strategy to improve the literacy rate amongst the SC boys and girls, as no specific budget provision has been made in 2009-10.

· Though 2 habitations are eligible for opening of PS and 12 habitations are eligible for opening of UPS but State does not have any proposal of opening of new schools perhaps because PS to UPS ratio is 1.5:1.

· The State has proposed direct enrollment of 629 children in regular schools and admission of 2032 children in non-residential bridge courses in 76 centers.

· The State has not made any specific proposal for posting of more teachers in the single teacher schools even though the PTR is very comfortable.
	· State can think of providing some new incentives for bringing the SC children in the schools and retaining them till they attend the age of 14 years so that the literacy rate among them is improve significantly.

· The State has made make proposal for opening of new primary and upper primary schools to cover all the children by bringing them in regular schools. Thus all the left out habitations will be provided the schooling facility. 

· State has may provision for 2475 children in NRBC which may be restricted 2032 children.

· State should rationalize the posting of teachers as more number of teachers are available in States.

	Moga-

SFD (D)
	· The SC literacy rate in Moga is 48% for male and 35.65% for female as against 68% for general male and 58.5% for general female.

· There are 387 habitations and every habitation has a primary school. Only 383 habitations have upper primary schools with in 3 KM. The remaining 4 habitations are eligible for opening of new upper primary schools.

· There are 1143 out of school children as per house hold survey.
	· State has thought of providing vocational classes, coaching, exposure visits and arranging competitive examinations.

· State has proposed opening of 4 upper primary schools.

· State has proposed to enroll 485 children in regular schools and admit 658 children in non-residential bridge courses.
	· As the literacy rate among SC is far below the general community, some realistic steps are required to be taken by the State to motivate the SC children to complete the elementary education. State can think of mobilizing the community and extending some special benefits to SC children. 

· State has made provision for 1318 children for non-residential bridge course, which should be restricted to 658 children.

	Nawanshahar- SFD (D)
	· The SC literacy rate is 81.54% for male and 64.79% for female as against 82.9% for general male and 69.5% for general female. Though the literacy rate for general community has been given block wise but no literacy rate block wise has been given in the case of SC population.

· There are 529 habitations which are covered by 528 primary schools with in 1 kilometer. There is 1 habitation without a primary school which is also eligible for a new primary school. There are 503 UPS with in 3 kilometers, leaving 26 habitations without upper primary schools. All these habitation are eligible for new upper primary schools.

· There are 513 out of school children as per house hold survey.

· The transition rate from PS to UPS is 89.39%. 
	· No specific strategy has been disclosed by the State in their AWP&B for 2009-10 for further improving the literacy rate among the SC population.

· State has proposed to open 1 primary school and 26 upper primary schools.

· State has proposed direct enrollment of 90 children in regular schools and admission of 116 children in NRBC and 307 children in HBS/RR.

· No specific proposal has been made by the States for improving the transition rate.
	· State should collect the figures of SC literacy amongst SC block wise and make special provisions for improving the SC literacy.

· State has made the provision for opening of the schools in their project.

· State has provided for admission of 205 children in their budget. State should make provision for remaining children as well.

· State should make special provision for admission of all the primary graduates in upper primary schools so the transition rate is improved.

To further improve the literacy rate among the SC children, State can think of providing remedial teaching with more emphasis on SC children. To stop drop-out rate among SC girls some special monetary benefits can be thought of by the State.

	Ferozpur-

SFD (D)

(Border district)
	· High repetition rate of 8.32% in 6-11 years age group and 13.13% in 11-14 years age group.

· Problem in enrolment of girls due to orthodoxy.

· Transition rate from primary to UPS in the case of girls is not satisfactory.

· Problem of child labour.

· Problem of access to schools due to distance from home to school.

· Problem of retention

· Shortage of teachers.

· Engagement of teachers in non-teaching work. i.e. survey, elections, census etc.

· Large number of CWSN i.e. 7035.

· Large number of 4062 children are OoSC due to household work (638), lack of access (734), earning compulsion 1284.
	· Home based education for 501 under HBE and distribution of aids and appliances

· Educational tour, sports meet.

· Community mobilization.

· Strategies for girl’s education:

i. Enrolment & retention

ii. Special camps

iii. Remedial coaching classes

iv. ECCE centres

v. Up-gradation of 64 PS to UPS


	· There is a need for  remedial/ coaching classes   to address the problem of  high repetition rate 

· Opening of BRCs and NRBCs  for dopouts, child labour, children engaged in  household work

· Intervention of  ECCE

· Innovative programmes like  special enrolment  and retention drives

· Community  mobilization

· Special camps 

· There is a need for focusing attention on OoSC 2510 CWSN numbering.

· There is a need to mainstream 4062 OoSC specially 2191 OoSC from SC in 6-11 years group and 1297 in 11-14 years age group.

	Hoshiarpur: SFD C 

(Gender Gap above 10% at Pri.& 20% at UP)

and D (SC concentrated)

	· 449 Rooms require partial/major repairs.

· Problem of accountability of teachers.

· Low retention of children.

· Absenteeism of students due to engagement of children in household work.

· Lack of strategy for SC children in the district which has 34.28% SC population 

· Building less school.

· Lack of facilities of toilets and drinking water.

· Poor maintenance of buildings.

· Low level of community participation.

· Lack of ECCE facilities.

· Inadequate seating arrangement.

· Lack of ABL.

· Three habitations without primary schools with in 1 kilometer.

· 64 habitations without UPS with in 3 km area.

· 2 villages (with more than 40% SC population) are without PS with in 1km.

· 25 villages are without UPS with in 3km.

· There are 157 OoSC from all communities out of which 74 are from SC in 6-11 years age group.

· There are 94 OoSC from all communities out of which 47 OoSC are from SC in 11-14 years age group.

· Repetition rate is 5.59% in 6-11 years age group and 18.91% in 11-14 years age group.

· Transition rate form primary to upper primary is 89.18%.

· PTR w.r.t. sanctioned post is 19.24 and PTR w.r.t. working posts is 26.71.

· There are 3560 teachers in UPS whereas percentage of female teachers is 0 at UPS.

· There are 2893 teachers at primary level and the percentage of female teachers is 52.25%.

· 310 UPS are without furniture.

· 4004 CWSN have been identified but only 2871 have been enrolled.
	· Distribution of free text books to 31659 non SC primary students and 24099 non SC upper primary students and 74598 free workbooks to SC and non SC students.

· Introduction of Pilot ABL project.

· Remedial coaching for 5% rural students and 10% urban students of classes IV-VIII for 4 months.

· Intervention of ECCE at the cost of Rs. 15 lakhs.


	· There is a concentration of 34,28% SC population  in the district. Therefore, there is a need for following interventions  for SC children:-

· Community  participation

· Setting up alternative schooling facilities in un-served habitations for Out of school children.

· Alternative education interventions for SC children living in difficult circumstances.

· Monitoring attendance and retention of children from weaker sections.

· Context specific intervention in the form of a hostel, an incentive or a special facility as required.

· There is a need   for focussed attention on CWSN as 1133 CWSN are yet to be enrolled out of 4004.

	Amritsar SFD (C) SC >=25% )

	· Lack participation of VEDC members.

· Need of teachers training to support and encourage the SC/ST children

· The fund utilization of district under SC/ST is 100% from last 3 years, the allocation may be increased by planning of different initiative to encourage the SC/ST enrolment.

· Up gradation of EGS to PS: last year 4 EGS were planned to upgrade, but not a single EGS is upgraded.

· Girls Share of girls enrollment at Primary and Up.Primary level is reduced from 47.25 to 44.94 

· Transition Rate has reduced from 89.60 to 84.74.

· 100 teachers post are vacant at Primary Level and 500 posts are vacant at upper Primary level.
	· Need of more meetings with VEDC

· Exposure visit & competitive exams

· Grant for girl’s education has been received in the month of Dec. 08.

· No proposal for additional teacher.
	· Community Mobilization and awareness campaign should be frequently organized.

· Planning can be more broadly by introducing new initiative as district fully utilizing the amount.

· Up gradation should be done for mainstreaming the children.

· Activities like Meena Manch, Teaching of life skills/vocational skills should be implemented.

· District should give more attention for quality aspects.

· Rationalization should be done.



	· Out of 9, 7 blocks have more than 25% SC population. Block Majitha (42%), Jandiala (41%), Gandiwind (38.03%) are major SC concentrated blocks and  SC enrolment in these blocks are 113%,178% and 99% respectively.

· 4 eligible habitations without Primary schools covering 91 children.

· 270 Govt. UP schools are not covered under CAL

	Rupnagar ‘Ropar’ SFD (A) PS:UPS>3:1 


	· Girls Share of girls enrollment at Primary and U. Primary level is reduced from 47.93 to 44.37

· Transition Rate has reduced from 100 to 93.93

· Retention Rate has also reduced from 100 to 86.54 at Primary Level

· 3 eligible habitations without Primary schools covering 130 children. 

· The district GER in 6-11 age group is 83.16 and in 11-14 age group is 82.39 which is very low against state GER 93.22 at Primary.

· The district NER in 6-11 age group is 66.86 and in 11-14 age group is 58.77 which is very low against state NER 93.22 at Primary.

· 244 teachers post are vacant at Primary Level and 170 posts are vacant at upper Primary level.

· 99 Govt. UP schools are not covered under CAL.

· No KGBV and NPEGEL are running in the district.
	· Free text books

· AIE centers

· Remedial Coaching

· 6 para teacher at primary and 300 para teachers at Up. Primary are proposed.
	· Girl’s education environment building strategies should also be implemented.

· District should give more attention for quality aspects.

· Habitation should be covered.

· The district should targeting the GER and NER to be reduced.

· Rationalization of regular teacher may also be done.

· Since girls share has reduced, the KGBV and NPGL should be initialized.

	Gurdaspur SFD (A) PS:UPS>3:1 & (C) Border Area 


	· 2 eligible habitations without Primary schools covering 105 children.

· 88 eligible habitations without U. Primary schools. 

· District improved its PS:UPS from 3.5 to 3.0

· Both Transition & Retention Rate have increased.

· The district GER in 6-11 age group is 88.90 and in 11-14 age group is 87.83 which is very low against state GER 93.22 at Primary.

· The district NER in 6-11 age group is 74.49 and in 11-14 age group is 69.92 which is very low against state NER 93.22 at Primary.

· 1186 teachers post are vacant at Primary Level and 521 posts are vacant at upper Primary level.

· 294 Govt. UP schools are not covered under CAL.

· No KGBV and NPEGEL are running in the district
	
	· Habitation should be covered.

· District should give more attention for quality aspects

· Rationalization of regular teacher may also be done.

· CAL should be implemented.

· To increase girls share, the KGBV and NPGL should be initialized.


6. Comment on the State’s overall direction/ preparedness towards meeting the expected outcomes identified for 2009-10

	SNo.
	Points
	Comments

	1.
	Saturating access at upper primary by up-gradation of upper primary    schools to meet the desired ratio of 2:1 PS to UPS. 
	In order to saturate the access at upper primary level and to meet the desired ratio of 2:1 PS to UPS, a proposal for 69 primary and 649 upper primary schools has been submitted for 2009-10. However, an in-depth study to assess the position in blocks will be done shortly and further requirement if any will be placed at the time of next plan.

	2.
	Saturating requirement of access at both primary level and upper primary level in villages with 40% SC, ST or Muslim population.


	There are 3778 villages with more than 40% SC population, out of which 6 villages don’t possess primary school facility within 1 km radius and 91 such villages which don’t have upper primary school facility within 3 km radius. A proposal for requisite primary and upper primary schools for these villages has been submitted under AWP&B 2009-10 (the proposal is infact included in the proposed 69 primary and 649 upper primary schools).  

There are 45 villages which have more than 40% muslim population. All the villages have upper primary access except one in district Sangrur for which the proposal has been put up under AWP&B 2009-10 (the proposal is a part of 649 upper primary schools proposed for the state).

	3.
	Bringing all children to school by reducing out of school children & tracking the mainstreaming process.


	As per the household survey carried out during January, 2008 there were 100457 out of school children in the age group of 6-14. A large number of interventions were done to bring these children into the fold of education. 42322 children were directly admitted in to the regular schools. 51911 children were covered under non-residential bridge courses and 1007 were covered under residential bridge courses. So in all 95240 children were covered in schools/bridge courses. 

	4.
	Better identification system of children with special needs including survey to improve their coverage.


	IERT teachers have been appointed one each in every educational block in the state. Household survey of special children has been carried out. Software has been prepared to track such children including even photographs of the special children etc.

	5.
	The share of enrollment of Special Focus Groups i.e. girls, SC, ST, and Muslim minority children would reflect their share in the population in the District/State and gaps in enrolment, dropouts, transition & learning levels will be eliminated. 


	(i) The share of girls in the total population of 6-14 years in Punjab is 45% and share of girls enrolled in the school system is 32.74%. 

(ii) So far as the point of SCs is concerned their share in the 6-14 population is 36% whereas their share in the enrolled population in schools is 46.47%. 

(iii)  44.31 % of girls in primary schools stands enrolled and 49.28 % of SC students stand enrolled at primary level. Infact there is an improvement of 5.24% in enrolment at primary level among SC children as per DISE 2008-09.

(iv) Similarly 44.92 % girls and 41.57 % SC student constitute the total enrolment at upper primary level. 

(v) It may also be relevant to state that child sex ratio in Punjab is only 893 per 1000 as per census 2001.

	6.
	Improvement in learning levels and participation of children through specific programmes for reading and mathematics in early primary grades and Science & Maths at upper primary level with independent testing. 


	The State has started the “Parrho Punjab” programme as an intervention to improve the quality of education at primary level during the year 2008-09. The project shall be continued during the year 2009-10 also as substantial improvement in learning level has been noticed. Supplementary material and the special teacher programme shall be carried out to improve the learning level of children. Similarly, special science resource groups have been constituted at district level to monitor the learning levels of the students for math and science. Hard topics have been identified and specific training has been imparted to teachers in these topics during the year 2009-10. It is also apprised that under CAL component, the state has developed the contents in math and science and thus it is felt that this will further improve the learning level in math and science of the students. 

	7.
	The urban provisioning in terms of access, SCR, PTR to be completed and coverage plan of urban out of school children has been developed. 


	Provisions for access SCR and PTR for urban locations are nearly complete. A big part of out of school children of urban locations has been covered in the school system. The freshly identified out of school children would be covered in non-residential and residential bridge course and even in regular schools during the coming academic session. It would be pertinent to mention that 95240 OOSC were covered during 2008-09 and there is a further plan to cover 47165 OOSC under AWP&B 2009-10.

	8.
	All vacant posts of teachers that of State and sanctioned under SSA will be filled by June 09.
	All the vacant posts have been filled up. 10678 posts at primary and 4405 at upper primary level have been filled up during 2008-09.

	9.
	All single teacher schools will have minimum of two teachers at primary level and one teacher for every section at upper primary level.
	There is no single teacher school at primary and no two teacher school at upper primary level as of now.

	10.
	All spillover civil works will be completed before 31st July 09.


	All the civil works sanctioned during 2008-09 are almost complete. However, as per the figures conveyed by EdCIL, it seems that some works have not been taken up in the district. This matter shall be reconciled within the period of three months after collecting information from districts.


8. The major findings of Monitoring Institutes on implementation of the programme
Punjab University, Chandigarh is looking after the monitoring activities for the State of Punjab. The MI has undertaken monitoring activities for the period of 1-10-2007 to 31-03-2008 submitted the reports for 5 districts namely Amritsar, Bathinda, Gurdaspur, Nawanshahr, Sangrur.

Key observations:

1. Textbooks: 

Free text books are made available to children from two sources: State Govt. and SSA. The state Govt. gives free text-books to SC students and girl students from grade I to grade V whereas SSA gives books to students of EGS centres and girl students of general category. Only boys of general category do not get text books. Workbooks are given to all students of grades I to Grade VIII. The distribution of text-books is through BPEO’s office and schools collect the books according to the number of students in each of these categories. In almost all the five selected FIVE DISTRICTS, the books were distributed in April and May, 2007. Text books were distributed during the month of April and May

2. Civil works: 

871 schools in district Amritsar have 3 classrooms.

3. School Grants:

Rs. 2000/- per school is distributed as school grant. Some schools visited by MI in the five districts during October, 2007 to March 2008, reported to have received Rs. 2000/- as school grant in first three months of 2008. Maintaince grants received during the month of October and these grants are used for repairing buildings and furniture.

4. TLM:

 Most of the teachers use their TLM in preparing teaching aids during the training programme.

5. AIE:

Most of the EVs expressed satisfaction with the training. Salary of VT; Volunteer teachers get a salary of Rs. 1000/- each. Volunteer teachers are paid their honorarium of Rs. 1000/- mostly by cheque through the head teacher. Qualifications of VTs; Although the minimum essential qualifications of volunteer teachers is +2, yet most of the volunteer teachers working in various EGS centres are not less than graduates . Some of the volunteer teachers in the EGS centres  are Post graduate degree holders in Hindi, political science, history etc. A few of them even know Typing and shorthand, Training of VTs;
Most of the EVs expressed satisfaction with the training, which they say, increases their know how about teaching learning processes. Volunteer teachers have a very challenging job to attend 30-40 students of different educational and mental levels and keep a pace with them and motivate them to keep a pace with each other. Each one gets a 30 days training provided by DIET or CRC.  The VT's get training in record keeping, teaching methodology etc. 

Volunteer teachers have a very challenging job to attend 30-40 students of different educational and mental levels and keep a pace with them and motivate them to keep a pace with each other. This requires a different pedagogy. Although most of the VTs feel that they are benefited by the training yet they need to be groomed better than the regular mode teachers are.

The achievement level of children studying in EGS clusters is not high. Even in class I to V in elementary schools wherever the MI teams conducted evaluation through snap tests children were invariably found to be poor in English and math's. 

In fact most of them were not even able to read from the books. The children of EGS on that account were not exception. 

Although volunteer teachers seem to develop good rapport with students, they are not able to help in mainstreaming large number of students. 

6. CWSN: 129 camps were organized in 17 districts. 200 teachers who are trained in special education have been appointed in almost all the blocks of all districts. These teachers work in itinerant mode to bring all children with disabilities under the ambit of elementary education and provide them a need based specialized training to the regular teachers of the school so that these children can receive relevant education in regular schools.

7. VEC:

VECs in almost all villages have been formed according to the prescribed guidelines. VEC keeps separate accounts of funds and material for construction. All the construction work is executed by VEC. Instruction Manual has been prepared by SPO and each VEC has a copy of the manual. 

Ramps are being constructed wherever funds have been granted for this purpose. But most of the VEC members are unaware of the exact specifications of construction of ramps. 

VEC keeps separate account of funds and materials for construction. A few sample cheeks of passbooks were done.

8. BRC/CRCs:

BRP's provide academic support and monitoring of class rooms activities and schools, and organize different types of training whereas CRP's are responsible for improving position of enrolment, retention and quality which they do with the help of VEC's. Training to members of VEC, PTA and MTA's is also their responsibility. They hold meetings with cluster head teachers, volunteer teachers etc and prepare a monthly review report. 

9. Research and Evaluation:

Schools have not undertaken any kind of research work, at least the schools visited by MI reportedly have not heard about any research being carried out involving their schools. However state Research Advisory committee was constituted by SSA Authority of Punjab to undertake research in different areas. MI has a representation in this committee. Four research projects were identified and Department of Education Punjab University was asked to take up these projects.

10. NPEGEL:
For education of girls at Elementary School level no additional incentives were proposed or implemented in any district of Punjab. Government of Punjab is however continuing with the scheme of Hazri Vazifa. Meritorious girls, whose attendance in school is 80%, get Rs. 50 per month. All schools are observing it. No other incentives have been implemented apart from this.

There is however a question mark on the regularity of scholarship. Field observations of MI reveal the following facts; (only) sample examples have been quoted. The situation is almost the same in all the districts of Punjab).

10. KASTURBA GANDHI BALLIKA VIDYALYA

No Kasturba Gandhi Ballika vidyalaya has been sanctioned for any of the five districts covered during October, 2007-March 2008. In fact only two KGBV were sanctioned for state of Punjab till 20 March 2008, and both are in District Ferozepur

11. MDM: The schools are serving daily hot cooked food.

Punjab Appraisal Report 2009-10
Page 61

