Special Secretary cum Director General School Education &

State Project Director Sarva Shiksha Abhiyan Authority, Punjab 
Minutes of the Monthly meeting held on 20.03. 2009 to review the Mid Day Meal scheme in the State of Punjab
1.0 A meeting was held in the office of Director General School Education, Government of Punjab, on 20.03.2009 at SCO No 104-106, Sector 34-A, Chandigarh to review the implementation of the Mid Day Meal scheme in the State of Punjab.  Mr. Krishan Kumar, Director General School Education chaired the meeting. 
2.0 List of officers who attended the meeting is enclosed at Annexure 'A'.
3.0 After review of action taken following decisions were taken in the meeting :-
3.1 While initiating discussion, it was noted that requisite information is not received from the DEOs in time and as a result, the meeting loses its very importance.  It was informed in the meeting that the information from the districts Jalandhar, Faridkot and Ludhiana has only been received on 17.02.2009 and as a result it becomes very difficult for the head office to compile and review the issues in the meeting.  It was decided that the explanation of the DEOs Jalandhar, Faridkot and Ludhiana be called immediately under intimation to the State Government;
3.2 Lifting and utilization of foodgrains for Feb., 2009
(i) It was noted that 3161.21 MT of rice and 3153.06 MT of wheat is available as on 28.02.2009 in all the districts to run the Mid Day Meal scheme during the coming months in primary schools.  All DEOs were asked to inform immediately in case there is any shortage of foodgrains in their districts.  Manager Foodgrains informed that districts of Bathinda, Faridkot, Gurdaspur, Mansa and Sangrur did not lift any foodgrains in pursuance of the orders passed by Government of India whereby it was allowed to lift foodgrains of the previous quarters on 31.12.2008.  The DEOs of district Faridkot, Bathinda and Nawanshaher informed in the meeting that they are not short of foodgrains, however, it was noted that in case of Ludhiana, Mid Day Meal scheme was not functional during the month of April and May, 2008.  It was decided that necessary explanation of District Manager, Mid Day Meal Ludhiana be called in this regard.  

(ii) Manager (Food grains) further informed that release orders have also been issued by FCI Punjab.  It was decided that the DEOs may pursue the matter and ensure that  adequate food grains are available to provide Mid day meal in the schools; 

(iii)  It was noted that the lifting and utilization of the foodgrains has been poor in the districts of Sangrur, Fatehgarh Sahib, Mansa, Ludhiana, Muktsar and Patiala. All DEOs were asked to explain the reasons in the next meeting;
(iv) lt was also noted that quality of foodgrains is not checked at the source point as well as the destination point.  As per Government of India guidelines, the DCs are the authority who is responsible to ensure that only Fair Average Quality foodgrain is lifted from FCI godown.  All DCs may be requested again to ensure the compliance of guidelines issued by Government of India asking them further to depute some senior officer of the rank of Assistant Commissioner for this task.;
(v) Observations on lifting of foodgrains during the month are that in district of Bathinda have not lifted any foodgrains during the month.  They were asked to explain the reasons within a fortnight.  Similarly lifting has been poor in respect of wheat in the districts of Faridkot, Mansa, Sangrur, Gurdaspur and Nawanshaher.  All DEOs (EE) were asked to explain the reasons for the poor progress;
(vi)  It was noted that the minimum utilization of the foodgrains should have been 80% percent of the total foodgrains allotted as on 31.01.2009, however the percentage utilization is poor in the district except Sangrur. Districts of Mansa, Jalandhar, Ludhiana, Patiala and Fatehgarh Sahib are the poorest in the percentage utilization of the foodgrains.  It was decided that explanation of DEO concerned be called for the poor utilization; 
(vii) On lifting of the foodgrains for the Upper Primary sections, it was noted that 3404.92 MT of Rice and 3489.90 MT of Wheat is stock in hand of all districts to run Mid Day Meal scheme for Upper Primary sections.  All DEOs confirmed that Mid Day Meal has been implemented in all the Upper Primary Schools in the respective districts. However, it was noted that despite having released the funds for the Upper Primary sections to the districts, the same have not reached to the schools till date.  All DEOs (EE) were advised to get in touch with their DEOs (SE) and resolve all the pending issues. 
3.3 Utilization of Cooking Cost: 
(i)
It was informed by Manager Finance in the meeting that the funds as per the details in the Annexure 'B' attached to these minutes have already transferred electronically to these districts to implement the Mid Day Meal scheme in the schools.  All DEOs were advised to ensure that the funds reach the school without any delay;
(ii)
It was noted that some funds are lying in excess in some of the schools / blocks whereas some of the schools are not having funds.  This is primarily because of lack of adequate information with the DEOs.  It was decided that cooking cost on monthly basis may be calculated in respect of each and every school and the same information be provided to DEOs by head office.  This will perhaps ensure the proper utilization of funds. Similar information may also be prepared for the requirement of the foodgrains i.e. wheat and rice as well.
3.4 Utilization of Cooking Cost vis-à-vis 
Utilization 
of foodgrains.

(i) The information given by the districts was noted to be satisfactory.  It was further noted that the DEOs may verify these figures once again. 
(ii) It was also decided that the Manager Finance and GM (MDM) may inspect one or two districts to know the time taken in releasing the funds and also the figures sent by the district regarding the cooking cost vis-à-vis the utilization of the food grains and submit a report.
(iii) It was further noted that there is a mis-match in the utilization of Wheat vis-à-vis Rice in some of the districts where as the utilization of both Wheat and Rice should have been equal.  For example there is mis match in the districts of Barnala, Fatehgarh Sahib, Ferozepur and Jalandhar between the utilization of Rice and Wheat.  All DEOs were asked to explain the reasons in writing within fortnight;

(iv) On the Upper primary side there is a mis match in the cooking cost actually utilized and the cooking cost as per the norms in district of Gurdaspur.  Concerned DEO was asked to explain the reasons for the same within a fortnight.
4.5.        Progress of Kitchen Sheds
(i) It was noted that out of 4571 kitchen sheds, only 4516 kitchen sheds have been constructed till date leaving a balance of 53 kitchen sheds. The performance was noted to be very poor in the districts of Faridkot, Fatehgarh Sahib, Jalandhar and Tarn Taran. It was decided that a D.O. letter be written to the DCs as well as the DEOS seeking the detailed report in this regard; 
4.6             Procurement of Kitchen devices through PUNSUP
(i) It was noted that out of 4748 gas connections, only 4139 connections have been provided in the schools, leaving a balance of 609.  The major districts who could not even register reasonable progress in procurement of gas connections are Amritsar, Hoshiarpur and Patiala.  It was decided that the re-distribution of the gas connections may be done as per the discussions held in the meeting chaired by M.D. PUNSUP.  The revised list will be sent by the districts within a week and matter may be perused with PUNSUP;
(ii) Few other issues were also discussed in the presence of Superintendent PUNSUP in the meeting which are as follows:
a. It was pointed out by DEOs that the foodgrains are lifted from the FCI godowns from the contractor of the PUNSUP and keep it in their own godowns before sending it to the schools.  During this period the possibility of the mixing the poor quality foodgrains is not ruled out.  It was decided that this matter may be brought to the notice of DCs to look into this matter and also to MD PUNSUP to give directions to their district officers to ensure that no such mixing or supplying less quantity of foodgrains are supplied to schools;
b. It was informed by DEOs that foodgrains are supplied by PUNSUP in the cement bags which is not understandable at all;

c. The DEOs informed that the foodgrains are not being supplied by PUNSUP as per their terms & conditions rather the contractor of the PUNSUP open the bags of foodgrains and deliver the less quantity of foodgrains.  They also do not have any scale for the physical measurement as required by them;

d. PUNSUP does not deliver the foodgrains according to the route chart.  Moreover, the foodgrains are delivered in the schools after the school hours and thus there is no teacher available in the schools at the time of delivery;

e. There is no reconciliation of the bills / accounts by the PUNSUP with the Department of School Education regarding the transportation.

It was decided in the meeting that the references made by DEOs as indicated above may be made to the Deputy Commissioners and the MD PUNSUP requesting to take necessary action on the issues raised above.  DEOs were advised to direct the concerned officers in the schools to ensure that only the correct quantity of foodgrains are accepted in the schools.
4.7
 
Kitchen devices to be procured by D.C.

(i) It was noted that adequate funds have already been released to the D.C.s to procure Gas Bhattis, Fire Extinguishers and Gas connections.  However, as on 28.02.2009, 1154 Gas Bhattis, 1062 Fire Extinguishers and 2123 Gas connections are still required to be procured in the districts. The districts who are still to register a reasonable progress in procurement of kitchen devices are Amritsar, Gurdaspur, Jalandhar, Hoshiarpur, Ludhiana, Patiala and Sangrur.  It was decided that a letter may be written to all the DCs seeking reasons for such poor performance.   The matter may also be brought to the notice of Chief Secretary, Punjab.  

(ii) A meeting at the level of Principal Secretary, Government of Punjab, Department of Food and Supplies was held and issues relating to providing gas connections etc were discussed in detail.  It was informed in the meeting requisite information has been collected in the districts and the same has been sent to the Gas Agencies.   It was decided that a meeting may be held at the level of DGSE inviting the Gas Agencies to take further necessary action in this regard.
4.8
          Storage Bins



(i)
It was noted that out of 13423 schools, only 6620 schools have been provided Storage bins leaving a balance of 6489 schools where such storage bins to store wheat and rice and other items are required to be stored.  The details where storage bins still need to be provided are at Annexure C to these minutes.  All DEOs were advised to get in touch with the DCs and ADC (D) in their respective district in this regard.  A reference in this regard may be made to Deputy Commissioners and ADCs (D) expediting the delivery of storage bins of specific capacity.



(iii)
It was decided that a reference may be made to all the ADC (D) and the DCS by the Head Office asking them to provide such storage bins without any further delay.
4.9

Disposal of Used Bardana

It was noted during previous meeting with great concern that the used Bardana is not being disposed of by the districts in a time bound manner.  Moreover the used Bardana is not being accounted correctly.  It was therefore decided previously that Manager Foodgrains may clearly calculate the quantity of the used Bardana in respect of each and every district on the basis of the utilization of the food grains during the previous years, the quantity of Bardana disposed of by the districts the balance Bardana so calculated may be compared with the Bardana which is physically present in the districts. 
4.10            Health Check Up
(i) District of Ferozepur, Sangrur and Ludhiana has not sent the health check up reports during the month of Jan. 2009.  Similarly some of the districts have not even sent the health check up reports during the month of July, August and September also.  It was decided that a reference may be made to Secretary Health requesting to direct the Civil Surgeons of these districts to send the reports to this office;
(ii) It was informed in the meeting that detailed discussions were held with Secretary Health in the meeting held on 02.01.2009.  Certain information is required by the Department of Health from the Department of Schools as per the details given below (separate minutes have also been sent to the DEOs in this regard):

a. Health registers are to be maintained in all the schools;

b. The Nodal Officer be identified and nominated by the Department of School Education for each school for health check up;
c. Health cards are to be maintained in all the schools and certain information needs to be filled up and maintained by the school teachers themselves;

d. A certificate need to be given by the school teacher certifying whether the medical officers has visited in the school and have conducted the health check up or not;

e. The DEO shall provide a list of schools which was not visited by the health officers up to 31.01.2009 during the current financial year so that the same can be forwarded to the Department of Health for taking further necessary action.
4.11 Minutes of the meeting of the District Level Steering and Monitoring Committee
(i)
It was noted that the all the districts except Patiala, Kapurthala, Bathinda, TarnTaran, Ferozepur and Nawanshaher held the monthly meeting to implement the scheme at district level.  It was decided that a reference may be made to the DCs to hold this meeting regularly.
4.12 Utilization Certificates
(i) It was noted that utilization certificates of the cooking cost for the primary schools has been received for the year 2007-08 from all the districts.  However the utilization certificates of the cooking cost (Primary Classes I – V) for the funds released during the year 2008-09 are still pending from the districts as per the details given below:
                                                                         (Rs. In Lacs)
	Sr No
	Name of the district
	Amount Released 
up to 

30.09.2008

	U.Cs received
	U.Cs pending for the amount

	1
	Amritsar
	814
	295
	519

	2
	Barnala
	228
	75
	153

	3
	Bathinda
	429
	150
	279

	4
	Faridkot
	260
	77
	183

	5
	Fatehgarh Sahib
	309
	100
	209

	6
	Ferozepur
	726
	161
	565

	7
	Gurdaspur
	741
	242
	499

	8
	Hoshiarpur
	704
	220
	448

	9
	Jalandhar
	752
	193
	559

	10
	Kapurthala
	338
	107
	231

	11
	Ludhiana
	876
	216
	660

	12
	Mansa
	230
	13
	217

	13
	Moga
	585
	217
	368

	14
	Mukatsar
	289
	150
	139

	15
	Nawan Shehr
	271
	62
	209

	16
	Patiala
	662
	115
	547

	17
	Ropar
	312
	107
	205

	18
	Sangrur
	561
	139
	422

	19
	SAS Nagar
	277
	124
	153

	20
	Tarn Taran
	412
	44
	368

	
	Total
	9776
	2807
	6933


All DEOs were advised to expedite the utilization certificates of the pending amount without any further delay.  A reference may also be made to all the DCs concerned also in this regard.  Further utilization certificates of the cooking cost for the upper primary schools may also be provided.
4.13

Miscellaneous Issues:-
(i) It has come to the notice that the funds are lying with the BDPOs of district Gurdaspur against cooking cost.  DEO 
Gurdaspur was asked to collect the information from BDPOs and also receive the funds.  A reference in this regard may also be made to the Deputy Commissioner, Gurdaspur to intervene into the matter; 
(ii) It was noted that mid day meal is being provided in the districts of Ferozepur, Tarn Taran and Nawanshaher through Voluntary Agencies. Before starting the scheme from 15.09.2008 in the revised mode, some funds and the foodgrains must be lying in the schools.  However, no action has been taken by DEOs Ferozepur, Tarn Tarn and Nawanshaher.   DEOs were advised once again to take the necessary action under intimation to the head office without any delay failing which the responsibility shall be fixed in case of any embezzlement comes to the notice of this office.
Special Secretary cum Director

General School Education &

SPD SSA, Punjab

Encls: As above
PAGE  
2

